## README
Proto Switcher — Integration DVP + FMEA v1.4 (draft, 2026-10-16) — CSX4091 drivetrain energy decomposition; demo charge limit 2.1 MW / 1,666 A (ground ESS) drives Showcase 2
Purpose: guide final integration at Cerritos -> Huntington -> dead-in-tow -> Jacksonville toward the end-Feb showcase, then the CSX 90-day evaluation.
Showcase 1 — Wheels turning: accelerate to 10 mph (TBD), hold 20 min. Showcase 2 — Dynamic charging at 0.5 mph, up to 2 mi or pack full, at the demo charge limit: 2.1 MW at the wire (0.5C of the 4.2 MWh Jacksonville ground ESS) and no more than 1,666 A wire current (2 x 833 A DPS100) (DR-17). The 4.2 MWh here is the wayside ground ESS, not the retired 4.2 MWh locomotive pack.
Huntington exit (Dragan, Oct 6): wiring added and audited; HV system Megger; Voltify + Integral SW/FW loaded; idle power-on with zero Class A faults; first movement forward and reverse (Class B faults may be overridden and logged, then fixed in Jacksonville).
Tabs
DVP — every test: gate, site, what it proves, pass line, equipment, criticality, link to FMEA. Status column is editable (dropdown). Yellow rows are new in v0.4.
FMEA — what could go wrong, scored S/O/D 1-10. RPN = S x O x D (formula). AP = simplified AIAG-VDA action priority (formula). 'Plain English' column is for execs. Yellow rows are new in v0.4.
Demo Requirements — requirements tagged Stated / Document / Derived / Assumption / Open, with source. Use the Bill decision column.
Fault Classes — A (blocks motion) / B (overridable, logged) / C (information); override rules; fault-code register template.
Load Cases & Perf — GP40 reference performance, switcher load cases (trailing tons), EPA switch duty cycle energy estimate, Jacksonville ramp-up matrix. Blue cells are inputs.
Data Logging — signal list, sources, rates and why each is needed (range, performance trend, fault triage). Logging starts at first LV power at Huntington.
Gates — exit criteria per gate (the go/no-go checklist).
Equipment & Access — what the production lead must have on site, per site.
Conflicts (RSK) — contradictions and gaps between sources; proposed RSK entries.
Energy — charge-window model and dead-in-tow standby model. Blue cells are inputs.
v0.4 changes (2026-10-07, from Bill/Dragan call Oct 6)
1) G3 is now a REQUIRED Huntington exit gate: H-31 idle readiness, H-12 creep, H-13 first movement fwd/rev. Extended pre-check (H-14..H-18, H-21) moves to optional G3+.
2) New Huntington tests: H-29 system Megger, H-30 SW/FW load + version manifest, H-31 idle readiness with fault classes, H-32 data logging live from first power, H-33 electric handbrake works with 72 V off.
3) Dead-in-tow: unit acts as a railcar (CCB-2E dead-engine regulator; 49 CFR 229.9 non-complying move; Parts 231/232). Compressor not required. Grounding-switch padlock optional.
4) HSCB not needed for demo; HSCB and MCS tests move to P1 Post-demo (P-03, J-13).
5) New G10 performance ramp at Jacksonville (J-14..J-19, non-gating) to trend toward CSX targets: Notch 8 for 15 min and continuous pull at 10 mph. P1 gate (CSX 90-day) holds the pass/fail versions (P-01..P-05).
6) Pack basis corrected to 5.02 MWh (48 batteries, 6 strings, Oct 6 decision). Charge cap 2.5 MW (0.5C). 4.2 MWh Phase 1 retired.
7) FMEA F45..F53 added; F04, F06, F09, F22 updated. RSK-NEW-16..21 added; NEW-02, NEW-03, NEW-11 updated.
8) Load case: 20-50 tons/day (as stated) is less than one loaded car. Proposed per-move load cases LC-0..LC-3 and the EPA switch duty cycle (40 CFR 1033.530) as the default energy profile, pending CSX Moncrief data.
v1.4 changes (2026-10-16, CSX4091 drivetrain energy decomposition)
1) decompose_csx4091.m (loco_system) run on results_csx4091_20261016_0823.mat (Rev C: 42 in wheel, Integral chopper loss, D77 flux, 536 kW cap, regen off). Balance closes exactly (residual 0.0 kWh, Ah vs SOC 0.00%). Chopper loss basis confirmed Integral sim from signals. Output results/decompose_csx4091_20261016_0823.csv. C-26 decomposition half done; numerics half still open.
2) Yard day (25.5 h, 813 kWh from the battery, SOC 90 -> 74.4%): aux budget 209 kWh (25.7%), TMS 88.7 (10.9%), aux converter 12.4 (1.5%), motor copper 110.5 (13.6%), chopper 11.4 (1.4%), gear 11.4 (1.4%), battery I2R 0.5, wheel 369.1 (45.4%). Of the wheel energy: rolling 194.4, friction brake 181.6, grade -8.0, aero 1.1. Motoring-window efficiencies: chopper 97.7%, motor 77.4%, gear 97.0%; battery-to-wheel 59.5% while motoring, 45.4% over the day. Loco at standstill 66% of the time; 123 kWh to the aux bus while stopped.
3) Corrections: System Model D94 said battery-to-rail ~64% (that was drivetrain energy / battery out); the decomposition gives 45.4% whole day. Model wheel energy is 9-11% above the recorder rail energy (yard 369.1 vs 331.1 kWh; peak2h 85.7 vs 78.4). RSK-NEW-51 friction figure updated (181.6 kWh).
4) New RSK-NEW-54 (motor resistance basis, largest drivetrain loss), RSK-NEW-55 (aux + TMS share of daily energy / standstill power management), RSK-NEW-56 (model vs recorder +10%). RSK-NEW-18, -19, -28 annotated. Energy tab: yard-duty days-per-charge block. No FMEA score changes.
v1.3 changes (2026-10-16, demo charge limit and Jonathan dashboard review)
1) REQUIREMENT: Showcase 2 charge limit is 2.1 MW at the wire (0.5C of the 4.2 MWh Jacksonville ground ESS) and no more than 1,666 A wire current (2 x 833 A DPS100) (Jonathan, dashboard comment 2026-10-12; adopted by Bill 2026-10-16). Replaces the 2.5 MW (0.5C x 5.02 MWh) cap and retires the 3 MW dynamic target for the demo. At the loco this is 0.42C, inside the Jinko 0.5C rating.
2) Updated to the limit: README, DR-14/DR-17/DR-23, Energy tab, DVP J-03/J-06/J-09/J-10 and new J-25 (wayside limit verification), FMEA F06, RSK-NEW-03 (closed for demo), -22, -36, -39, Thermal Sweep and System Model notes. S3 (2.5 MW) and S4 (3 MW) become bounding cases above the demo limit; new model trace S9 (2.1 MW) and test C-27.
3) Jonathan review (10 dashboard threads, Oct 12-14): RSK-NEW-01 closed (Integral is the only master of the DC-link to TRB-bus contactors); RSK-NEW-04 ITV date Oct 19 target, end of Oct latest, and dynamic charging without the ITV ruled out (new RSK-NEW-52, FMEA F69); RSK-NEW-06 lowered (continuous ground-fault detection exists; check it senses the TRB-bus); RSK-NEW-43 partial control (pantos fold only after the panto contactor panel opens); F05 string-loss response (isolate that string, derate, alert); RSK-NEW-07 adds Jonathan; RSK-NEW-08 owner Jack -> Micah (confirm the row); RSK-NEW-17 rewritten in v1.2 answers the Notch 8 question.
4) Scores: S/O/D changed only where noted (F06 O 6->3, F15 O 6->4); others unchanged pending Bill review.
v1.2 changes (2026-10-16, model Rev C and supplier data)
1) Model Rev C (System Model tab): D77 flux from the D77-D78 curve (Jonathan, 40 in / 62:15; legacy fit was 10-26% low below 600 A), D77 ratings 1050 A cont / 1150 A 15 min / 1500 A 5 min, 42 in wheels (to confirm), chopper loss from Integral simulation (2.47 kW at 1170 A, 500 Hz; was 5.25 kW at 1050 A deck basis), motor power cap option 536 / 373 kW.
2) Integral reply (J. Jankowski, 2026-10-15): HV lab test was stall-only, dry, 1000 V / 1000 A for ~5 min, cold plate high 40s C; no measured efficiency. Controls: 2 ms chopper loop, 10 ms CAN and LCC loops, ~22 ms worst case; OC/OV trips local in hardware. AUX-B002: 55 C is the coolant INLET limit; 0.8 bar is nominal at 30 L/min; ~6 C rise at 30 L/min; onboard cold-plate derate. Charger losses vs power still open.
3) CSX4091 Jacksonville yard trace (Aug 26-27, 25.5 h) run on Rev C vs legacy: battery out 812 vs 841 kWh (-3.4%), TMS 89 vs 96 kWh, SOC 90->74.4% (OPTIMAL). Chiller stayed off on Rev C only because peak cell 27.2 C sits just under the 28 C chiller-on threshold.
4) Notch 8 (S6): the DERATED verdict was a Phase 3 report bug (speed check forced on; Phase 2 defines S6 v_ref as unreachable). Physics: 3,640 t on 0.5% needs 3.17 MW at the rail for 30 mph; 2.144 MW balances at 20.4 mph, 1.49 MW (500 hp/motor) at 14.2 mph. RSK-NEW-17 updated.
5) RSK-NEW-17/18/38/39/40 updated; new RSK-NEW-47..51. FMEA F49, F65, F66 text updated (S/O/D unchanged, Bill to re-score). DVP C-24 in progress; new C-25 (Rev C, passed) and C-26 (Rev D, planned); notes on J-17, J-22, H-35.
6) Not in this version: Jonathan v1.1 comments (not accessible from the assistant; add on review).
v1.1 changes (2026-10-10, HSCB retained for demo)
1) HSCB retained for the demo; RSK-NEW-16 proposed closed (owner Jonathan Ronai, Integral POC). Basis: the ITV (Integral AUX-B002) is a non-isolated bidirectional buck/boost, so its freewheel diodes let the traction battery feed any roof or charging-bus fault; the ITV-bypass fallback and direct-to-TRB MCS also put the battery on the charge bus. Contactors cannot break this; string fuses are slow and split 6 ways; dynamic charging needs a resettable interrupter. Supersedes v0.4 item 4 (Dragan, Oct 6); Dragan review pending.
2) Closure conditions: (a) Integral confirms the ITV freewheel back-feed path; (b) Jinko pack/string short-circuit impedance (prospective fault current); (c) Secheron trip curve clears it within busbar/cable I2t limits.
3) DVP: J-05 updated; new J-23 (HSCB trip and interlock) replaces P-03; new J-24 (roof bus dead with pantographs down). Gates G7 and P1 updated.
4) FMEA: F09 updated; new F67 (battery back-feed into a roof/charge-bus fault) and F68 (roof bus live through ITV diodes). DR-42 and DR-05 updated. RSK-NEW-43..46 added. System Model L05 and Spares 6.1.2 updated.
5) Not swept: Confluence/Jira (Rovo access denied). No AES charger short-circuit or trip-time data found in Drive.
v1.0 changes (2026-10-10, PE loop update, fault sweep re-run, native model regression)
1) PE loop parameters per Vince KULI review (2026-10-09; 3 SPAL pumps at 4500 rpm, 223 L/min, 40 C): chopper coolant 1180 W/K (was 1430), front inverter 1100 W/K (was 950) on the poc baseline; phase2 baseline frozen. New fault PE_PUMP_1OF3 (one of three pumps out, 95.4% flow).
2) Fault Sweep tab re-run 2026-10-10 (20 faults x 20/40/45 C): no verdict or relative-to-baseline changes. Chopper peaks +0.7-0.9 K (less flow per chopper), inverter peaks -0.1 K (more flow). PE_PUMP_1OF3 = SAME at every ambient.
3) Supplier data gaps from the KULI review and the Integral datasheets: chopper loss basis (model 1.5 kW vs KULI 4.0 kW per chopper at 425 A; ITC-0002 lists no losses) and charger coolant limit and flow (AUX-B002: 55 C, location unstated; KULI 40 C: 59.0 C outlet, 29.7 vs 30 L/min per passage). New FMEA F65/F66, RSK-NEW-38..42, tests C-24, H-35, J-22. Data request to Integral via Jonathan (2026-10-10).
4) Model: native Simscape plant (native/loco_native.slx, switchable with the Phase 3 plant via PLANT_ID) passes 11/11 regression cases vs Phase 3 across S1-S8 at 25/40 C, including 8 h, 6 h and 3 MW cases (C-23 passed). Phase 3 solver min-step events at traction transitions logged as RSK-NEW-40.
v0.9 changes (2026-10-08, fault sweep on the POC baseline)
1) Fault Sweep tab replaced: 19 faults x 20/40/45 C on the POC baseline (12 kW heater, POC load budget incl. SPAL fans, MTM COP map, 2.6 kW pumps). New LRU faults: BTMS_24V_PS_TRIP (all pumps) and BTMS_12V_PS_TRIP (all chillers).
2) Results match the previous sweep within ~1 K except PE fan loss at 20 C (margin now 8 K, lower aux heat). BTMS 24 V supply trip is as severe as PE pump loss: F61 and the DCC65M24 spare confirmed. C-21 marked re-run.
3) Model fixes behind this run: automatic states evaluated every 1 s (S8 had stayed in SLEEP), UseBudget option, plot autoscale (MODEL_NOTES Phase 3 fixes).
v0.8 changes (2026-10-08, alignment with POC Power Budget Rev B)
1) System Model tab load budget rebuilt from Micah POC Power Budget (IDs, buses 750V/72V/24V_Ctrl/24V_BTMS/12V_BTMS, nominal/peak, converter efficiencies). Totals: ~0.8 kW STANDBY, ~3.6 kW READY/TRACTION + 12.75 kW blowers when moving, ~3.7 kW CHARGING (at the 750 V bus).
2) Model thermal baseline: heater 12 kW (1 x HVH120), 12 kW cooling per MTM, compressor 3 kW nominal / 8 kW peak, pumps 2.6 kW. Radiator fans kept as EMP (KULI) by decision; SPAL VA117 in the POC sheet is a conflict (RSK-NEW-35).
4) New Spares tab: initial risk-based spares plan (75 BOM lines; aligned to Jonathan's targets where higher) from Jonathan's Locomotive Kit FULL BOM, linked to FMEA/RSK/fault sweep; go-kit (Huntington, travels with the loco) vs Jacksonville depot; delta vs BOM spare targets; reduce-when triggers.
3) Effects (model): hot-ambient verdicts unchanged; TMS energy +10-16%; cold-soak recovery 0->5 C now ~4.0 h (was ~1.9 h). F56/F58/F60 and DR-55 updated; RSK-NEW-25 decided; RSK-NEW-34..37 added. Thermal Sweep and Fault Sweep tabs were run on the previous baseline (re-run C-21/C-22).
v0.7 changes (2026-10-08, Phase 3 fault sweep, 54 runs)
1) New tab Fault Sweep: verdict and relative-to-baseline matrices, findings, full 54-row results.
2) FMEA: F55 occurrence raised (45 C baseline exceeds check valve); F59 updated with timing; new F61 PE pump failure, F62 axle cut-out tonnage, F63 cell temperature sensing bias, F64 traction motor blower loss.
3) DVP: C-21 passed; new C-22 (sweep v2: 8 h duty, breakaway resistance), H-34 (PE loop fault detection on the loco). RSK-NEW-30..33.
v0.6 changes (2026-10-08, MATLAB Phase 3 system model)
1) New tab System Model: Phase 3 structure, auxiliary load budget by operating state (15 loads), fault library (17 faults) mapped to FMEA, team demo results.
2) PE radiator fans are hot-day critical: F54 updated; new F59 (PE fan bank failure) and F60 (aux budget assumption); J-20 adds fan status; Data Logging group 18 (TMS actuator status).
3) Tests: C-20 Phase 3 regression vs Phase 2 (passed); C-21 fault sweep (planned, feeds FMEA O/D). RSK-NEW-28/29. DR-55.
v0.5 changes (2026-10-08, MATLAB Phase 2 thermal sweep, 80 runs)
1) New tab Thermal Sweep: verdict matrix (8 scenarios x 0/10/20/40/50 C x soaked/preconditioned) and full MATLAB results (proto_loco Phase 2, verified against Python replica).
2) FMEA F54..F58 (PE loop hot ambient, condenser loop/check valves, BMS cold cutoffs, heating setpoint, preconditioning). RSK-NEW-22..27. DR-52..54.
3) New tests: C-19 model re-run with measured thermal data; J-20 hot-day PE loop trend; J-21 preconditioning time and energy.
Edit rules
Edit only: DVP Status/Owner/Notes, FMEA S/O/D/Owner/Action, blue cells on Energy and Load Cases & Perf, Fault register rows. Add tests as new rows; keep IDs unique.
Cerritos coverage: Full = proven before ship; Partial = proven at reduced power (one combiner) or on bench; None = first proven on the locomotive.
Sources reviewed
v0.3 sources plus: Dragan call notes (Bill, Oct 6); voltify_dynamic_charging_demo_plan.md (Oct 6); NYAB CCB-II description (dead engine regulator, 16CP backup); 49 CFR 229.9; 40 CFR 1033.530 (switch duty cycle, notch power levels); GP40 data sheet (54,700 lbf continuous @ 11.1 mph, 62:15, D77).
Not swept: CET Jira, Confluence, Smartsheet Gantt, GP40 operating manual (Dragan to send). Values are draft; TBD numbers need owner confirmation.

## Demo Requirements
ID | Group | Requirement | Value | Type | Source | Bill decision | Notes
DR-01 | General | Showcase location and date | Jacksonville, end of February | Stated | Bill, Oct 6
DR-02 | General | Demo metrics: wheels turning, traction capability, deployable pantograph, dynamic charging | 4 functions | Document | Timeline Status meeting, Oct 6
DR-03 | General | CSX operation before the showcase | 1 month; running at Moncrief by ~Jan 20 for ~Feb 20 | Document | Timeline Status meeting, Oct 6 (Daphna)
DR-04 | General | Wheels turning is shown before pantograph charging | Order of demos | Stated | Bill, Oct 6
DR-05 | General | MCS manual charging not needed for the first month | Post-demo | Stated | Dragan via Bill, Oct 6 call |  | HSCB retained for demo in v1.1 (DR-42)
DR-06 | Showcase 1 | Accelerate and hold steady speed | 20 minutes | Stated | Bill, Oct 6 ('assume 20 minutes for now')
DR-07 | Showcase 1 | Steady speed | 10 mph | Assumption | Yard switcher duty; Bill's speed is TBD
DR-08 | Showcase 1 | Run in both directions | Forward and reverse | Stated | Dragan via Bill, Oct 6 call |  | Also required for Huntington first movement (DR-29)
DR-09 | Showcase 1 | Light engine, no train attached | Light engine | Assumption | Claude
DR-10 | Showcase 1 | Track needed | ~3.3 mi or repeated passes | Derived | DR-06 x DR-07
DR-11 | Showcase 1 | Battery current limit during runs | <= 1,884 A peak | Document | Voltify-System-Architecture.md, ESS table
DR-12 | Showcase 1 | Component temperatures during runs | Inside supplier limits | Assumption | Limits not yet sourced from Integral, Jinko, Maxwell
DR-13 | Showcase 2 | Dynamic charging speed and distance | 0.5 mph average, up to 2 mi | Stated | Bill, Oct 6
DR-14 | Showcase 2 | Charge power | Up to 2.1 MW at the wire (demo charge limit, DR-17) | Stated | Bill, Oct 6 (near 2.5 MW); superseded by DR-17 demo limit, Oct 16 |  | v1.3: was "Near 2.5 MW"
DR-15 | Showcase 2 | Charge time limited by battery capacity | Rule | Stated | Bill, Oct 6
DR-16 | Showcase 2 | Pack energy | 5.02 MWh (48 batteries, 6 strings) | Document | Dynamic charging demo plan, Oct 6 (confirmed decision) |  | v0.4: 4.2 MWh Phase 1 retired
DR-17 | Showcase 2 | Demo charge limit (wayside ground ESS) | 2.1 MW at the wire (0.5C of the 4.2 MWh Jacksonville ground ESS) and no more than 1,666 A wire current (2 x 833 A DPS100) | Stated | Jonathan (dashboard comment, 2026-10-12): Jacksonville ground ESS rating and DPS100 converters | Adopted 2026-10-16: drives Showcase 2 | Loco side 0.42C (inside Jinko 0.5C). Replaces 2.5 MW (0.5C x 5.02 MWh) cap; 3 MW dynamic target retired for the demo (RSK-NEW-03 closed for demo).
DR-18 | Showcase 2 | Usable SOC window | 10-90% | Assumption | Claude; replace with Jinko/BMS window
DR-19 | Showcase 2 | Start SOC | <= 20% | Assumption | Claude; maximizes charging window
DR-20 | Showcase 2 | Segment A: hold cap while moving | >= 10 minutes | Assumption | Claude
DR-21 | Showcase 2 | Segment B: full 2 mi at reduced power | ~1.03 MW | Derived | DR-13, DR-16, DR-18
DR-22 | Showcase 2 | Pantograph operation | Automatic | Document | HLR, Sep 2026
DR-23 | Showcase 2 | Pantographs in contact while charging | 2 heads (971 A each x unbalance factor) | Document | HLR, Sep 2026; architecture doc 'two per leg' |  | v1.3: at the 1,666 A wire limit, ~833 A per head with 2 heads (below 971 A per head)
DR-24 | Showcase 2 | Charging losses | Measure now; deep-dive later | Stated | Bill, Oct 6
DR-25 | Showcase 2 | No dynamic or regenerative braking on prototype | Not supported | Document | HLR, Sep 2026
DR-26 | Tow & sites | Move Huntington -> Jacksonville | Dead-in-tow in a CSX train | Stated | Bill, Oct 6 (correction)
DR-27 | Tow & sites | Cerritos pre-check capability | Single string/combiner, ~1/6 power, full voltage | Stated | Bill, Oct 6
DR-28 | Tow & sites | Packs at Huntington | Arrive with some SOC; manual power-supply charging | Stated | Bill, Oct 6
DR-29 | Tow & sites | Wheels-turning check at Huntington | Required: first movement forward and reverse before tow | Stated | Dragan via Bill, Oct 6 call |  | 20-min run (H-14) stays optional
DR-30 | Tow & sites | Tow SOC window | 30-50% | Assumption | Claude; floor ~22% derived; CSX hazmat review needed
DR-31 | Tow & sites | Tow monitoring | Lean telemetry (~60 W) on 72 V battery + logger | Assumption | Claude; 72 V battery 650 Ah per GP40-V spec
DR-32 | Safety | E-Stop timing T1, T2, T3 | TBD seconds | Open | Proto Switcher deck
DR-33 | Not tested in demo | Operating temperature range | -30 C to +55 C | Document | HLR, Sep 2026
DR-34 | Not tested in demo | Tractive effort and power similar to GP40-2 | 2,000-3,000 HP | Document | HLR and GP40-V spec (gap NEW-12) |  | Now trended at JAX (DR-44, DR-45, DR-51); pass/fail at CSX 90-day
DR-35 | Tow & sites | Dead-in-tow unit behaves as a railcar: CCB-2E dead-engine setup; moved as non-complying locomotive under 49 CFR 229.9 with CSX restrictions; Part 232 Class I brake test; Part 231 safety appliances | Rule | Document | Dragan (Oct 6) + NYAB CCB-II description + 49 CFR 229.9 |  | CSX mechanical sets speed/position restrictions
DR-36 | Tow & sites | Brake compressor not required for the tow | Not required | Stated | Dragan via Bill, Oct 6 call |  | MR charged from brake pipe via dead-engine regulator
DR-37 | Tow & sites | Grounding switch padlock during tow | Optional | Stated | Dragan via Bill, Oct 6 call |  | HV contactors still open and verified de-energized
DR-38 | Huntington exit | All wiring added and audited for accuracy | 100% audited | Stated | Dragan via Bill, Oct 6 call |  | H-02
DR-39 | Huntington exit | HV system insulation test (Megger) | Pass before first HV | Stated | Dragan via Bill, Oct 6 call |  | H-29; pass limit TBD (proposed >= 0.75 Mohm at 1,500 V)
DR-40 | Huntington exit | Software/firmware loaded: Voltify and Integral | Version manifest signed | Stated | Dragan via Bill, Oct 6 call |  | H-30
DR-41 | Huntington exit | Readiness: idle power-on; comm faults minimized; zero Class A faults; Class B may be overridden for movement and fixed at JAX | Fault classes A/B/C | Stated | Dragan via Bill, Oct 6; fault classes confirmed by Bill Oct 7 |  | Fault Classes tab; H-31
DR-42 | General | HSCB retained and functional for the demo (charge-path fault interruption) | Demo | Derived | RSK-NEW-16 closure analysis, Oct 10 (ITV AUX-B002 datasheet; DEMO Loco Config & Fallbacks, Sep 2026) |  | v1.1: supersedes Oct 6 position (Dragan: not needed). Dragan review pending. J-05, J-23; RSK-NEW-16
DR-43 | Post-demo | CSX 90-day evaluation: reasonable interruptions accepted; performance converging to diesel-like by day 90 | 90 days | Stated | Dragan via Bill, Oct 6 call |  | P1 gate
DR-44 | Performance | Notch 8 (full power) held for 15 minutes | 15 min | Stated | Dragan recollection; confirm in GP40 manual |  | ~2.5 MW at battery = ESS peak (Load Cases tab); v1.3: Notch 8 is power-limited at 2.144 MW (RSK-NEW-17); unrelated to the charge limit
DR-45 | Performance | Continuous pull at 10 mph sustained | GP40 ref: 54,700 lbf @ 11.1 mph | Stated | Dragan; reference value from GP40 data sheet (thedieselshop.us) |  | ~1.25 MW at battery; duration TBD from GP40 manual
DR-46 | Duty | Switcher service: frequent stop/go, fast acceleration | Switch duty | Stated | Dragan via Bill, Oct 6 call |  | EPA switch cycle used as default profile (DR-48)
DR-47 | Duty | Daily load handled at CSX (post-demo) | 20-50 tons/day (as stated) | Stated | Dragan via Bill; confirmed "tons" Oct 7 |  | Less than one loaded car (~130-143 t); see RSK-NEW-18
DR-48 | Duty | Proposed load cases and duty cycle for test and range | LC-0..LC-3 + EPA switch cycle; LC-3 = protect case | Assumption | Claude: 40 CFR 1033.530; GP40 continuous TE. Bill Oct 7: protect for normal CSX yard ops |  | LC-3 protect case holds unless CSX yard data shows heavier normal cuts
DR-49 | Performance | Range / energy per shift | Determine empirically | Open | Dragan via Bill, Oct 6 call |  | First estimate on Load Cases tab; J-18, J-19
DR-50 | Data | Log required signals from first LV power at Huntington; cloud sync (Starlink, Matan) | Data Logging tab | Stated | Bill/Dragan, Oct 6 |  | H-32
DR-51 | Performance | Jacksonville ramp-up test plan shows trend toward DR-44 and DR-45 | Trend, non-gating | Stated | Bill, Oct 7 |  | J-14..J-17
DR-52 | Thermal | Operating ambient envelope | TBD (model swept 0-50 C) | Open | Maxwell TMS designed for -10 to 45 C |  | Sweep: fails at 50 C (PE + condenser); RSK-NEW-23
DR-53 | Thermal | Pack preconditioned (TMS on standby/wayside) before each duty | Required to stay OPTIMAL/OK at 0-40 C | Assumption | Claude, from Phase 2 sweep (Oct 8) |  | Soaked starts need 1.2-3.6 h recovery; J-21
DR-55 | Power | Auxiliary power budget by operating state (excl. TMS and traction), at the 750 V bus | ~0.8 kW STANDBY, ~3.6 kW READY/TRACTION + 12.75 kW blowers when moving, ~3.7 kW CHARGING | Document | POC Power Budget Rev B (Micah, 2026-09-22) via loco_system/load_budget.csv; state mapping is ours |  | Phase 2 assumed 30 kW base + 42 kW moving; validate in H-17/J-18
DR-54 | Thermal | BMS temperature thresholds are owned by Voltify (Jinko as-shipped values adjustable) | Voltify-set | Stated | Bill, Oct 7 |  | F56, F57; RSK-NEW-24, -26
Type key: Stated = Bill said it (incl. Dragan relayed by Bill); Document = named file/meeting/regulation; Derived = calculated; Assumption = Claude proposal, needs decision; Open = no value yet.
Stated
Document
Derived
Assumption
Open

## DVP
Test ID | Gate | Location | What we prove | Subsystems | Owner domain | Suggested lead | Preconditions | Method | Pass criteria | Equipment / access | Showcase criticality | Cerritos coverage | FMEA link | POC tracker (10/01) | Notes | Status | Date done | Result / evidence link
C-01 | G0 Bench | Cerritos | VMS boots and sees every node on all 4 CAN buses + Ethernet | VMS, Kvaser ETH-CAN gateway, ETH switch | Voltify | Micah / Jared | VMS image under config control (Jared release process) | Node census script: list every expected node ID per bus; compare to ICD | 100% of expected nodes present; bus load <40%; zero error frames over 30 min | CAN analyzer, VPN to VMS | MUST | Full | F21 | VMS bring-up; gateway integrated |  | Not started
C-02 | G0 Bench | Cerritos | LCC<->VMS CAN spec R2 works end to end (SIL) | VMS, LCC (Integral code), Simulator v1.4 | Voltify + Integral | Micah + Bailey (Integral) | DBC/simulator updated to PGN 65283 | Run Integral LCC build against Voltify simulator; script every message: ready-to-run, power limit, SOC, E-Stop, deep sleep, inverter request/status | Every PGN decoded both directions; power-limit change honored within 100 ms (TBD); loss-of-message timeout drives safe state | Simulator v1.4, CAN logs | MUST | Full (SIL) | F21, F22 | LCC not available on bench | PGN renumbered 65301->65283 on 10/5 | Not started
C-03 | G0 Bench | Cerritos | VMS master-BMS reads BCUs and reacts to bad states | BCUs (Modbus TCP), VMS | Voltify | Micah | BCUs on Ethernet | Read cell V/T/SOC; inject over-V, under-V, over-T, comm loss (unplug) | Correct values vs handheld; each fault -> correct derate/open within spec time; comm loss -> contactors open | Laptop, DMM, heat gun | MUST | Partial (1/6) | F04, F05 | BCUs integrated (12/12 shipped) | No ESMU on prototype | Not started
C-04 | G0 Bench | Cerritos | String connection algorithm prevents paralleling mismatched strings | Combiner panels, BCUs, VMS | Voltify | Micah | Two strings (one combiner) available | Set strings at different SOC; command connect | Connect blocked above dV limit (TBD, e.g. 5 V); allowed below; inrush logged | 2 strings, DC clamp meter | MUST | Partial (1 combiner) | F04 | Combiners not developed | Define dV limit in VMS | Not started
C-05 | G0 Bench | Cerritos | DC-link precharge works with real capacitance | VMS VIO #1, 400 A precharge resistor, DC-link contactors | Voltify (ownership TBD vs LCC) | Mitchell | Cap bank sized to chopper + LCF (9,200 uF) + ITV (13,770 uF) input | Precharge at test-rack voltage; scope current and voltage | Peak current <400 A; reaches >=95% bus V before bypass; resistor temp rise within rating; no welds | Cap bank, isolated scope, thermocouples | MUST | Partial (V/I scaled) | F02, F03 | DC-link contactors incomplete | Resolve owner: VMS VIO (arch doc) vs LCC (deck FER page) | Not started
C-06 | G0 Bench | Cerritos | E-Stop tree opens everything in the right order (T1/T2/T3) | E-Stop loop, VIOs, MCS ctrl, Panto ctrl, 750V-PS EN, VMS | Voltify | Micah / Mitchell | T1/T2/T3 values defined | Press each E-Stop PB; scope every EN line and contactor aux contact | Order = stop current (T1) -> open charge contactors (T2) -> fold pantos + open battery contactors (T3); all within defined times; restart blocked until reset | 8-ch isolated scope, E-Stop PBs | MUST | Full (LV), Partial (HV) | F01, F37 | Not tested | T1-T3 are TBD in deck | Not started
C-07 | G0 Bench | Cerritos | 750V-PS converts and fails safe | 750V-PS (Zekalabs LB-1186) | Voltify | Mitchell | Test rack at 1/6 power; load bank | Step loads; remove 24 V control power; E-Stop EN | Regulates 750 V +/- spec; loss of 24 V -> no uncommanded output; EN low -> output off <T1 | HV load bank, DMM | MUST | Partial (1/6) | F18 | Bring-up |  | Not started
C-08 | G0 Bench | Cerritos | 72V-PS powers loco bus and charges starter battery; load shedding | 72V-PS, starter battery, load-shed contactor | Voltify + donor | Mitchell | 750V source | Load steps; battery charge; shed test | Holds 72 V under step; charges PB battery; load-shed opens at threshold | 72 V load bank, battery | MUST | Full | F17 | Bring-up (shipped) |  | Not started
C-09 | G0 Bench | Cerritos | Compressor inverter starts and runs the brake compressor | Compressor-INV, compressor test stand | Integral (integration) + Voltify | Dave / Mitchell | Test stand built | Start under head pressure; log inrush | Starts every time at max head pressure; inrush within inverter limit; reservoir fill time logged | Compressor stand, air tanks, clamp meter | MUST | Full | F19 | Bring-up; Integral integrates | Inrush ~5-6x FLA per Micah/Dave | Not started
C-10 | G0 Bench | Cerritos | Blower inverter runs traction blowers | Blower-INV | Integral + Voltify | Mitchell | Blower motor or equivalent load | Run at each speed setpoint | Stable at Low/Med/High; faults reported on CAN | Motor load | SHOULD | Partial | F20 | Bring-up; Integral integrates |  | Not started
C-11 | G0 Bench | Cerritos | Battery thermal module heats and cools on command | MTM #1, pumps, Therminator/controls, BTMS 12V PS | Voltify + Maxwell | Jack / VJ | Coolant filled (G-48 50/50) | Command cool and heat; heat-load test | Coolant temp tracks setpoint; flow and pressure in range; no leaks | Heat source, flow meters (IFM SU2631) | SHOULD | Partial (1 of 3-4 modules) | F07, F29 | MTM1 bring-up; others N/A |  | Not started
C-12 | G0 Bench | Cerritos | PE cooling loop flow is balanced | PE pumps, choppers/ITV cold plates (or dummies) | Voltify | VJ / Jack | Loop plumbed | Measure flow per branch; pressure test | Each branch >= required LPM (deck: ~30 LPM chiller loop); hold pressure 30 min | IFM flow meters, pressure tester | MUST | Full | F30 | PE pump bring-up |  | Not started
C-13 | G0 Bench | Cerritos | Pantograph raises, folds and senses (one head) | Pantograph FR, panto controller, HAX 1000-S sensors | Voltify | Micah | Panto on bench | Raise/fold via CAN; cut 24 V; E-Stop; inject current and polarity | Raise and fold times logged; fold on E-Stop without MCU; current reads within 2%; polarity reads correctly | DC current source, HV supply | MUST | Partial (no catenary) | F09, F10 | FR integrated on charging CAN; controller not developed |  | Not started
C-14 | G0 Bench | Cerritos | Panto contactor panel sequences precharge and discharge | Panto panel VIO #3, contactors | Voltify | Mitchell | Panel wired | Command sequence at test voltage | Correct order; aux feedback matches; discharge to <50 V within spec | HV supply, scope | SHOULD | Partial | F03, F37 | VIO #3 incomplete |  | Not started
C-15 | G0 Bench | Cerritos | Grounding switch cannot move until all 4 HV nodes are safe | RTV, grounding switch, maintenance key | Voltify | Micah | RTV built | Apply V on each node; try release | EM releases only when all 4 nodes <50 V for 5 s; any node high blocks | HV supply, 4 probes | MUST (safety) | Full | F16 | RTV not developed |  | Not started
C-16 | G0 Bench | Cerritos | Harnesses and panels are insulated before shipping | All HV harnesses/panels | Voltify | Mitchell | Built assemblies | Insulation resistance test at 2.5 kV (TBD) | IR >= agreed limit (proposed 500 ohm/V at 1,500 V = 0.75 Mohm min; use higher internal target) | Megger 2.5/5 kV | MUST | Full | F15 |  |  | Not started
C-17 | G0 Bench | Cerritos | Busbar joints carry rated current without overheating | TRB busbars, contactor panel bars | Voltify | Dave | Joints torqued and marked | 2,000 A from LV supply; thermal camera | Joint temp rise within design limit; mV drop per joint logged; torque marks intact | 2,000 A LV supply, IR camera, micro-ohmmeter | MUST | Full (current) | F28 |  | Ties to 1,800 A joint study | Not started
C-18 | G0 Bench | Cerritos | Deep sleep, wake-up and maintenance mode sequences run end to end | VMS, VIOs, 750V-PS, TRB contactors, UPS | Voltify | Micah | C-03..C-07 passed | Run each documented sequence | Each step in order; parasitic draw in deep sleep logged (target ~50 W) | Clamp meter | SHOULD | Partial | F17 |  |  | Not started
C-20 | G0 Bench | Cerritos | Phase 3 system model reproduces the verified Phase 2 sweep | loco_system (Stateflow states, load budget, fault injection, +locosys plant) | Voltify | Bill | Phase 2 sweep results | run_regression_phase2 on S2/S3/S5 at 20 and 50 C (preconditioned); yard-day baseline and hot-day fault demo | Same verdict; dTcell < 0.5 K; dT PE supply < 1 K; dSOC < 0.01 | MATLAB/Simscape, proto_loco repo | SHOULD | Full (model) | F54, F59 |  | Passed 2026-10-08; committed | Passed | 2026-10-08 | results/regression_p3_vs_p2_*.csv
C-21 | G0 Bench | Cerritos | Fault sweep: every fault in the library at 20/40/45 C ranked by effect and time to first limit | loco_system fault library | Voltify | Bill | C-20 | run_fault_sweep on traces/fault_test_3h.csv; each fault alone from 0.5 h; compare against no-fault baseline | Ranked table; FMEA O/D and RSK updated from results | MATLAB/Simscape | SHOULD | Full (model) | F54, F55, F59, F61-F64 |  | Run 2026-10-07 (54 runs, 15 min); see Fault Sweep tab | Passed | 2026-10-08 | results/fault_sweep_20261007_1600.csv (POC baseline re-run)
C-22 | G0 Bench | Cerritos | Fault sweep v2: 8 h yard duty, breakaway (starting) resistance, baseline-relative classes | loco_system | Voltify | Bill | C-21; starting resistance added to vehicle model | Re-run run_fault_sweep on an 8 h trace (long-duty effects: blower loss, sensor low bias, string loss); add breakaway resistance so starts of heavy trains are checked | Ranked table; long-duty WATCH items resolved to WORSE/SAME | MATLAB/Simscape | SHOULD | Full (model) | F62, F63, F64 |  | Planned | Not started
C-19 | G0 Bench | Cerritos | MATLAB thermal sweep re-run with measured thermal data | proto_loco Phase 2 model | Voltify | Bill + VJ | Measured battery-coolant UA, Maxwell MTM capacity map, D77 thermal data | Replace placeholders (MODEL_NOTES Phase 2 table) with measured values; re-run run_thermal_sweep; compare verdict matrix | Verdict matrix updated; no new FAIL at the design ambient (DR-52) for preconditioned starts | MATLAB/Simscape, proto_loco repo | SHOULD | Full (model) | F54, F55, F58 |  | v0.5 baseline in Thermal Sweep tab | Not started
H-01 | G1 Receive & build | Huntington | Shipped LRUs arrive undamaged and match BOM | All shipped LRUs (choppers x5, packs, panels) | Voltify | Production lead | Shipments landed | Receiving inspection + photos; shock indicators | No damage; serials logged; BOM match | Camera, receiving log | MUST | None | F28 |  | Choppers ship Oct 8-9 (5 units) | Not started
H-02 | G1 Receive & build | Huntington | Every harness is wired to the schematic and the wiring audit is signed (Huntington exit item a) | All LV/HV harnesses | Voltify | Production lead + Mitchell | Electricians done per compartment | Point-to-point continuity vs wire list; independent second-person audit of 100% of terminations; redlines incorporated into the schematic; per-cable IR (system Megger is H-29) | 100% continuity; audit signed by production lead + Voltify engineer; all redlines closed | Continuity tester, megger | MUST (Huntington exit) | None | F31 |  | 5 electricians start Oct 12 | Not started
H-30 | G1 Receive & build | Huntington | Software and firmware loaded on every controller, Voltify and Integral (Huntington exit item c) | VMS, VIOs x4, BCUs x12, panto ctrl, PE cooling ctrl, LCC/TECU, choppers x5, IAC | Voltify + Integral | Jared + Integral | Release packages frozen; DBC R2 | Flash each node from the release package; read back version and checksum; record in a signed manifest; re-run after any update | 100% of nodes on manifest versions; checksums match; manifest signed by Voltify and Integral | Flash tools, laptops, release package, VPN | MUST (Huntington exit) | Partial (bench images) | F51, F21 |  | Jared release process covers Voltify only today | Not started
H-03 | G1 Receive & build | Huntington | Low-voltage power-up is clean | 72 V battery, 24 V PDMs, breaker panels | Voltify | Mitchell | H-02 passed, H-30 loaded | Energize breaker by breaker; check PDM channel map | Each load on the correct channel; no trips; E-Stop loop continuity | DMM, PDM config tool | MUST | None | F31, F32 | PDM #1 bring-up |  | Not started
H-04 | G1 Receive & build | Huntington | All nodes talk on the locomotive | CAN x4, Ethernet, LCC, BCUs x12 | Voltify + Integral | Micah | H-03 passed | Repeat C-01 census on the loco | 100% nodes; no error frames 30 min | CAN analyzer | MUST | None | F21 |  |  | Not started
H-29 | G2 HV energize | Huntington | HV system insulation (Megger) passes before first energization (Huntington exit item b) | TRB-BUS, DC-link, choppers, ITV path, aux converters, panto/MCS buses | Voltify | Mitchell | H-02 passed; written Megger procedure; electronics isolated or shorted per procedure | Test each HV section to chassis at the procedure voltage (proposed 2.5 kV, or component rating if lower); record 1-min IR and polarization index; discharge after | IR >= limit per section (proposed >= 0.75 Mohm at 1,500 V; internal target higher); no section below; values logged as baseline for J-01 | 5 kV insulation tester, shorting leads, discharge stick, HV PPE | MUST (Huntington exit) | Partial (C-16 harness level) | F15, F52 |  | Do not Megger with semiconductors, sensors or EMC caps connected | Not started
H-32 | G2 HV energize | Huntington | Data logging is live from first LV power and syncs to the cloud | VMS logger, LCC data, BCUs, GPS, Starlink, cloud store | Voltify | Matan + Jared | H-03; signal list frozen (Data Logging tab) | Start logging at first LV power; verify every signal group at its rate; pull 24 h and check gaps and time alignment; verify Starlink sync and store-and-forward when offline | 100% of P1 signals present at rate; time alignment < 100 ms across sources; no gap > 1 min in 24 h; >= 7 days onboard buffer; cloud copy within 24 h | Starlink or LTE, laptop, cloud bucket | MUST | None | F48 | Starlink incomplete | Range is empirical (DR-49); data starts here | Not started
H-05 | G2 HV energize | Huntington | Each battery string comes on line safely, then strings are paralleled | Packs, combiners, BCUs, VMS | Voltify | Micah | H-29 passed; isolation checked per string | One string at a time; verify V, polarity, feedback; then parallel with dV rule | String V matches BCU; contactor feedback matches; parallel inrush within limit | HV probes, DC clamp | MUST | Partial (C-03/04) | F04, F05 |  |  | Not started
H-06 | G2 HV energize | Huntington | Traction bus isolation is healthy | TRB-BUS, DC-link, HV room | Voltify | Micah | H-05 | Measure isolation +/- to chassis at full V (IMD or megger) | Isolation >= agreed limit; logged as baseline | Insulation monitor or megger | MUST (safety) | Partial | F15 | No IMD in architecture | Add IMD or a manual check rule ¦ v1.3: Jonathan: continuous ground-fault detection exists; verify the detector senses the TRB-bus (source), not only the DC-link | Not started
H-07 | G2 HV energize | Huntington | DC-link precharge at full voltage and full capacitance | VMS VIO / LCC, choppers, LCF | Voltify + Integral | Mitchell + Integral | H-05, choppers installed | Precharge at full bus V; scope | Same as C-05 at full V; no contactor weld | Isolated scope | MUST | Partial | F02, F03 |  |  | Not started
H-08 | G2 HV energize | Huntington | Aux power chain runs the locomotive's own loads | 750V-PS, 72V-PS, compressor INV, blower INV, BTMS | Voltify + Integral | Mitchell | H-07 | Staged load-up; pump main reservoir | Main reservoir pumped to cut-out pressure in FRA time (TBD); no aux trips | Air gauges (digital), clamp | MUST | Partial (C-07..C-11) | F18, F19 |  |  | Not started
H-09 | G2 HV energize | Huntington | E-Stop disconnects all HV at full voltage | E-Stop tree | Voltify + Integral | Micah | H-08 | Press each PB with aux running; repeat with light traction | All HV sources off in T1-T3; residual V decays; restart needs reset | Isolated scope | MUST (safety) | Partial (C-06) | F01, F37 |  |  | Not started
H-10 | G2 HV energize | Huntington | Air brakes, alerter and penalty work with the new control system | CCB2 / air brake, LCC, alerter, handbrake | Integral + donor | Dragan + Integral | H-08 | Standard air brake tests; alerter timeout; handbrake-applied inhibit | Pass FRA Part 229/232 brake tests; penalty applies; loco will not load with handbrake applied | Air brake test kit | MUST | None | F24 |  |  | Not started
H-11 | G2 HV energize | Huntington | Start, stop and timeout sequences run between VMS and LCC | VMS, LCC | Voltify + Integral | Micah + Bailey | H-04, H-07 | Run deck start/stop/timeout flows | Each step and alarm per flowchart | CAN logs | MUST | Partial (C-02) | F21 |  |  | Not started
H-31 | G3 Huntington readiness + first movement | Huntington | Idle readiness: system powers to idle with zero Class A faults and comm faults minimized | Whole loco at idle (HV on, no motion) | Voltify + Integral | Micah + Bailey | H-04, H-09, H-11; every fault code classified A/B/C | Power up to idle 3 times from cold; hold 60 min each; export fault log and CAN error counters | Zero Class A active or latched; every Class B listed with an override plan and an owner for JAX; CAN error frames below threshold (TBD) per bus | CAN analyzer, fault log export | MUST (Huntington exit) | Partial (C-01, C-02) | F46, F47, F21 |  | Readiness definition per Dragan | Not started
H-12 | G3 Huntington readiness + first movement | Huntington | Each motor turns the right way at creep | Choppers 1-4, D77 motors, reverser/MCO | Integral + Voltify | Integral field engineer | H-09, H-10, H-31 | Cut in one axle at a time; <1 mph fwd/rev | Correct direction per axle; current per axle balanced within 10% | Track access, radios | MUST (Huntington exit) | None | F23 | Choppers at motor lab Oct 5-7 |  | Not started
H-13 | G3 Huntington readiness + first movement | Huntington | FIRST MOVEMENT: locomotive moves forward and reverse under its own power and stops (Huntington exit item d) | Full drivetrain, brakes, E-Stop | Integral + Voltify | Dragan + Integral | H-12 | Shop/yard track, <=5 mph. Forward then reverse. Stop with independent brake, automatic brake, and E-Stop. Class B faults may be overridden per the override rules (Fault Classes tab); any Class A fault = abort | Moves both directions; stops on each brake; E-Stop safe stop; zero Class A faults; every override logged | Track authority (CSX/HRR); qualified engineer + conductor; DAQ logging on | MUST (Huntington exit) | None | F01, F24 |  | Confirm with CSX whether 49 CFR 229.9(c) yard-move basis covers this test move (RSK-NEW-21) | Not started
H-14 | G3+ Optional extended pre-check | Huntington | Pre-check of Showcase 1 at Huntington: accelerate and hold speed 20 min | Whole loco | All | Bill (test director) | H-13 | Accelerate to 10 mph (TBD); hold 20 min; repeat in reverse | No latched faults; battery current <=1,884 A; temperatures in limits; speed holds +/- 1 mph | ~3.3 mi of track or repeated passes; DAQ | SHOULD | None | F20, F22, F23 |  | Optional. Not required for the tow. If skipped, first 20-min run is J-02B. | Not started
H-15 | G3+ Optional extended pre-check | Huntington | Thermal soak during the run stays in limits | Choppers, motors, battery, PE loop, blowers | Voltify + Integral | VJ / Jack | H-14 | Log temps through H-14 and 15 min after | All temperatures below supplier limits; no derate | Thermocouples, VMS logs | SHOULD | None | F07, F20, F30 |  |  | Not started
H-16 | G3+ Optional extended pre-check | Huntington | Wheel slip control works | LCC/IAC, choppers | Integral | Integral | H-14 | Sand off / wet rail start; light-engine notch steps | Slip detected and corrected; no flats | Track access | SHOULD | None | F23 |  |  | Not started
H-17 | G3+ Optional extended pre-check | Huntington | Early energy baseline from shop moves (kWh/mi, idle kWh/h) | VMS energy counters | Voltify | Bill / Jared | H-32 | Log kWh and miles across all runs | Idle and moving energy logged with timestamps; feeds Load Cases tab | VMS logs | SHOULD | None |  |  | Seeds the range model; full data at J-18/J-19 | Not started
H-18 | G3+ Optional extended pre-check | Huntington | Recharge with the shop power supply safely | Lab DC supply, charge entry point, VMS limits | Voltify | Mitchell | Defined connection point + procedure | Charge from X to Y% SOC; log kW, time, temps | VMS current limits honored; no bypass of contactors/protection; kW achieved logged | HV DC supply (e.g. MPS125 + transformer), 480 V service | SHOULD | None | F36 | MCS controllers not developed | Needed only if packs arrive below the tow SOC window or pre-check runs drain them | Not started
H-21 | G3+ Optional extended pre-check | Huntington | Safe reaction to the most likely faults | VMS, LCC, BMS | Voltify + Integral | Micah | H-14 | Inject: LCC msg loss, BMS comm loss, 72 V dip, one string trip | Each fault -> defined safe state; no unsafe motion; recovery procedure works | CAN tool, breaker | SHOULD | Partial (C-02/03) | F05, F21 |  |  | Not started
H-34 | G3+ Optional extended pre-check | Huntington | PE loop fault detection: VMS alarm and traction response to pump stop and fan stop | PE cooling controller, VMS, LCC | Voltify | VJ + Micah | H-32 logging live; Class B fault list | At idle and at low power: stop PE pumps, then PE fans (one at a time); verify alarm, fault class and traction derate/inhibit timing | Pump stop detected and traction inhibited before chopper fluid exceeds 63 C; fan stop raises Class B alarm with derate | Loco on HV, logging | SHOULD | None | F59, F61 |  | Model: pump loss exceeds 63 C at onset under load; fan loss ~9-12 min at 40-45 C | Not started
H-19 | G4 Dead-in-tow ready | Huntington | 72 V system lasts the whole tow with monitoring on | VMS, UPS, 72 V | Voltify | Micah | H-32 | Run the chosen tow monitoring mode (lean or full) on the 72 V battery for 48 h; log draw | Measured draw x tow duration (up to 1.5 wk) < 50% of 72 V battery; wake works after | Clamp meter | MUST | None | F17, F44 |  |  | Not started
H-20 | G4 Dead-in-tow ready | Huntington | Dead-engine air brake setup works from a trailing position | CCB2 air brake, dead-engine cut-out, brake pipe, MR, handbrake | Donor + Integral | Dragan | H-10 | Configure CCB2 for dead-in-tow per NYAB procedure; charge from a lead unit or yard air via brake pipe; apply/release from the lead | Loco main reservoir charges from brake pipe; brakes apply and release with the train; no drag; handbrake holds | Yard air or lead unit, single-car test device, NYAB DIT procedure | MUST | None | F40 |  |  | Not started
H-22 | G4 Dead-in-tow ready | Huntington | Pantographs folded and mechanically locked, or not fitted, for the tow; inside Plate M | Pantos, hatch, roof | Voltify | Dave | Hatch installed (or not) | Fold, mechanical lock, measure height | Inside AAR Plate M; locks hold | Tape/laser, lift | MUST | None | F14, F42 | Hatch into Dec | Hatch runs into Dec; tow without pantos is acceptable | Not started
H-23 | G4 Dead-in-tow ready | Huntington | CSX mechanical acceptance for dead-in-tow movement | Running gear, brakes, safety appliances, records | Voltify + CSX | Dragan / Daphna | H-20, H-26 | CSX mechanical inspection; move as a non-complying locomotive under 49 CFR 229.9 tag (CSX sets max speed and restrictions) unless a periodic inspection is current; Class I air brake test as a car in the train (Part 232); safety appliances (Part 231); battery/hazmat paperwork review | Written CSX acceptance and routing instructions (speed, position in train, no-hump) | CSX carman, FRA inspector | MUST | None | F27 |  | Still the largest schedule unknown, but much smaller than own-power mainline acceptance | Not started
H-24 | G4 Dead-in-tow ready | Huntington | Put the locomotive into its tow configuration | HV isolation, traction motors, MU, packs, cab, placards | Voltify | Production lead | H-23 | Open all string and DC-link contactors and verify de-energized (RTV/HV probe); engage grounding switch (padlock optional per Dragan); isolate traction motors; isolate MU trainlines; CCB-2E dead-engine cut-out IN; compressor not required; release electric handbrake (H-33); set pack SOC to the tow window; torque-check and paint-mark joints; restrain packs; lock doors; post placards and the emergency response sheet; install shock/temperature logger; tag control stand DEAD-IN-TOW | Tow checklist 100% signed by two people | Torque wrenches, logger, placards; padlocks optional | MUST | None | F26, F28, F38, F39, F43, F45 | Starlink incomplete |  | Not started
H-25 | G4 Dead-in-tow ready | Huntington | Traction motors cannot back-feed voltage while being towed | D77 motors, MCO/reverser, choppers, DC-link | Integral + Voltify | Integral + Mitchell | HV isolated (H-24 HV steps) | Move the loco slowly (switcher or shop mule) with control power OFF; measure voltage at motor leads, chopper inputs and DC-link | Below 50 V at every point at test speed; MCO/reverser state verified with control power off | Shop mule, HV probes, DMM | MUST (safety) | None | F38 |  | Spec removed manual TM cutout switches; confirm safe state with LCC unpowered | Not started
H-26 | G4 Dead-in-tow ready | Huntington | Running gear is fit for a 750-900 mile tow | Wheels, journal bearings, TM suspension bearings, gear cases, brake rigging | Donor (Dragan) | Dragan | Trucks installed | Wheel and bearing inspection; fill TM suspension bearing oil and gear case lube; set brake piston travel | All within FRA/AAR limits; lube levels recorded | Lube supplies, wheel gauges | MUST | None | F41 |  |  | Not started
H-27 | G4 Dead-in-tow ready | Huntington | MU trainline signals cannot command the prototype | MU receptacles, LCC, VMS | Integral + Voltify | Integral | H-03 | Apply trainline throttle, reverser, sand and headlight signals from an MU test box with the loco in tow config | No contactor, inverter or actuator responds | MU test box, dummy receptacle plugs | MUST | None | F39 |  |  | Not started
H-28 | G4 Dead-in-tow ready | Huntington | Emergency responders know what they are looking at | Placards, emergency response sheet, contacts | Voltify | Bill | H-24 | Prepare Li-ion emergency response info (chemistry, energy, SOC, HV isolation points, 24/7 contact); review with CSX hazmat | CSX hazmat sign-off; copies in cab and with waybill | Placards, printed ERG sheet | MUST | None | F43 |  |  | Not started
H-33 | G4 Dead-in-tow ready | Huntington | Electric handbrake can be applied and released with 72 V off | Graham-White electric handbrake, brake-applied indication | Donor (Dragan) | Dragan | Handbrake installed | With 72 V off, apply and release using the manual method; verify brake-applied indication behaviour | Applies and releases manually; holds the loco on the shop grade; released state verified before tow | Supplier manual | MUST | None | F45 |  | New gap from dead-in-tow review | Not started
T-01 | G5 Tow | In train (CSX) | Monitor the pack during the tow | Logger; lean telemetry (BCUs on 72 V) | Voltify | Bill / Matan | H-24 | Watch remote alerts (cell temperature, smoke if fitted); CSX crew checks at crew changes per instructions | No temperature or smoke alert; logger peak shock below agreed limit | Cellular telemetry or standalone logger | MUST | None | F43, F44 |  | A Voltify rider is unlikely to be permitted in a dead unit | Not started
J-01 | G6 Recommission | Jacksonville | Nothing came loose or got hurt in the tow | Busbars, connectors, packs, coolant | Voltify | Production lead | Arrived | Read shock logger; inspect torque marks; IR test; coolant level; cell imbalance; then undo the tow configuration (motors, MU, grounding switch) | No broken marks; IR >= baseline x 0.5; imbalance within limit | Megger, IR camera | MUST | None | F28, F29, F38 |  |  | Not started
J-02 | G6 Recommission | Jacksonville | Regression: LV/HV power-up and E-Stop at full voltage after the tow | Whole loco | All | Bill | J-01 | Repeat H-03, H-05, H-07, H-09 | Same pass lines as Huntington | Track access | MUST | None | F01 |  |  | Not started
J-02B | G6 Recommission | Jacksonville | SHOWCASE 1: accelerate and hold speed for 20 minutes | Whole loco | All | Bill (test director) | J-02 | Accelerate to 10 mph (TBD); hold 20 min; repeat in reverse | No latched faults; battery current <= 1,884 A; temperatures in limits; speed holds +/- 1 mph | ~3.3 mi of track or repeated passes at JAX; DAQ | MUST | None | F20, F22, F23 |  | First run here if H-14 was not done | Not started
J-03 | G7 Charging infra | Jacksonville | Wayside side is ready: charger, wire, protection, grounding | AES charger, contact wire, mast, microgrid PLC | Voltify site team | Oren / Matan | AES delivered; Dynapower commissioned | Site acceptance; polarity and return path; protection settings | Signed site acceptance; polarity documented; DPS100 current limits set to 833 A each (1,666 A total) and ground ESS discharge limit 0.5C (2.1 MW) verified in the site acceptance | Site test kit | MUST | None | F13 | AES ETA late Nov-mid Dec |  | Not started
J-04 | G7 Charging infra | Jacksonville | Pantographs meet the wire correctly (de-energized) | Pantos, hatch, wire | Voltify | Dave / Micah | Hatch + pantos installed | Raise under dead wire; measure contact force, height, alignment | Contact force in supplier range; all used heads align | Force gauge, man-lift | MUST | None | F08, F14 |  |  | Not started
J-05 | G7 Charging infra | Jacksonville | Live wire, no current: sensing, polarity, reverser, HSCB close | Panto ctrl, reverser, HSCB, panto panel | Voltify | Micah | J-03, J-04 | Energize wire; read V and polarity; close HSCB | Polarity correct and selected automatically; HSCB closes on command (trip test in J-23) | Scope, HV probes | MUST | None | F09 |  | v1.1: HSCB retained (RSK-NEW-16); trip and interlock test in J-23 | Not started
J-06 | G8 Static charge | Jacksonville | Static charging power ramp and loss measurement | ITV, pantos, battery, BTMS, PE loop | Voltify + Integral | Micah + Integral | J-05, ITV installed | Steps 0.1 -> 0.5 -> 1.0 -> 1.5 -> 2.1 MW demo limit (wire current <= 1,666 A); hold each 10 min | Charge current within cell limit; strip, busbar, ITV, battery temps within limits; loss measured at each step; wire current <= 1,666 A and wire power <= 2.1 MW at every step | Wayside meter, DAQ, IR camera | MUST | None | F06, F07, F08, F12 | ITV not delivered | Charging-loss deep dive ¦ v1.3: Demo charge limit DR-17 (was 2.5 MW cap) | Not started
J-07 | G8 Static charge | Jacksonville | Locomotive and wayside charger talk and stop each other safely | VMS, PLC/microgrid, AES | Voltify | Matan / Micah | J-03 | Handshake; stop on fault from each side; E-Stop notify | Either side can stop current within spec; no hot disconnect | CAN/ETH logs | MUST | None | F11 | Line 79 on Gantt |  | Not started
J-08 | G9 Dynamic charge | Jacksonville | Moving under the wire at 0.1-0.5 mph, no current | Pantos, drivetrain | All | Bill | J-06 | Raise pantos and move; check contact and arcing | Continuous contact; no arcing marks; speed holds | Video, IR camera | MUST | None | F08 |  |  | Not started
J-09 | G9 Dynamic charge | Jacksonville | SHOWCASE 2: dynamic charging at 0.5 mph | Whole system | All | Bill | J-08 | Segment A at the demo limit (2.1 MW, <= 1,666 A) >= 10 min; segment B 2 mi at ~1.03 MW | Per success criteria table; no trips; temperatures in limits | Wayside meter, DAQ | MUST | None | F06, F07, F08, F11 |  | DR-17 demo limit; filling 20->95% at 2.1 MW takes ~1.9 h (~1 mi at 0.5 mph) | Not started
J-10 | G9 Dynamic charge | Jacksonville | Pantograph fold and E-Stop under load while moving | Pantos, ITV, contactors | Voltify | Micah | J-09 | E-Stop at 0.5 mph under 0.5 MW, then 1 MW | ITV stops current before contactors open; pantos fold; no arc damage | Scope, video | MUST (safety) | None | F01, F10 |  | Top step stays inside the 2.1 MW demo limit | Not started
J-11 | G10 Operate | Jacksonville | 30-day CSX operation reliability log | Whole loco | All | Production lead | Showcase passes | Daily checklist + fault log | No open safety faults; availability tracked | Logbook | MUST | None | all |  | Target start ~Jan 20. Ramp tests J-14..J-19 run inside this window; non-gating for the showcase | Not started
J-12 | G10 Operate | Jacksonville | Showcase rehearsal | Whole loco | All | Bill | J-09 | Run the scripted demo 3 times in a row | 3 of 3 clean runs | Full crew | MUST | None | all |  |  | Not started
J-14 | G10 Operate + performance ramp | Jacksonville | TREND: notch ramp, light engine | Drivetrain, battery, aux | Voltify + Integral | Bill (test director) + Integral | J-02B | Light engine (LC-0). Notch 1 -> 8, 30 s to 2 min per notch, both directions; log battery V/I/P, motor currents, speed, acceleration | Data captured every notch; no Class A; battery current <= 1,884 A at Notch 8; power per notch compared with 40 CFR 1033.530 Table 3 profile | Track (~1 mi), DAQ | TREND (non-gating) | None | F22, F49 |  | Establishes the power-vs-notch map | Not started
J-15 | G10 Operate + performance ramp | Jacksonville | TREND: trailing-load step ramp | Drivetrain, battery, slip control, brakes | Voltify + Integral | Bill + Integral | J-14; CSX cuts of cars | Pull LC-1, then LC-2, then LC-3 (Load Cases tab): start, accelerate to 10 mph, stop. Repeat 3x each | Time to 10 mph and peak tractive effort per load case logged; slip control active; no Class A; TE vs motor current fits the D77 curve | CSX cuts of cars, track >= 1 mi, optional drawbar load cell | TREND (non-gating) | None | F23, F50 |  | Switcher acceleration is the key yard metric | Not started
J-16 | G10 Operate + performance ramp | Jacksonville | TREND: continuous pull at 10 mph | D77 motors, choppers, blowers, PE loop, battery | Voltify + Integral | Bill + VJ | J-15 | Hold 10 mph against the heaviest available load: 50% -> 75% -> 100% of 54,700 lbf (estimated), holds of 15 -> 30 -> 60 min; log all temperatures; fit a first-order thermal model and project steady state | Projected steady-state temperatures below supplier limits at the highest step reached; report % of GP40 continuous TE achieved | Heaviest CSX cut (LC-3), long track or loop, thermocouple DAQ | TREND (non-gating) | None | F50, F20, F30 |  | Ramp matrix on Load Cases tab | Not started
J-17 | G10 Operate + performance ramp | Jacksonville | TREND: Notch 8 duration | Battery, choppers, motors, cooling | Voltify + Integral | Bill + Micah | J-14, J-16 thermal model | Notch 8 with enough trailing load to stay inside track and speed limits: holds of 1 -> 5 -> 10 -> 15 min, cool-down between; log SOC drop per minute and temperatures; project to 15 min | 15-min projection inside limits, or the limiting component and the time to limit documented | Heavy cut, long track, DAQ | TREND (non-gating) | None | F49, F07 |  | 15 min at ~2.5 MW uses ~0.63 MWh (~16% of usable) ¦ v1.2: Rev C: on LC-3/0.5% Notch 8 balances at ~20 mph (2.144 MW) or ~14 mph (500 hp cap); motors at the D77 15-min rating. Choose load and speed so the hold is power-limited and inside track limits | Not started
J-18 | G10 Operate + performance ramp | Jacksonville | Energy use over a representative switching shift | Whole loco | Voltify | Bill / Jared | H-32, J-15 | Run a 4-8 h switching shift: EPA switch cycle as the default script, Moncrief moves when available; record kWh/h, kWh per car-move, SOC used, idle draw, contactor and precharge cycles | Energy per shift known +/- 10%; cycle counts logged; range model updated | DAQ, crew log of cars/tons per move | SHOULD | None | F48, F53 |  | Feeds DR-49 (range) | Not started
J-19 | G10 Operate + performance ramp | Jacksonville | Range model matches logged data | Energy model (Load Cases tab), logs | Voltify | Bill | J-18 + 30-day ops data | Predict energy for held-out days from the model; compare with logged kWh | Error <= 10% on held-out days | Logs | SHOULD | None | F48 |  |  | Not started
J-20 | G10 Operate + performance ramp | Jacksonville | TREND: PE and condenser loop temperatures vs ambient | PE loop (choppers, ITV, inverters), condenser loop, radiators | Voltify | VJ | H-32 logging live | Log PE supply, charger/inverter/chopper outlet and condenser loop temperatures, PE and condenser fan status (speed/current) with ambient during J-06..J-09 and J-16/J-17; fit rise over ambient per load; project to the design ambient | Projected charger supply <= 55 C, inverter <= 60 C, chopper <= 63 C, condenser loop <= 65 C at the design ambient (DR-52) | Thermocouples / logged coolant temps, ambient sensor | TREND (non-gating) | None | F54, F55 |  | Sweep predicts limits reached at ~46-50 C ambient; Phase 3: PE fan loss at ~34 C exceeds chopper/inverter limits within minutes | Not started
J-21 | G10 Operate + performance ramp | Jacksonville | TREND: preconditioning time and energy after an overnight soak | BTMS (Maxwell MTMs, heaters), BMS thermal control | Voltify | Micah + Jack | H-32 logging live | On a cool and a warm morning, start from soaked pack; run TMS until cells are inside 15-35 C; log time and TMS kWh; compare with model scenario S8 | Measured time/energy within 25% of model; preconditioning procedure written | Logging, wayside or battery power | TREND (non-gating) | None | F56, F57, F58 |  | Model: 0 C -> 5 C in ~1.9 h; 50 C -> 45 C in ~1.2 h | Not started
J-13 | P1 Post-demo (CSX 90-day) | Jacksonville | Manual MCS charging (deprioritized for showcase) | MCS controllers, inlets, contactors | Voltify | Jared / Marwan | After showcase | Per MCS controller spec sequence | Per IEC 61851-23-3 sequence | MCS charger | POST-DEMO | None | F36 | MCS not developed | Dragan: not needed for first month | Not started
P-01 | P1 Post-demo (CSX 90-day) | Jacksonville / CSX | Notch 8 held for 15 minutes | Whole loco | All | Bill + Integral | J-17 trend acceptable | Notch 8 for 15 min under representative load | 15 min at full rated traction power without derate; temperatures within limits | CSX train or heavy cut | POST-DEMO | None | F49 |  | Dragan target; confirm wording in GP40 manual | Not started
P-02 | P1 Post-demo (CSX 90-day) | Jacksonville / CSX | Continuous pull at 10 mph sustained | Whole loco | All | Bill + Integral | J-16 trend acceptable | Sustain >= GP40 continuous TE at >= 10 mph | >= 54,700 lbf (reference) at >= 10 mph for duration TBD from GP40 manual (proposed >= 60 min or thermal steady state) | Heavy train, track | POST-DEMO | None | F50 |  |  | Not started
P-03 | P1 Post-demo (CSX 90-day) | Jacksonville | HSCB integration and trip test (only if HSCB is retained) | HSCB A/B, REV+CB VIO | Voltify | Micah | Decision on HSCB (RSK-NEW-16) | Close/trip on command; trip on injected overcurrent signal; interlock with polarity | Trips within spec; interlocks hold | Scope, current injection | SUPERSEDED (see J-23) | None | F09 |  | v1.1: superseded by J-23 (HSCB retained for demo) | Not started
P-04 | P1 Post-demo (CSX 90-day) | CSX | Availability and service interruptions converge toward diesel baseline | Whole loco | All | Production lead + Daphna | CSX service start | Weekly availability, fault rate by class, interruptions; compare with CSX diesel switcher baseline | Trend improving each month; day-90 target agreed with CSX (TBD) | Logs, CSX baseline | POST-DEMO | None | F46, F53 |  |  | Not started
P-05 | P1 Post-demo (CSX 90-day) | CSX | Daily switching duty met on one charge per shift-day | Whole loco, charging | All | Bill | J-18, J-19 | Run actual CSX duty; log tons/cars per day, energy and charge events | Meets agreed daily duty (DR-47/48, TBD with CSX) without unplanned charge stops | Logs | POST-DEMO | None | F48 |  |  | Not started
C-23 | G0 Bench | Cerritos | Native Simscape plant reproduces the Phase 3 plant in the same harness (switchable plant) | loco_native (native library plant), loco_system | Voltify | Bill | Phase 3 model built; native library component benches pass | run_regression_native: S1-S8 through both plants at 25/40 C (soaked); compare verdict, Tcell, Tsup, SOC, speed and pack current | Same verdict; ¦dTcell¦ < 0.5 K, ¦dTsup¦ < 1 K, ¦dSOC¦ < 0.01, speed rms < 0.1 mph | MATLAB/Simscape | SHOULD | Full (model) | F60, F65 |  | 11/11 pass (2026-10-09/10); Phase 3 solver min-step events at traction transitions (RSK-NEW-40) | Passed | 2026-10-10 | native/results/regression_native_vs_p3_*.csv
C-24 | G0 Bench | Integral (remote) | Measured chopper and charger losses replace the design-basis heat in the PE loop and system models | ITC-0002 choppers, AUX-B002 charger | Integral | Integral + Bill | Integral HV motor-lab tests (Oct 5-7); data request via Jonathan (2026-10-10) | Obtain loss or efficiency vs output current (at least 425 A and 1500 A) with coolant inlet/outlet temperature and flow; update model loss curve; re-run KULI full-peak case and the fault sweep | Loss data received and applied; 45 C baseline chopper fluid <= 63 C, or a mitigation agreed | Integral data package, MATLAB, KULI | MUST | None | F65, F66 |  | Model 1.5 kW vs KULI 4.0 kW per chopper at 425 A (RSK-NEW-38) ¦ v1.2: 2026-10-15 Integral: stall-only dry lab test (1000 V/1000 A, ~5 min), no measured efficiency; simulated loss table at 1170 A received and applied (model Rev C). Waiting: basis per chopper/module, losses at 425/1500 A, charger losses vs power | In progress
H-35 | G3+ Optional extended pre-check | Huntington | PE loop flow balance: every device gets its minimum flow with 3 pumps and with one pump out | PE loop pumps, choppers, ITV charger, inverters, DC-DC converters | Voltify | VJ + Dave | PE loop filled and bled; IFM flow meters installed | Measure total and per-branch flow and the charger loop pressure drop at 4500 rpm (3 pumps) and with one pump off (2 at 4750 rpm); compare with KULI 2026-10-09 | Each chopper >= 20 L/min; charger >= 30 L/min per passage and >= 0.8 bar per loop (or Integral-confirmed values); one-pump-out flow >= 95% of nominal | IFM SU2631 flow meters, pressure gauges, logging | SHOULD | None | F61, F66 |  | KULI: charger 29.7 L/min per passage (28.3 with one pump out); choppers 19.6-19.7 L/min (RSK-NEW-39) ¦ v1.2: Integral: 0.8 bar is nominal at 30 L/min, not a minimum. TMS meeting 10/14: temporary 3/4 in vane flow meters for spot checks; BTMS condenser-loop dry-break QDs cut flow 95.7 -> 79.7 L/min (VJ) | Not started
J-22 | G8 Static charge | Jacksonville | Charger coolant stays inside its limit at full charge power | ITV charger, PE loop, radiator | Voltify + Integral | VJ + Micah | J-06 power ramp; Integral-confirmed limit location (RSK-NEW-39) | During J-06 at the highest available ambient, log charger inlet and outlet coolant temperature and flow at full static charge power; project to the design ambient | Charger coolant within the Integral-confirmed limit (55 C at the confirmed location) at full power, projected to the design ambient | Logged coolant temperatures and flow, ambient sensor | MUST | None | F66 |  | KULI 40 C: 59.0 C outlet vs 55 C limit if outlet-based ¦ v1.2: Integral confirmed 55 C applies to the inlet (2026-10-15) | Not started
J-23 | G7 Charging infra | Jacksonville | HSCB integration: close/trip on command, trip on injected overcurrent, polarity and ITV-enable interlocks | HSCB A/B, REV+CB VIO, panto panel, ITV | Voltify | Micah | J-05; Secheron trip setting coordinated with prospective battery fault current (RSK-NEW-16 condition c) | Close/trip on command; secondary current injection to trip; verify trip removes ITV enable and HSCB opens on polarity disagreement | Trips within Secheron spec at the coordinated set point; interlocks hold | Scope, secondary current injection set, HV probes | MUST | Partial | F09, F67 |  | v1.1: replaces P-03 (HSCB retained for demo, RSK-NEW-16) | Not started
J-24 | G7 Charging infra | Jacksonville | Roof bus is dead with pantographs down | Charger contactor panel, panto panel, VMS, ITV | Voltify | Micah | H-29 Megger; HV bring-up | Battery connected, pantos down: command charger contactors closed and confirm the interlock blocks it; measure roof bus voltage | Charger contactors cannot close with pantos down; roof bus below 50 V | HV probes, DMM | MUST (safety) | None | F68 |  | v1.1 new (RSK-NEW-43) ¦ v1.3: Jonathan: VMS folds pantos only after the panto contactor panel opens; test both the VMS sequence and the hardware interlock | Not started
C-25 | G0 Bench | Cerritos | Model Rev C: D77 curve, Integral chopper loss, 42 in wheels; CSX4091 yard baseline | loco_system (+locosys axle, params, report) | Voltify | Bill | D77-D78.pdf; Integral loss table (2026-10-15); CSX4091 trace | run_regression_phase2 (phase2 baseline unchanged); run_csx4091_baseline on Rev C and legacy settings | Phase 2 regression physics deltas < 0.01 K and < 0.001 SOC; CSX4091 energy balance closes within 2%; verdict recorded | MATLAB/Simscape | SHOULD | Full (model) | F49, F65 |  | 73/80 regression (7 = S6 report-label bug, fixed); CSX4091: 812 kWh out, OPTIMAL; legacy 841 kWh | Passed | 2026-10-16 | results_csx4091_20261016_0823.mat
C-26 | G0 Bench | Cerritos | Model Rev D: clean numerics and drivetrain loss decomposition | loco_system (+locosys), decompose_csx4091 | Voltify | Bill | C-25 | Smooth friction-brake / TE-sign / precharge switching; test zero-crossing on; decompose CSX4091 energy into battery, chopper, motor, gear, brake, TMS and aux; I^2t check vs D77 ratings | Solver warnings < 100 per 25 h run; decomposition closes within 2%; native plant agrees within C-23 limits | MATLAB/Simscape | SHOULD | Full (model) | F49, F50, F65 |  | RSK-NEW-40, -48, -50 ¦ v1.4: decomposition done (decompose_csx4091.m, 0823 Rev C run): closes exactly (residual 0.0 kWh, Ah vs SOC 0.00%); yard chopper 97.7%, motor 77.4%, gear 97.0% while motoring; battery-to-wheel 45.4% day. Open: smooth switching numerics, solver-warning count, I^2t vs D77 ratings, native-plant comparison | In progress |  | results/decompose_csx4091_20261016_0823.csv
J-25 | G7 Charging infra | Jacksonville | Demo charge limit is enforced on both sides: wayside and locomotive | DPS100 x2, ground ESS, VMS charge request, ITV | Voltify site team + Voltify | Oren / Matan + Micah | J-03, J-07 | Set and read back DPS100 limits (833 A each) and ESS 0.5C limit; command the VMS/ITV request above 2.1 MW and confirm it is capped; log wire V/I | Wire current never above 1,666 A; wire power never above 2.1 MW; VMS request capped at 2.1 MW; ESS stays inside 0.5C | Wayside meter, DAQ, CAN logs | MUST | None | F06 |  | DR-17 (Jonathan 2026-10-12) | Not started
C-27 | G0 Bench | Cerritos | Model: Showcase 2 at the demo limit (2.1 MW) stays inside charger, PE and cell limits | loco_system (S9 trace) | Voltify | Bill | C-25; traces/S9_dyncharge_2p1MW_demo.csv | run_loco_system S9 from 20% SOC at 25/40/45 C (precond and soaked); compare with S3 (2.5 MW) and S4 (3 MW) bounding cases | Verdict OK or better at the design ambient; charger inlet margin reported; time 20->95% SOC reported | MATLAB/Simscape | SHOULD | Full (model) | F06, F54, F66 |  | RSK-NEW-22, -39 | Not started
Summary
Total tests
MUST tests
Huntington exit tests
TREND tests (JAX ramp)
Post-demo tests
Passed
Blocked/Failed
First proven on loco (no Cerritos coverage)

## FMEA
ID | Item / interface | Function | Failure mode | Effect | S | Potential cause | O | Current controls | D | RPN | AP | Recommended action | Owner | Linked tests | Plain English (exec) | Action status
F01 | E-Stop dispatch tree | Remove all HV energy in order | Contactors open while current still flows | Contactor weld or arc; HV stays live; fire or shock risk | 10 | T1/T2/T3 delays undefined; ITV/choppers slower than contactor timer | 6 | Hardware-only disconnect paths in design; no timing test yet | 6 |  |  | Define T1-T3 numerically with Integral; scope-test on bench and at full V | Micah + Integral | C-06, H-09, J-10 | Emergency stop might open switches under load and weld them. We will time it on the bench and at full voltage. | Open
F02 | DC-link contactor control | Connect battery to choppers safely | Two controllers command the same contactor (VMS VIO vs LCC) | Precharge skipped, inrush, contactor weld, chopper damage | 8 | Arch doc says VMS VIO owns it; deck FER page says LCC controls all FER switchgear | 5 | None; open conflict | 5 |  |  | Write one ICD line: who commands, who monitors, interlock between them; Jonathan 2026-10-12: Integral is the only master of the DC-link to TRB-bus contactors; write this ICD line and remove the VMS VIO path from the architecture doc | Jonathan + Integral | C-05, H-07 | Two computers think they control the same main switch. One owner must be written down. | Open
F03 | Precharge circuit | Charge DC-link capacitance before main close | Precharge too slow or resistor overheats | Main contactor closes on large dV; resistor or contactor damage | 8 | Capacitance larger than sized (ITV 13,770 uF + LCF 9,200 uF + choppers) | 4 | Close threshold raised to 99% in sim | 4 |  |  | Verify resistor energy rating vs total capacitance; test with cap bank | Mitchell | C-05, C-14, H-07 | Start-up charging circuit may be undersized for all the capacitors now connected. | Open
F04 | String paralleling | Connect 6 strings to one bus | Strings at different voltages connected together | Large circulating current; fuse blows; pack damage | 9 | Connection algorithm not yet validated; combiners not developed | 5 | BCU voltage data available | 5 |  |  | Define dV limit; test with 2 strings; enforce in VMS | Micah | C-04, H-05 | Battery strings at different charge levels could short-circuit each other when joined. | Open
F05 | BMS data path | Give VMS cell limits | BCU data lost or stale (Modbus TCP, no ESMU) | VMS runs blind; over-charge or over-discharge | 9 | Ethernet fault; BCU reboot; no watchdog | 5 | BCUs integrated on bench | 5 |  |  | Comm-loss timeout -> open contactors; test by unplugging; Jonathan 2026-10-13: if a string stops reporting, isolate that string with its combiner panel contactors, derate the system and alert the operator | Micah | C-03, H-21 | If the battery stops reporting, the system must shut down, not keep running blind. | Open
F06 | Cell charge rate | Accept charge without damage | Charge current above cell rating | Accelerated aging, lithium plating, heat | 8 | Demo limit 2.1 MW at the wire (ground ESS 0.5C, <= 1,666 A) = 0.42C into 5.02 MWh, inside the 0.5C cell rating; 3 MW dynamic target retired for the demo | 3 | VMS power limit (not yet validated) | 6 |  |  | Cap the VMS/ITV charge request at 2.1 MW; verify wayside limits in J-25; Jinko/BMS written limit still needed post-demo (MCS 2.25 MW/port) | Bill + Micah | J-06, J-09, J-25 | The demo charger site can only deliver 2.1 MW, which keeps the battery below its charge rating. | Open
F07 | Battery cooling | Hold cell temperature during fast charge | Cooling can't keep up | Charge derates or stops mid-demo | 6 | ~38 kW battery heat est.; only 1 of 3-4 modules in bring-up; Florida heat | 6 | BTMS rated 60 kW | 5 |  |  | Bring up all modules; pre-cool before demo; measure in J-06 | Jack / VJ | C-11, H-15, J-06 | Battery may get too hot during the charging demo and slow down. | Open
F08 | Pantograph contact at low speed | Carry ~960 A per head at 0.5 mph | Strip or wire overheats (near-static contact) | Strip damage, wire damage, arcing | 7 | Dynamic rating assumes speed; at 0.5 mph the contact point barely moves | 5 | Supplier static rating (971 A x2) in HLR | 7 |  |  | Confirm static/low-speed rating with supplier; IR camera on ramp | Dave / Micah | J-04, J-06, J-08, J-09 | At walking pace the pantograph behaves almost like a parked one and may overheat. | Open
F09 | Polarity selection | Present correct polarity to charger | Wrong polarity to ITV | Charger damage | 9 | Polarity sense fault; reverser fault | 3 | Opto + isolated amp dual sensing | 4 |  |  | Test both polarities live (J-05); interlock HSCB on polarity agreement (J-23) | Micah | C-13, J-05, J-23 | Power could arrive backwards and damage the charger; two sensors check it. | Open
F10 | Pantograph fold | Fold on E-Stop or power loss | Pantograph stays up | Wire or roof damage while moving | 10 | Firmware or actuator fault; HW timer not tested | 3 | Hardware timer fold path | 5 |  |  | Test fold with MCU disabled; fold under motion | Micah | C-13, J-10 | The pantograph must drop by itself in an emergency; not yet tested. | Open
F11 | Loco <-> wayside handshake | Coordinate charging | Handshake not ready or unstable | No charging demo | 8 | Panto firmware + PLC software unfinished; single owners (Micah, Yoni) | 7 | Simulator; Gantt line 79 | 3 |  |  | Hire/assign firmware backup; joint SIL test before site | Bill + Matan | J-07 | Locomotive and charger software must talk; few people know it. | Open
F12 | ITV onboard charger | Convert wire power to battery charge | ITV not delivered in time | No dynamic charging (fallback = static only) | 8 | Integral builds ITV after choppers; no date; ITV date per Jonathan: Oct 19 if all goes well, end of October latest | 7 | Weekly Integral status | 2 |  |  | Get ITV/LCF build date from Integral now; decide fallback demo; No dynamic charging without the ITV (F69); fallback demo is static charging only | Jonathan | J-06 | The onboard charger has no delivery date; without it, no dynamic charging. | Open
F13 | AES wayside charger | Supply wire power | Charger arrives late | No on-site charging test window | 8 | Supplier lead time; late Nov-mid Dec | 7 | CEO escalation (Oren) | 2 |  |  | Expedite; plan static tests to start day 1 of arrival | Oren | J-03 | The track-side charger may arrive mid-December. | Open
F14 | Pantograph hatch | Support pantos, seal roof, keep clearance | Hatch late or outside Plate M | Pantos not fitted; clearance violation in transit | 7 | Final design/venting open; build into Dec | 6 | Design frozen except venting | 4 |  |  | Freeze venting; decide ship-with or ship-without pantos | Dave / Dragan | H-22, J-04 | Roof structure for the pantographs is the last item and runs into December. | Open
F15 | Isolation monitoring | Detect HV leakage to chassis | Ground fault not detected | Shock risk to crew; second fault = short | 10 | Continuous ground-fault detection exists (Jonathan 2026-10-13); unconfirmed whether it senses the TRB-bus (source) or only the DC-link | 4 | MCS isolation check only at the inlet | 7 |  |  | Confirm the detector senses the TRB-bus; add a manual IR rule only if it does not; verify in H-06 | Jonathan | C-16, H-06, J-01 | Nothing continuously checks the high-voltage system for leaks to the frame. | Open
F16 | Grounding switch + RTV | Prevent access to live HV | Lever moves while HV present | Electrocution | 10 | RTV not developed; interlock not tested | 3 | Design: EM release only <50 V for 5 s | 4 |  |  | Build and test RTV before first HV at Huntington | Micah | C-15 | Maintenance safety lock is not built yet; it must work before full voltage. Padlock is optional for the tow; the interlock is not. | Open
F17 | 72 V system | Keep control and wake circuits alive | 72 V battery drained during a tow of up to 1.5 weeks | Monitoring goes dark; cannot wake on arrival | 6 | Telemetry and BCUs run from the 72 V battery with HV off | 6 | Deep sleep design (~50 W) | 4 |  |  | Pick lean monitoring mode; measure draw (H-19); size against 650 Ah battery | Mitchell | H-19 | The small 72 V battery powers monitoring during the tow; it must last the whole trip. | Open
F18 | 750V-PS | Feed all aux loads | Converter trips | Loss of compressor, blowers, cooling during motion | 8 | Transients from inverters/choppers; control-V loss | 4 | Supplier: no uncommanded op on control-V loss | 5 |  |  | Transient test with real loads (H-08) | Mitchell | C-07, H-08 | One converter feeds every auxiliary; if it trips, cooling and air stop. | Open
F19 | Brake compressor | Keep main reservoir pressure | Compressor won't start (inrush) | Low air; brakes apply; can't move | 8 | Inrush 5-6x FLA on one inverter | 4 | Test stand being built | 4 |  |  | Characterize inrush; soft-start settings | Dave / Integral | C-09, H-08 | Air compressor start-up current is high; tested on a stand first. | Open
F20 | Traction blowers | Cool traction motors | Blowers off or low | Motor overheating in 20-min run or on the trip | 7 | Inverter integration by Integral pending | 4 | Motor temp limits in LCC (assumed) | 5 |  |  | Verify blower speeds vs motor current | Integral | C-10, H-15 | Motor cooling fans must run whenever the motors pull load. | Open
F21 | LCC <-> VMS interface | Exchange limits and commands | Message mismatch (PGN/DBC versions) | No traction, or limits ignored | 7 | Spec R2 PGN changed 10/5; simulator not updated | 6 | Simulator v1.4 | 4 |  |  | Put DBC under version control; SIL test before Huntington | Micah + Bailey | C-02, H-04, H-11 | Two companies' software must use the same message dictionary. | Open
F22 | Battery power limit | Keep battery inside 1,884 A / 2.5 MW | LCC draws more than battery allows | Over-current trip or damage | 8 | 4 choppers x 655 kW = 2.6 MW > 2.5 MW ESS peak; Notch 8 (~3,000 hp) needs ~2.5 MW at battery | 4 | VMS power-limit message | 5 |  |  | Test limit change response (C-02); cap in LCC config | Micah + Integral | C-02, H-14 | Motors can pull slightly more than the battery's peak rating; software must cap it. | Open
F23 | Choppers + D77 motors | Turn wheels with control | Wrong direction or unstable control | Damage, no motion | 6 | Field wiring; tuning on real motors | 5 | Integral motor-lab test Oct 5-7 | 4 |  |  | Axle-by-axle creep test | Integral | H-12, H-16 | Each motor is checked one by one at walking speed first. | Open
F24 | Air brake / CCB2 + alerter | Stop the train; alert crew | Brake or alerter not integrated with new control | Can't pass FRA tests; unsafe | 9 | New control system; LCC integration | 4 | Standard FRA tests | 3 |  |  | Run full brake tests at Huntington | Dragan + Integral | H-10, H-13 | Brakes and alerter must pass federal tests before any move. | Open
F25 | Dynamic brake (CSX yard ops) | Control speed in switching service | No dynamic brake | More air-brake wear in yard use | 5 | HLR: no dynamic/regen braking; GP40-V spec asks for DB grids | 3 | Air brakes; low switcher speeds | 3 |  |  | Confirm CSX accepts air-only braking for Moncrief duty | Daphna | J-11 | No electric brake; acceptable at switcher speeds, to be confirmed with CSX. No longer a transport issue. | Open
F26 | Pack SOC for the tow | Arrive safe and usable | SOC outside the tow window | Too high = more stored energy in an incident; too low = cannot run at JAX before charging infrastructure exists | 6 | No defined tow SOC; BMS off in transit | 4 | None defined | 4 |  |  | Set window (proposed 30-50%) with CSX hazmat; verify at H-24 | Bill | H-24, J-01 | Battery charge for the tow should be moderate: safe to haul, enough to run on arrival. | Open
F27 | CSX dead-in-tow acceptance | Allowed to move in a CSX train | Not accepted in time | Locomotive stuck at Huntington; schedule slip | 7 | 229 inspection, brake test, battery paperwork, routing not arranged | 5 | None yet | 3 |  |  | Start CSX mechanical + hazmat engagement now; book carman for H-23 | Daphna / Dragan | H-23 | CSX must accept the locomotive as a towed unit; not arranged yet, but simpler than running under its own power. | Open
F28 | Transport vibration | Hold joints and packs | Bolts loosen, connectors back out, packs shift | Hot joints, arcing, open circuits | 8 | 750-900 mi of vibration plus coupling impacts in yards | 6 | Torque spec; paint marks planned | 5 |  |  | Torque + mark; restrain packs; no-hump instruction; shock logger; re-check at J-01 | Production lead | C-17, H-24, J-01 | Shaking and coupling bumps over the trip can loosen high-current joints and shift packs. | Open
F29 | Coolant system | Cool battery and electronics | Leak or wrong fill | Pump dry run; shorts | 7 | New VOSS plumbing; PVC adapters near temp limit | 4 | G-48 50/50 spec chosen | 5 |  |  | Pressure test; use stainless adapters | VJ / Jack | C-11, C-12, J-01 | Coolant leaks near high voltage are both a thermal and an electrical risk. | Open
F30 | PE cooling balance | Cool choppers and ITV | Too little flow to one branch | ITV or chopper derate | 6 | Shared loop; branch balance | 4 | VJ re-routing proposal | 5 |  |  | Measure branch flows | VJ | C-12, H-15 | Cooling flow must be split evenly between charger and choppers. | Open
F31 | 24 V PDMs / breaker panels | Power controllers | Wrong channel or trip | Controller dark; contactors drop | 6 | New PDM topology (10/6) | 5 | Bench test of PDMs | 4 |  |  | Channel map test at power-up | Mitchell | H-02, H-03 | Low-voltage power boxes were re-laid-out this week; we check every channel. | Open
F32 | E-Stop line as enable | Allow operation | Single wire break stops loco | Nuisance stop (fail-safe) | 4 | 72 V enable loop length | 5 | Fail-safe design | 3 |  |  | Loop integrity check in daily checklist | Mitchell | H-03 | A broken wire stops the loco safely; it is an availability issue, not safety. | Open
F33 | Remote access | Monitor remotely | Unauthorized command via VPN/Starlink | Unsafe command | 8 | Remote access to VMS | 2 | VPN, credentials | 6 |  |  | Read-only remote mode during transport and demo | Matan | T-01 | Remote connections should be read-only while the loco moves. | Open
F34 | People single points | Keep bring-up moving | Key engineer unavailable | Stalled bring-up | 7 | Micah (firmware), Yoni (simulator) leave in crunch | 7 | Documentation push | 2 |  |  | Pair a backup on each; document daily | Bill | all | Some critical knowledge sits with one person. | Open
F35 | BTMS power supplies | Feed cooling skid | Supply undersized vs loads | Cooling skid brown-out | 5 | Arch doc 12V 3.25 kW vs deck 6 kW 12V + 7 kW 24V | 4 | Deck values newer | 4 |  |  | Reconcile in power budget | Jack | C-11 | Two documents disagree on cooling power supply sizes. | Open
F36 | Shop charging at Huntington | Recharge pack | Supply connected around protections | Over-charge, shock | 9 | No defined entry point; MCS controller not developed | 4 | None defined | 5 |  |  | Write a charging procedure and entry point before first use | Mitchell | H-18 | How the shop charger plugs in is not defined yet. | Open
F37 | Contactor feedback | Report true contactor state | Welded contactor reported open | HV present when believed off | 10 | Aux contact failure | 3 | RTV checks voltage before grounding | 4 |  |  | Cross-check aux vs HV sense every open command | Micah | C-06, C-14, H-09 | A stuck switch could look open on screen; voltage sensors double-check. | Open
F38 | Traction motors in tow | Stay electrically dead while wheels turn | Motors generate voltage as the wheels turn | Voltage on chopper/DC-link with control off; arcing; shock risk to responders | 9 | Residual field magnetism; MCO/reverser state unknown with LCC unpowered; manual TM cutout switches removed per spec | 4 | None defined | 5 |  |  | Define motor isolation with control off (MCO open / reverser centered / leads lifted); verify by test H-25 | Integral + Mitchell | H-25 | Towed motors can act as generators; we must prove they are disconnected. | Open
F39 | MU trainlines | Ignore lead-unit commands while dead | Prototype responds to MU trainline signals | Unexpected contactor or inverter action in train | 7 | New control system wired to MU receptacles | 3 | Isolation switch in ISOLATE | 5 |  |  | Isolate MU receptacles or prove LCC ignores trainlines (H-27) | Integral | H-27 | Commands from the lead locomotive must not reach the prototype's systems. | Open
F40 | Dead-engine air brake | Brake with the train while towed | Dead-engine setup wrong | No brakes on the loco, or brakes dragging (wheel overheating) | 9 | New CCB2 install; DIT setup not practiced | 4 | Class I brake test before departure | 4 |  |  | Follow NYAB DIT procedure; test H-20 before CSX inspection | Dragan | H-20, H-23 | The locomotive's air brakes must work from behind another engine. | Open
F41 | Bearings and gear lube | Turn freely for 750-900 mi | Hot journal or suspension bearing | Bearing seizure; train stop | 9 | Rebuilt trucks; long idle; lube not refilled | 3 | Wayside hot-box detectors on CSX | 4 |  |  | Fill and record lube; inspect bearings (H-26) | Dragan | H-26 | Wheel and motor bearings must be lubricated before a long tow. | Open
F42 | Pantographs in tow | Stay down and attached | Pantograph lifts or a part detaches | Strike on structures or wires | 9 | Actuator spring/air; loose hardware | 2 | Folded; Plate M check | 4 |  |  | Mechanical lock or tow without pantos fitted (H-22) | Dave | H-22 | Pantographs must be locked down or not fitted for the tow. | Open
F43 | Emergency response in transit | Responders act safely | Responders unaware of an energized Li-ion pack | Unsafe response to an incident | 9 | Prototype not in any CSX hazmat profile | 3 | None defined | 5 |  |  | Emergency response sheet, placards, 24/7 contact; CSX hazmat review (H-28) | Bill | H-28 | Railroad responders need clear battery and HV information on board. | Open
F44 | Thermal event in transit | Detect a pack problem | Cell overheating not noticed | Fire spreads before detection | 10 | No rider; BMS may be unpowered; no fire sensor confirmed | 2 | None defined | 7 |  |  | Lean telemetry with alerts (BCU temps + smoke sensor) or standalone temperature logger with cellular alert | Matan / Micah | H-19, T-01 | If a cell overheats during the tow, someone must find out quickly. | Open
F45 | Electric handbrake (Graham-White) | Apply/release with the loco dead | Cannot release or apply with 72 V off | Dragging handbrake in tow (wheel flats, overheating) or no securement | 8 | Electric unit needs control power; manual method not verified | 4 | Spec breaker only bypasses the brake-applied signal | 5 |  |  | Verify manual apply/release procedure; test H-33 | Dragan | H-33, H-23 | The electric parking brake must work with the power off, or the loco cannot be towed safely. | Open
F46 | Fault classification at Huntington exit | Separate blocking faults from minor ones | Class A fault left open or classified as B | Locomotive shipped to JAX with a latent safety or control fault | 8 | No classified fault list yet; two suppliers fault codes | 5 | None yet | 4 |  |  | Classify every VMS and LCC fault code A/B/C before G3; joint review with Integral | Micah + Bailey | H-31, H-13 | We must agree which faults stop the loco and which can be fixed in Jacksonville. | Open
F47 | Manual fault override | Allow motion with minor faults | Override masks a protective function | Unsafe motion; component damage | 9 | Override applied without scope or time limits | 3 | None | 6 |  |  | Overrides only on the Class B list; per code, per session, logged, two-person sign-off; never on Class A | Bill | H-13, H-31 | Overriding a minor fault must never switch off a safety function. | Open
F48 | Data logging | Capture data from first power | Logging not running, gaps, or sources not time-aligned | No empirical basis for range or performance; minor faults cannot be diagnosed at JAX | 6 | Starlink incomplete; logger config; VMS, LCC and BCU clocks not synced | 6 | VMS logs (partial) | 5 |  |  | Freeze signal list (Data Logging tab); verify H-32; store-and-forward when offline | Matan + Jared | H-32, J-18, J-19 | If we do not record data from day one, we cannot estimate range or fix minor faults later. | Open
F49 | Notch 8 short-time power | Deliver full power for 15 min | Battery, chopper or motor limit derates before 15 min | Misses CSX convergence target | 6 | Notch 8 needs ~2.5 MW = ESS peak (1,884 A); choppers 2.6 MW; cooling sized for 0.5C; Model Rev C: Notch 8 is power-limited (2.144 MW -> 20.4 mph on LC-3/0.5%); motors ~1,060 A vs D77 15-min rating 1,150 A (RSK-NEW-17/48) | 6 | VMS power limit; LCC derate | 4 |  |  | Trend in J-17; size limits and cooling from data; Add D77 I^2t/time-rating check to the model report; size J-17 load at the agreed power cap (RSK-NEW-49) | Micah + Integral | J-14, J-17, P-01 | Full power for 15 minutes sits right at the battery limit; we will trend it in Jacksonville. | Open
F50 | Continuous pull at 10 mph | Sustain GP40 continuous tractive effort | D77 motors or choppers overheat; blower airflow short | Derate in heavy switching | 6 | High current at low speed for long periods; blower inverter integration pending; PE loop margin | 5 | Motor temperature limits in LCC (assumed) | 5 |  |  | Trend in J-16; confirm blower airflow vs motor current | Integral + VJ | J-15, J-16, P-02, C-10 | Pulling hard at low speed for a long time heats the motors; we will test in steps. | Open
F51 | SW/FW configuration | Run the agreed software on every controller | Wrong or mismatched versions (Voltify vs Integral) | Comms faults, wrong limits, faults that cannot be reproduced | 7 | Many controllers, two companies, field updates | 5 | Jared release process (Voltify only) | 4 |  |  | Version manifest with checksums for every node; joint release; re-verify after each update | Jared + Integral | H-30, H-04 | Every controller must run the agreed software version, and we write it down. | Open
F52 | Megger test | Prove HV insulation | Test voltage damages electronics or sensors | Damaged controllers, sensors or EMC capacitors; false failures | 7 | 2.5-5 kV applied with semiconductors, sensors or Y-caps connected | 4 | C-16 at harness level only | 4 |  |  | Written Megger procedure: isolate or short electronics; voltage per component rating; discharge after | Mitchell | H-29, C-16 | The insulation test uses high voltage; electronics must be disconnected first. | Open
F53 | Switcher stop/go duty | Survive frequent start/stop cycles | Contactor and precharge cycle wear; thermal cycling | Early contactor failure; nuisance faults in CSX service | 5 | Switching means many cycles per shift; contactor life is rated in cycles | 4 | None | 6 |  |  | Count cycles in J-18; check contactor ratings vs projected daily cycles | Mitchell | J-18, P-04 | Many stops and starts wear switches faster than mainline use. | Open
F54 | PE loop radiator | Keep PE coolant within device limits in hot ambient | Charger supply > 55 C or inverter > 60 C above ~46-50 C ambient (fans healthy); see F59 for fan loss | Charger or inverter derate/trip; charging or full power lost on hot days | 7 | Radiator sized at 40 C (KULI 47.9 kW); margin 2 K at 40 C (sweep) | 4 | KULI PE review; Phase 2 sweep | 4 |  |  | Set design ambient (DR-52); add radiator margin or flow; confirm whether 55 C is supply or outlet limit; derate map | VJ + Integral | J-20, C-19 | On very hot days the electronics cooling runs out of margin before the battery does. | Open
F55 | Condenser loop | Reject chiller heat | Condenser coolant 69 C at 50 C ambient and 66.4 C at 45 C during heavy duty with charging (check valves 65 C); chiller capacity -20% | Chiller high-pressure trip; battery cooling lost | 7 | Maxwell TMS designed for -10 to 45 C ambient; 45 C baseline exceeds check valve by 1.4 K (fault sweep) | 5 | KULI condenser review; sweep | 5 |  |  | Fix ambient envelope; specify check valves >= 80 C or relocate; obtain MTM capacity map | Jack + Maxwell | J-20, C-19 | Above 45 C the chiller loop exceeds its valve ratings. | Open
F56 | BMS low-temperature limits | Allow operation after a cold soak | As-shipped Jinko thresholds block charge and discharge below 3 C | Loco cannot move or charge until preheated (~4.0 h from 0 C with the 12 kW heater) | 6 | Jinko defaults; cell spec allows discharge to -30 C | 4 | None | 3 |  |  | Set Voltify BMS thresholds (discharge to ~-20 C; charge >= 0-5 C with reduced current); preheat procedure | Micah | J-21; sweep S1-S7 soaked 0 C | After a cold night the battery refuses to work until it is warmed, unless we change the settings. | Open
F57 | BMS heating setpoint | Keep the pack in its optimal band | Heater stops at 13.5 C, below the 15-35 C optimal band | Higher resistance and lower charge acceptance in cool weather | 4 | Jinko heating on/off 12/13.5 C | 6 | None | 3 |  |  | Raise heating on/off to ~15/18 C; re-run sweep | Micah | J-21, C-19 | The heater switches off before the battery reaches its best temperature. | Open
F58 | Preconditioning | Start each duty inside the temperature band | Pack left soaked (no standby TMS power) | 1.3-4.0 h recovery before full capability (12 kW heater); 100-210 kWh TMS energy on a hot day | 6 | No preconditioning requirement or procedure | 5 | None | 4 |  |  | Define preconditioning requirement (DR-53): standby TMS on wayside or battery; add to operating procedure | Bill | J-21, C-19 | A battery left sitting in the heat or cold needs hours of conditioning first. | Open
F59 | PE radiator fan bank | Reject PE heat on hot days | Fans fail (supply, controller, motor) while hauling | Chopper fluid > 63 C 14 min after fan loss at 40 C and 10 min at 45 C (fault sweep, POC baseline); 8 K margin left at 20 C; traction derate or trip | 7 | Single fan bank on PE radiator; no fan status to VMS defined | 4 | None | 5 |  |  | Fan speed/current feedback to VMS; Class B alarm + traction derate on fan fault; check partial-fan capacity; spare fan | VJ + Micah | J-20, C-21 | If the electronics radiator fans stop on a hot day, the choppers overheat within minutes. | Open
F61 | PE loop pumps | Circulate PE coolant | Pump stops (pump, controller, DCC65M24 24 V supply trip) or flow blocked | Chopper fluid 110-134 C at once under load (fault sweep, PE_PUMP_FAIL and BTMS_24V_PS_TRIP); chopper trip or damage; coolant boiling | 9 | No flow measurement defined; detection relies on temperature (lags) | 3 | PE cooling controller pressure/level sensing (per architecture doc) | 6 |  |  | Add pump speed/flow feedback; immediate traction inhibit on PE flow loss (Class A); verify in H-34 | VJ + Micah | H-34, C-21 | If the electronics coolant stops moving, the choppers overheat almost immediately. | Open
F62 | Axle cut-out (3 of 4 axles) | Keep hauling with one axle out | Adhesion and power drop to 3/4 | LC-3 (3,640 t on 0.5%) cannot hold 6 mph; remaining motors run ~20 K hotter (fault sweep) | 6 | Chopper or motor fault isolates an axle | 4 | LCC traction motor cut-out (computer-controlled per GP40-V spec) | 3 |  |  | Define reduced tonnage rating with 3 axles (~75% of 4-axle rating) in the operating procedure; add starting (breakaway) resistance to the model (C-22) | Dragan + Bill | C-21, C-22 | With one axle out the loco pulls about a quarter less. | Open
F63 | Cell temperature sensing | Give the BMS a true cell temperature | Sensor bias +5 K or -5 K | +5 K: chiller over-runs (TMS energy +70-130%), condenser over 65 C at 45 C; -5 K: cooling starts late and BMS protects late | 7 | Sensor drift or placement not representative of hottest cell | 3 | Multiple cell sensors per module (BMS) | 6 |  |  | Plausibility check across sensors; review sensor placement vs hottest cell; long-duty check in C-22 | Micah | C-21, C-22 | A wrong temperature reading either wastes energy on cooling or lets the cells run hot. | Open
F64 | Traction motor blowers | Cool D77 motors | Blowers lost (blower fault or 1500-750 V aux converter trip) | Motor temperature +49 K in 3 h with no limit reached yet; long duty or heavy pulls could overheat motors (placeholder motor model) | 7 | Single blower supply via aux inverter | 3 | LCC motor temperature limits (assumed) | 6 |  |  | Blower status to LCC with derate; confirm D77 thermal limits and model with Integral; long-duty check C-22 | Integral + VJ | C-21, C-22 | Without the blowers the traction motors heat up steadily. | Open
F60 | Auxiliary power budget | Size standby and range energy | Aux budget wrong (Phase 2 used 30 kW base; POC Power Budget values are first-pass estimates) | Range, standby and preconditioning energy mis-estimated | 4 | Budget built from estimates and datasheets, not measurements; blower and fan hardware conflicts open | 5 | load_budget.csv aligned with POC Power Budget Rev B | 5 |  |  | Measure per-bus aux power at Huntington (H-17) and in J-18; update load_budget.csv | Bill | H-17, J-18 | Our estimate of the always-on electrical loads is not measured yet. | Open
F65 | Chopper losses / PE heat basis | Size the PE loop for the real chopper heat | Chopper heat higher than the design basis | PE loop runs hotter; at 45 C chopper fluid ~64 C vs 63 C limit at the KULI basis (estimate); less radiator margin | 7 | No supplier loss data: model 1.5 kW vs KULI 4.0 kW per chopper at 425 A (KULI uses ~1.25% of output); Integral sim 2026-10-15: 2.48 kW per chopper at 1170 A (~0.78 kW at 425 A), basis per chopper vs module unconfirmed; model Rev C uses it | 5 | KULI PE review at reduced chopper load only; chopper cold-plate shutdown 90 C | 5 |  |  | Get Integral HV motor-lab loss data (C-24); re-run KULI at full chopper peak (32.8 kW) and the fault sweep with measured losses | Integral + VJ + Bill | C-24, C-21, J-20 | We do not yet know how much heat the choppers really make; at the high estimate they could overheat on 45 C days. | Open
F66 | HV charger (ITV, AUX-B002) cooling | Keep the charger inside its coolant limits at full charge | Coolant above the 55 C limit or flow below 30 L/min per passage | Charger derate or shutdown during charging on hot days (Showcase 2 power) | 7 | Limit location unstated (inlet/outlet); KULI 40 C: 53.5 C in / 59.0 C out; 29.7 L/min per passage (28.3 with one pump out); 0.8 bar minimum pressure drop not checked; Integral 2026-10-15: 55 C limit is the INLET; 0.8 bar nominal at 30 L/min; onboard derate; margin 1.5 K at 40 C | 6 | Model checks charger supply temperature only; KULI review | 6 |  |  | Integral to confirm limit location and pressure-drop meaning; rebalance charger branch to >= 30 L/min per passage; measure inlet/outlet temperature and flow (H-35, J-22) | Integral + VJ + Dave | H-35, J-22, J-20 | The charger may run hotter than allowed on a hot day, which would cut charging power during the demo. | Open
F67 | Charge-path fault interruption (HSCB A/B) | Interrupt fault current into a roof, pantograph or charge-bus fault | Battery feeds a roof/charge-bus fault through the ITV freewheel diodes (or directly in ITV-bypass / MCS direct mode) | Arc, fire, roof and HVR damage | 10 | Flashover or short on roof, pantograph or charge bus with charger contactors closed | 3 | HSCB A/B between panto panel and ITV; combiner string fuses as backup | 5 |  |  | Close RSK-NEW-16 conditions (Integral back-feed confirmation, Jinko short-circuit impedance, Secheron trip curve vs I2t); HSCB trip test J-23 | Jonathan | J-05, J-23 | If something shorts on the roof, the battery can push huge current back through the charger; the HSCB is what cuts it off. | Open
F68 | Roof bus isolation | Keep roof conductors dead when pantographs are down | Roof bus sits at battery voltage with pantos lowered | Shock risk to roof workers and responders; fault exposure | 9 | Charger contactors closed with pantos down; ITV freewheel diodes energize the roof side | 4 | None defined | 6 |  |  | Require charger contactors open whenever pantos are down (VMS logic plus hardware interlock); verify with J-24 | Micah | J-24 | With the pantographs down the roof wiring could still be live from the battery unless the charger is cut off. | Open
F69 | Dynamic charging without the ITV (fallback) | Charge through the pantographs safely | Pantographs feed the TRB-bus directly with no filtering | Contact-wire transients reach the Zekalabs 750V-PS (1.7 kV SiC) on the same HVR TRB-bus port; little spike margin when charging near 1.5 kV; 750 V aux loss | 8 | ITV late; contact-wire to moving-pantograph voltage not stable | 4 | None if the ITV-bypass mode is used | 6 |  |  | Do not run dynamic charging without the ITV; ITV-bypass allowed for static charging only after a surge/filter review | Jonathan + Micah | J-09, J-25 | Without the onboard charger, voltage spikes from the overhead wire could hit our 750 V supply directly. We will not run dynamic charging without it. | Open
Scale
S (severity): 10 = injury/fire without warning; 8-9 = loss of primary function or regulatory; 5-7 = degraded / demo at risk; 1-4 = nuisance.
O (occurrence): 7+ = expected given current status; 4-6 = plausible; 1-3 = unlikely. D (detection): 1-3 = test planned before exposure; 4-6 = found during integration; 7+ = likely missed until field.
AP rule (simplified): H if S>=9 & O>=4, or S>=7 & O>=6, or S>=9 & O>=2 & D>=7. M if S>=7 & O>=4, or S>=5 & O>=6, or S>=9 & D>=5. Else L.
Count of H
Count of M
Count of L

## Fault Classes
Class | Definition | Huntington exit rule (G3) | Movement rule | Examples: Voltify (VMS, BMS, HV) | Examples: Integral (LCC, choppers) and donor | Disposition
A — Blocking | Loss or degradation of a safety function, HV protection, braking, or loss of control authority. Never overridden. | Zero active or latched at exit. Any occurrence during H-31 or H-13 resets the gate. | No motion. Abort test move; make safe; root cause before retry. | E-Stop loop open or E-Stop path inoperative; HV isolation below limit; contactor feedback mismatch or weld; precharge failure; cell over/under-voltage or over-temperature; BMS (BCU) comm loss; RTV/grounding interlock fault; DC-link overvoltage | LCC<->VMS heartbeat loss; chopper overcurrent/desat trip; traction motor ground fault; brake/penalty or alerter inoperative; reverser/MCO position disagreement; handbrake-applied inhibit failed | Fix at Huntington. Ship only with zero Class A.
B — Degraded / overridable | Fault that reduces capability or diagnostics but leaves safety functions intact. May be overridden for a defined test move. | Allowed if listed with a cause hypothesis, an override plan and a JAX owner. | Motion allowed at <=5 mph (Huntington) or per test card, with override logged. | Non-critical node missing (panto ctrl, MCS ctrl, unused BTMS module); intermittent CAN error frames below threshold; redundant sensor disagree with the primary healthy; telemetry/Starlink offline; HMI display fault; aux converter warning without trip | Blower speed-feedback fault with airflow verified; non-critical temperature sensor open; slip-control tuning warning; event-recorder or display fault | Troubleshoot at Jacksonville (G6). Re-classify to A if it recurs 3+ times or masks an A.
C — Information | No functional effect. | No limit; log only. | No restriction. | Version notices; logging gap < 1 min; configuration reminders | Status messages; maintenance-due notices | Review weekly.
Override rules (Class B only)
1. Overrides apply to one fault code, for one test session, and expire at power-down.
2. Two-person sign-off: Voltify HV-qualified engineer + Integral field engineer (for LCC/chopper codes).
3. Log who, when, why, which code and the test card in the override log (Data Logging group 12).
4. Never override a Class A code. If unsure of the class, treat it as A.
5. Daily review of overrides; a B that recurs 3+ times is reviewed for re-classification to A.
6. Every fault code from VMS and LCC is classified before H-31 (FMEA F46).
Fault-code register (fill in; first row is an example)
Fault code | Source | Description | Class (A/B/C) | Override allowed (Y/N) | Owner | Status / notes
EXAMPLE: VMS-0142 | VMS | Pantograph controller heartbeat missing (panto not fitted) | B | Y | Micah | Expected until hatch install; clears at J-04

## Load Cases & Perf
A. GP40 reference and battery-electric equivalent
Locomotive weight (short tons) | 135 | [7 empty] | GP40-V spec 265,000-275,000 lb
GP40 continuous tractive effort (lbf) | 54700 | [7 empty] | GP40 data sheet: 54,700 lbf @ 11.1 mph, 62:15, D77 (thedieselshop.us)
GP40 minimum continuous speed (mph) | 11.1 | [7 empty] | Same source
Target continuous pull speed (mph) | 10 | [7 empty] | Dragan: continuous pull at 10 mph sustained
Adhesion for starting TE | 25% | [7 empty] | Data sheet basis (25%)
Notch 8 traction power target (hp) | 3000 | [7 empty] | Assumption: GP40 rated 3,000 hp (gross); rail hp is lower, so this is conservative
Battery-to-rail efficiency | 88% | [7 empty] | Assumption: chopper ~0.98 x D77 ~0.92 x gear ~0.97
Aux load while moving (kW) | 30 | [7 empty] | Assumption: blowers, cooling, 72 V (architecture doc worst case higher)
ESS energy (MWh) | 5.016 | [7 empty] | Architecture ESS table; 48 batteries, 6 strings
ESS peak discharge power (MW) | 2.508 | [7 empty] | Architecture ESS table (1,884 A)
Usable SOC fraction | 80% | [7 empty] | Assumption 10-90% (DR-18)
Starting tractive effort at adhesion (lbf) | [8 empty] | Starting TE limit for fast switcher starts (adhesion-limited)
Rail power at continuous pull (hp)
Battery power at continuous pull (MW)
Continuous pull C-rate
Hours of continuous pull from usable energy
Battery power at Notch 8 (MW)
Notch 8 battery power as % of ESS peak | [8 empty] | >100% means Notch 8 at 3,000 hp exceeds the ESS peak rating (RSK-NEW-17)
Energy for 15 min at Notch 8 (MWh)
15 min Notch 8 as % of usable energy
Inputs: starting resistance (lb/ton) | 15 | [7 empty] | Assumption: roller-bearing cars, warm, level; cold starts can be higher
B. Switcher load cases (trailing tonnage)
Case | Cars | Tons per car | Trailing tons | Grade (%) | Rolling resistance (lb/ton) | Steady TE needed (lbf) | % of GP40 continuous TE | Starting TE needed (lbf) | Description / basis
LC-0 Light engine | 0 | 0 |  | 0 | 4 |  |  |  | Showcase 1, J-14
LC-1 Industry switch | 10 | 143 |  | 0 | 4 |  |  |  | Assumption: 10 loaded 286k-lb cars; J-15
LC-2 Yard cut | 25 | 143 |  | 0.3 | 4 |  |  |  | Assumption: typical cut on a yard lead; J-15
LC-3 Protect case: GP40-equivalent heavy pull | 28 | 130 |  | 0.5 | 4 |  |  |  | Design/protect case for normal CSX yard ops: sized to ~100% of GP40 continuous TE, so anything a GP40 switcher handles is covered; J-15..J-17, P-02
Maximum trailing tons at continuous TE, 0.5% grade
Maximum trailing tons at continuous TE, 1.0% grade
Stated daily load (tons/day, DR-47) | 20-50 | [7 empty] | As stated by Dragan; equals ~0.15-0.35 loaded cars. Confirm per-move tonnage and cars/day with CSX (RSK-NEW-18)
One loaded car (short tons) | 143 | [7 empty] | 286,000 lb gross rail load
C. Switch duty cycle energy estimate (EPA 40 CFR 1033.530, single idle, switch)
Notch | Time weight | Power (% of rated) | Weighted power (%)
Idle | 0.598 | 0 | [6 empty] | Weights: 40 CFR 1033.530 Table 2 (switch); power %: Table 3
Notch 1 | 0.124 | 4.5
Notch 2 | 0.123 | 11.5
Notch 3 | 0.058 | 23.5
Notch 4 | 0.036 | 35
Notch 5 | 0.036 | 48.5
Notch 6 | 0.015 | 64
Notch 7 | 0.002 | 85
Notch 8 | 0.008 | 100
Sum of weights (check = 1.000)
Average load factor (% of rated)
Notch 8 traction power at battery, excl. aux (kW)
Average aux power over shift (kW) | 15 | [7 empty] | Assumption: between standby (~2.4 kW) and moving (~30 kW)
Average battery power over duty cycle (kW)
Shift length (h) | 8
Energy per shift (MWh)
Shifts per usable pack
Hours of switch duty per usable pack
First-pass range estimate only. Replace with J-18/J-19 measured data (DR-49). Notch power on a battery loco may not follow diesel engine-power notching.
D. Jacksonville ramp-up matrix (trend toward CSX targets; non-gating)
Step | Test | Load case | Target | Hold (min) | Est. battery power (MW) | Est. energy (MWh) | % of usable | Stop if
R1 | J-14 | LC-0 | Notch 1-8 map | 10 |  |  |  | Any Class A; battery > 1,884 A
R2 | J-15 | LC-1/2/3 | Start + accelerate to 10 mph | 10 |  |  |  | Uncontrolled slip; Class A
R3 | J-16 | LC-3 | 50% continuous TE at 10 mph | 15 |  |  |  | Projected temp > limit
R4 | J-16 | LC-3 | 75% continuous TE at 10 mph | 30 |  |  |  | Projected temp > limit
R5 | J-16 | LC-3 | 100% continuous TE at 10 mph | 60 |  |  |  | Projected temp > limit
R6 | J-17 | Heavy | Notch 8 | 1 |  |  |  | Derate; temp > limit
R7 | J-17 | Heavy | Notch 8 | 5 |  |  |  | Derate; temp > limit
R8 | J-17 | Heavy | Notch 8 | 10 |  |  |  | Derate; temp > limit
R9 | J-17 | Heavy | Notch 8 | 15 |  |  |  | Derate; temp > limit
R1/R2 power is a rough average (30% / 60% of Notch 8). Run steps in order; each needs the previous thermal data. Thermal limits come from Integral, Jinko and Maxwell (DR-12).

## Data Logging
# | Signal group | Signals | Source | Minimum rate | Needed for | Priority | Owner | Status
1 | Battery pack | Pack V, I, power, SOC, SOH, charge/discharge limits | BCUs / VMS | 10 Hz (V, I); 1 Hz others | Range, performance, faults | P1 | Micah
2 | Cells and strings | Cell min/max V and T, string currents, string contactor states | BCUs | 1 Hz | Faults, thermal trend, balance | P1 | Micah
3 | HV switching | DC-link V, precharge events, contactor commands and feedback | VMS VIO / LCC | 10 Hz; events | Faults (F37), cycle count (F53) | P1 | Mitchell
4 | Traction | Notch, reverser, TE request and estimate, chopper DC current, armature and field current per axle | LCC/TECU (Integral) | 10 Hz | Performance trend (J-14..J-17) | P1 | Integral
5 | Motion | Speed (radar / TM2-3), distance, GPS position and time | LCC, GPS | 1-10 Hz | kWh/mi, range, ramp tests | P1 | Jared
6 | Adhesion | Wheel-slip events, sanding | LCC | Events | Switcher acceleration (J-15) | P2 | Integral
7 | Air brake | Brake pipe, MR, BC pressures; handbrake state; penalty | CCB-2E / LCC | 1 Hz | Safety, tow (H-20) | P1 | Dragan
8 | Temperatures | Motor (if sensed), chopper heatsinks, ITV, coolant in/out per loop, ambient | LCC, PE cooling ctrl, BTMS | 1 Hz | Thermal trend (J-16, J-17) | P1 | VJ
9 | Aux power | 750 V, 72 V, 24 V bus V and I; inverter outputs; compressor and blower state | Aux converters | 1 Hz | Aux energy, standby draw | P1 | Mitchell
10 | BTMS | Mode, power, flow, coolant temperatures | BTMS (Maxwell) | 1 Hz | Thermal and energy | P2 | Jack
11 | Charging | Panto V, I, polarity; ITV in/out power; wayside meter | Panto ctrl, ITV, site | 10 Hz | Charging losses (DR-24) | P1 (from G7) | Micah
12 | Faults and overrides | Every VMS and LCC fault code with class, timestamps; overrides (who, why, test card) | VMS, LCC | Events | Fault triage at JAX; F46, F47 | P1 | Micah + Bailey
13 | Comms health | CAN error frames, bus load, node heartbeats | ETH-CAN gateway | 1 Hz | Comm-fault minimization (H-31) | P1 | Jared
14 | Configuration | SW/FW version manifest per node | All nodes | On boot | Config control (F51) | P1 | Jared
15 | Energy counters | kWh out, kWh in, Ah throughput | VMS | 1 Hz, cumulative | Range model (J-19) | P1 | Bill
16 | Operating context | Trailing cars and tons per move, crew notes | Operator tablet / form | Per move | Load cases, duty (DR-47/48) | P1 | Production lead
17 | Tow | 3-axis shock peaks, temperatures, GPS | Standalone logger | Events; 1 per 10 min | Tow (T-01) | P1 (tow only) | Matan
18 | TMS actuator status | PE and condenser fan speed/current, pump speed, MTM compressor status, heater status | PE cooling ctrl, BTMS | 1 Hz | Fan-loss detection (F59), J-20 | P1 | VJ
System requirements (H-32)
Start at first LV power at Huntington; never off during test or service.
Common time base (GPS or NTP) across VMS, LCC and BCUs; alignment < 100 ms.
Onboard store-and-forward >= 7 days; cloud sync via Starlink with LTE fallback (Matan).
Remote access read-only during motion and tow (F33).
P1 = needed from Huntington; P2 = needed by Jacksonville ramp tests.

## Gates
Gate | Site | Window (draft) | Purpose | Exit criteria (all must be true) | Key tests | Gate owner
G0 Bench | Cerritos | Now -> each LRU ships | Prove logic, sequencing and safety at reduced power | E-Stop timing defined and measured; precharge proven on cap bank; BMS fault reactions proven; LCC SIL passed; harness IR passed; RTV works | C-01..C-18 | Micah
G1 Receive & build | Huntington | Oct 12 -> early Nov | Everything installed and wired to print | Receiving clean; 100% continuity; wiring audit signed (Dragan a); SW/FW loaded with signed version manifest (Dragan c); LV power-up clean; full node census | H-01..H-04, H-30 | Production lead
G2 HV energize | Huntington | Early-mid Nov | Full voltage, no motion | System Megger passed before first HV (Dragan b); data logging live from first power; strings online one by one; isolation baseline; precharge at full V; aux chain runs; E-Stop at full V; brakes pass FRA tests | H-29, H-32, H-05..H-11 | Mitchell
G3 Huntington readiness + first movement (REQUIRED) | Huntington | Before tow | Dragan exit: system idles cleanly and moves both ways | Idle power-on with zero Class A faults and comm faults minimized; every Class B listed with override plan and JAX owner; creep per axle; first movement forward and reverse with stops; all overrides logged | H-31, H-12, H-13 | Dragan + Bill
G3+ Optional extended pre-check | Huntington | Before tow, if track time allows | Find drivetrain problems where Integral support is | 10 mph x 20 min; thermal soak; slip control; fault injection; early energy baseline | H-14..H-18, H-21 | Bill
G4 Dead-in-tow ready | Huntington | Before pickup (mid-Nov target) | Safe to haul in a CSX train | Dead-engine brakes work (CCB-2E, no compressor needed); electric handbrake manually operable; motors proven dead; MU isolated; running gear lubed; HV isolated and verified (grounding switch padlock optional); SOC in tow window; pantos locked or not fitted; 72 V lasts the trip; emergency sheet approved; CSX acceptance signed (229.9 movement) | H-19, H-20, H-22..H-28, H-33 | Dragan + Bill
G5 Tow | In CSX train | 3 days - 1.5 weeks | Arrive safely | No telemetry alerts; logger within limits | T-01 | Bill / Matan
G6 Recommission + Showcase 1 | Jacksonville | Arrival + ~1 week | Undo tow config; prove wheels turning | Inspection clean; logger read; IR >= 50% of H-29 baseline; power-up + E-Stop regression; Huntington Class B faults closed or re-classified; 10 mph x 20 min | J-01, J-02, J-02B | Production lead + Bill
G7 Charging infra | Jacksonville | Late Nov - mid Dec | Wire and charger ready, pantos fitted | Site acceptance signed; pantos meet dead wire; live wire sensing + polarity OK; HSCB close/trip and roof-bus interlock verified | J-03..J-05, J-23, J-24 | Oren + Micah
G8 Static charge | Jacksonville | Dec | Charge parked at rising power | Power ramp to cap with temperatures OK; handshake stop both ways; losses measured | J-06, J-07 | Micah + Integral
G9 Dynamic charge | Jacksonville | Dec - mid Jan | SHOWCASE 2 proven | Moving contact clean; segment A and B passed; E-Stop under load while moving | J-08..J-10 | Bill
G10 Operate | Jacksonville | ~Jan 20 -> Feb 20 | 30 days of CSX operation, performance trending, then showcase | No open safety faults; 3 clean rehearsals; ramp tests J-14..J-19 run and trended (non-gating) | J-11, J-12, J-14..J-21 | Production lead
P1 CSX 90-day evaluation (post-demo) | Jacksonville / CSX | Showcase -> +90 days | Converge to diesel-like performance | Notch 8 for 15 min; continuous pull at 10 mph; availability trend agreed with CSX; daily duty on one charge per shift-day; MCS integrated if retained | P-01..P-05, J-13 | Daphna + Bill

## Equipment & Access
Site | Category | Item | Why / which tests | Quantity / spec | Lead time / cost note | Owner | Have it? (Y/N)
Huntington | People | 5 electricians (from Oct 12) + 1 HV-qualified Voltify engineer on every energized shift | All H tests | 5 + 1 per shift | Confirmed in 10/6 stand-up | Production lead
Huntington | People | Integral field engineer for chopper/LCC first power and motor isolation proof | H-07, H-11..H-16, H-25, H-27 | 1, ~2 weeks | Book now | Jonathan
Huntington | People | CSX carman / mechanical inspector; FRA inspector | H-23 | Book date | Long lead; start now | Dragan / Daphna
Huntington | People | Qualified engineer + conductor for shop moves (pre-check, H-25 mule move) | H-12..H-14, H-25 | 1 + 1 | Via HRR/CSX | Dragan
Huntington | Track | Shop/yard track and track authority for creep and first movement fwd/rev (required); optional ~3.3 mi for 20-min pre-check | H-12, H-13 (required); H-14 (optional) | Optional | Confirm with HRR | Dragan
Huntington | Equipment | Shop mule or switcher to move the dead loco for the back-EMF test | H-25 | 1 |  | Dragan
Huntington | Equipment | Yard air or lead unit + single-car air brake test device; NYAB CCB2 dead-in-tow procedure | H-20, H-23 | 1 |  | Dragan
Huntington | Equipment | MU test box + dummy/isolation receptacle plugs | H-27 | 1 |  | Integral
Huntington | Consumables | TM suspension bearing oil, gear case lube, journal checks | H-26 | Per truck |  | Dragan
Huntington | Tow kit | Padlocks/hasps for grounding switch and HV doors (optional per Dragan); DEAD-IN-TOW tags; placards; printed emergency response sheet | H-24, H-28 | Set |  | Bill
Huntington | Tow kit | Battery-powered shock + temperature logger (GPS, cellular alert preferred); optional smoke sensor | H-24, T-01 | 1-2 | Order now | Matan
Huntington | Power | HV DC shop supply + 480 V 3-ph (only if packs arrive below tow SOC window or pre-check drains them) | H-18 | kW sets dwell | Optional now | Mitchell
Huntington | Power | 72 V battery charger; 650 Ah starter battery fully charged before tow | H-03, H-19 | 1 |  | Mitchell
Huntington | Test gear | Isolated 8-ch scope + 1,500 V probes; 5 kV insulation tester with shorting leads and discharge stick (H-29); 2,000 A DC clamps; CAT IV DMMs; CAN analyzers with DBC R2 + VPN; IR camera; thermocouple DAQ | H-02..H-25 | 1 set | Kit travels with loco (separately, not in the dead unit) | Production lead
Huntington | Mechanical | Calibrated torque wrenches + torque-seal paint; pack restraint hardware; coolant fill cart | H-24 | Set |  | Production lead
Huntington | Safety | HV PPE (Class 0 and 2 gloves, arc-flash kit, insulated tools), LOTO kits; Li-ion fire plan with local FD | All HV work | Per person | Before first HV | Production lead
Huntington | Access | CSX hazmat review of the battery-equipped dead unit; routing instructions (speed, position, no-hump) | H-23, H-28 |  | Start now | Daphna
Jacksonville | People | HV engineer + Integral support for recommission and ITV first power | J-01..J-07 | 1 + 1 |  | Micah / Jonathan
Jacksonville | Track | ~3.3 mi of usable track (or repeated passes) for Showcase 1 | J-02B |  | Now needed here | Daphna
Jacksonville | Infrastructure | AES wayside charger commissioned; energized contact wire; mast + insulators; microgrid commissioned | J-03..J-10 | Length under wire TBD | AES late Nov-mid Dec | Oren
Jacksonville | Test gear | Wayside revenue-grade energy meter; high-rate DAQ; contact-force gauge; man-lift with fall protection | J-04..J-09 | 1 each |  | Matan / Dave
Jacksonville | Access | Track time under wire at Moncrief; CSX coordination | J-08..J-12 |  |  | Daphna
Cerritos | Test gear | Capacitor bank (~23 mF) for precharge test; 2,000 A LV supply; HV load bank; compressor test stand | C-05, C-07, C-09, C-17 | existing / rental | $17.5k / $20k rental per test table | Mitchell
Huntington | People | Integral engineer for LCC/chopper software load and joint fault classification | H-30, H-31 | 1 | Book with chopper delivery | Jonathan
Huntington | Software | Release packages with version manifest: Voltify (VMS, VIO, BCU, panto, PE cooling) and Integral (LCC/TECU, choppers, IAC) | H-30 | 1 set | Freeze before Oct 12 build | Jared + Integral
Huntington | Procedure | Written Megger procedure: sections, test voltages, what to isolate/short, discharge | H-29 | 1 | Before G2 | Mitchell
Huntington | Data | Starlink online (or LTE fallback), cloud bucket, GPS time sync, logger config per Data Logging tab | H-32 | 1 | Needed at first LV power | Matan
Huntington | Access | CSX confirmation that first movement can run under 49 CFR 229.9(c) yard rules (<=10 mph) or other authority | H-13 | Written | Start now | Dragan / Daphna
Huntington | Procedure | Graham-White handbrake manual apply/release instructions | H-33 | 1 | Request from supplier | Dragan
Jacksonville | Track | Cuts of cars for load ramp: LC-1 (~10 cars), LC-2 (~25), LC-3 (~28 loaded, ~3,600 t) | J-15..J-17 | Per Load Cases tab | Coordinate with CSX Moncrief | Daphna
Jacksonville | Track | Track for sustained 10 mph: ~2.5 mi per 15 min, or loop / repeated passes | J-16, J-17 | TBD | Same as Showcase 1 need | Daphna
Jacksonville | Test gear | Thermocouple DAQ on motor frames, chopper heatsinks, coolant loops; optional drawbar load cell or dynamometer car for TE | J-15..J-17 | 1 set | TE can be estimated from motor current if no load cell | Integral / VJ

## Conflicts (RSK)
Proposed RSK | Level | Topic | Source A says | Source B says | Why it matters | Proposed owner / next step
RSK-NEW-13 | HIGH | Dead-in-tow requirements | Move plan: Huntington -> JAX dead-in-tow | GP40-V spec and HLR contain no dead-in-tow or transport requirement | Tow config, motor isolation, brakes, SOC undefined | Bill: adopt DIT set (G4). Dragan: unit acts as a railcar per CCB-2E dead-engine setup and 49 CFR 229.9 / 231 / 232
RSK-NEW-14 | HIGH | Traction-motor isolation with control off | Tow needs motors disconnected with LCC unpowered | GP40-V spec: TM cutouts computer-controlled; manual cutout switches removed from HVC | No verified way to isolate motors when dead (F38) | Integral + Mitchell: define and test (H-25)
RSK-NEW-01 | LOW | DC-link contactor owner: PROPOSED CLOSED (v1.3) | Architecture doc: VMS VIO #1 drives DC-link contactor and precharge | Deck FER slide: all FER switchgear controlled by LCC; start flow: 'LCC connects DC-link' | Two masters on one HV contactor (F02) | Jonathan 2026-10-12: Integral is the only master of the DC-link to TRB-bus contactors. Jonathan + Integral: write the ICD line; Micah: correct the architecture doc (VMS VIO #1)
RSK-NEW-03 | LOW | Charge rate: CLOSED FOR DEMO (v1.3) | HLR / demo plan: 3 MW dynamic target | Demo limit (DR-17): 2.1 MW at the wire (0.5C of the 4.2 MWh Jacksonville ground ESS) and no more than 1,666 A wire current (2 x 833 A DPS100) = 0.42C at the loco, inside the 0.5C cell rating | Over-rate charging (F06) | Closed for the demo. Post-demo (MCS 2.25 MW/port, future wayside): Bill/Micah still need the Jinko/BMS written charge limit
RSK-NEW-04 | HIGH | Dynamic charging without ITV | Showcase needs dynamic charging | HLR fallback (no ITV): dynamic N/A ¦ v1.3: Jonathan 2026-10-12: without the ITV the pantographs connect straight to the TRB-bus with no filtering; the Zekalabs 750V-PS (1.7 kV SiC) on the same port has little spike margin at 1.5 kV | ITV has no date (F12) | ITV date (Jonathan): Oct 19 target, end of October latest. Decision: no dynamic charging without the ITV (F69, RSK-NEW-52); static-only fallback
RSK-NEW-06 | MED | Insulation monitoring | Architecture: isolation check only at MCS inlet | No IMD on TRB-BUS in any source ¦ v1.3: Jonathan 2026-10-13: continuous ground-fault detection exists | Ground fault undetected (F15) | Jonathan + Micah: confirm the detector senses the TRB-bus (source), not only the DC-link; H-06
RSK-NEW-22 | HIGH | PE loop hot-ambient limit | KULI PE review: 40 C design point, charger supply 53.3 C (limit 55 C) | Sweep: charger supply passes 55 C at ~46-47 C ambient when charging; inverter 60 C at ~50 C under Notch 8 | Summer CSX operation in Jacksonville; charging and full power lost first (F54) ¦ v1.3: demo charging is now 2.1 MW (charger heat ~14 kW vs ~17-20 kW at 2.5-3 MW), so the charging crossover ambient should rise; quantify in C-27 | VJ + Integral: confirm design ambient and radiator margin
RSK-NEW-30 | HIGH | PE pump failure detection | Fault sweep: chopper fluid 110-135 C at onset of pump loss under load | Architecture doc: PE cooling controller senses temperature, pressure, level; no flow/pump-status trip defined | Choppers overheat before a temperature alarm reacts (F61) | VJ + Micah: define flow loss trip; test H-34
RSK-NEW-35 | HIGH | Radiator fan hardware | KULI PE and condenser reviews: EMP fans, ~7 kW per 3-fan bank (model baseline by decision 2026-10-08) | POC Power Budget: SPAL VA117 12 V fans only. Locomotive Kit BOM: BOTH per loop (EMP HV radiator + fan assembly 750 V, and LV truck radiator with 3 SPAL fans) | Model and KULI cover EMP only; POC budget omits the EMP 750 V fan load (~7 kW per loop); radiator capacity and aux power both uncertain | VJ: confirm radiator/fan architecture per loop; update KULI, POC budget and model
RSK-NEW-38 | HIGH | Chopper loss basis | Vince KULI PE reviews (Oct 5/9): 4.02 kW per chopper at 425 A, 32.8 kW full peak (~1.25% of output; Voltify design basis) | Integral sim (2026-10-15): 2.48 kW per chopper at 1170 A, 500 Hz (switching 1.58 kW, conduction 0.90 kW), ~0.78 kW at 425 A; no measured data (stall test only). Model Rev C uses it; deck basis was 5.25 kW at 1050 A. Per-chopper vs per-module basis not stated (2x). | PE loop sizing and hot-day verdicts: at the KULI basis the 45 C baseline chopper fluid reaches ~64 C vs 63 C (estimate) (F65) | Integral via Jonathan: HV motor-lab loss data (C-24); VJ: KULI full-peak case; Bill: update model loss curve ¦ v1.2: Jonathan/Bill: Integral to confirm table basis (per chopper or per module) and send loss at 425/1500 A; KULI basis (4.02 kW at 425 A) is ~5x the Integral sim -> PE loop sizing conservative. Propose MED once basis confirmed
RSK-NEW-39 | HIGH | Charger coolant limit and flow | AUX-B002-P-V0-R2 datasheet: maximum cold plate fluid 55 C (location unstated); minimum 30 L/min and 0.8 bar per loop | Integral (2026-10-15): 55 C is the maximum coolant INLET; 0.8 bar is nominal at 30 L/min (proportional to flow); ~6 C rise at 30 L/min (2 loops = ~21 kW at 3 MW, matches model 99.34%); onboard cold-plate derate. Model already checks supply (inlet) temperature. ¦ v1.3: At the 2.1 MW demo limit the charger rejects ~14 kW | Full-power charging on hot days (Showcase 2); verdict logic changes if the limit applies at the outlet (F66) | Integral: confirm limit location and pressure-drop meaning; VJ + Dave: rebalance charger branch; H-35 / J-22 ¦ v1.2: Margin is 1.5 K at 40 C (53.5 C inlet). Open: Integral losses vs charge power, ramp rate, current limits; IGBT temps junction or case. Location question closed
RSK-NEW-43 | HIGH | Roof bus live through ITV diodes | ITV AUX-B002 non-isolated buck/boost: battery energizes the roof side through freewheel diodes | No requirement that charger contactors open when pantos are down ¦ v1.3: Jonathan 2026-10-13: VMS folds the pantographs only after opening the panto contactor panel contactors (partial control) | Roof/pantograph conductors at battery voltage with pantos lowered (F68) | Micah: add VMS + hardware interlock; verify J-24 ¦ v1.3: Keep J-24: VMS sequence plus hardware interlock
RSK-NEW-15 | MED | Battery in a towed unit | Pack ships energized at some SOC | No defined tow SOC, hazmat classification or responder info | CSX acceptance and incident response (F26, F43) | Bill + Daphna: CSX hazmat review
RSK-NEW-07 | MED | E-Stop timing | Deck: T1, T2, T3 = TBD seconds | ITV contract: stop within T1 | Untestable until numbers exist (F01) | Micah + Jonathan + Integral
RSK-NEW-08 | MED | BTMS supplies | Architecture: 750->12 V BTMS LV PS 3.25 kW | Deck: 12 V PS 6 kW (NetPower) + 24 V PS 7 kW (inmotion) | Aux budget and wiring (F35) | Micah: update power budget (owner changed from Jack per Jonathan 2026-10-14; confirm this is the intended row)
RSK-NEW-10 | MED | Pantograph hatch vs tow | Gantt: hatch/bussing into December | Tow targeted mid-Nov | Tow without pantos fitted is simplest (F14, F42) | Dave + Dragan: decide
RSK-NEW-16 | MED | HSCB necessity: PROPOSED CLOSED, RETAIN (v1.1) | ITV (AUX-B002) is non-isolated buck/boost: battery back-feeds roof/charge-bus faults through freewheel diodes; ITV-bypass fallback and direct-to-TRB MCS also put the battery on the charge bus (analysis Oct 10; same risk as RSK-101) | Dragan (Oct 6): HSCB may not be needed for demo at all. Review pending | Contactors cannot break a battery-fed fault; string fuses are slow and split 6 ways; dynamic charging needs a resettable interrupter. Hardware on hand (Secheron), no cost or schedule hit | Jonathan Ronai (Integral POC). Close when: (a) Integral confirms ITV freewheel back-feed path; (b) Jinko pack/string short-circuit impedance; (c) Secheron trip curve clears within busbar/cable I2t. Dragan to review
RSK-NEW-17 | MED | Notch 8 margin | Dragan target: Notch 8 for 15 min (~3,000 hp); S6 model trace: 3,640 t on 0.5% at 30 mph | Model Rev C: 30 mph on that load needs 3.17 MW at the rail; 2.144 MW (4 x 536 kW) balances at 20.4 mph, 1.49 MW (500 hp/motor) at 14.2 mph. Motors then run ~1,060 A (D77: 1,050 A cont, 1,150 A 15 min). Earlier DERATED verdict was a report bug (fixed). | The target is power-limited, not model-limited; a 15-min Notch 8 lands at the D77 15-min current rating (F49) | Bill: confirm target wording (speed, load, grade) in GP40 manual; size the J-17 load so Notch 8 is power-limited at a stated speed
RSK-NEW-18 | MED | Duty load case | Dragan: 20-50 tons/day | One loaded car is ~130-143 t; GP40 continuous TE supports ~2,300-3,800 trailing tons at 10 mph on 1.0-0.5% grade | Test loads and range need per-move tons and cars/day | Decision Oct 7: protect for normal CSX yard ops via LC-3 (GP40-equivalent). Dragan + Daphna: sanity-check typical cut sizes with CSX ¦ v1.2: CSX4091 yard trace (Aug 26-27) adopted as duty profile; trailing tons per move still unknown (Rev B energy-fit tonnage placeholder). Dragan: CSX switch list / car counts for that shift ¦ v1.4: model wheel energy 1.11 x recorder rail with Rev B tonnage (RSK-NEW-56); switch list still needed
RSK-NEW-19 | MED | Range undefined | Dragan: determine range empirically | No logging spec in any source; Starlink incomplete | No data = no range estimate (F48) | Matan + Bill: freeze Data Logging tab; H-32 at first power ¦ v1.4 model estimate: CSX4091 yard day uses 15.6% SOC (813 kWh) -> ~5 days per charge in a 90-10% window, before cold/ageing derates; to be replaced by logged data
RSK-NEW-20 | MED | Electric handbrake in tow | GP40-V spec: Graham-White electric handbrake | Dead-in-tow: control power off or limited | Cannot release, or drags in tow (F45) | Dragan: manual procedure; test H-33
RSK-NEW-21 | MED | First-movement authority at Huntington | Dragan exit: first movement fwd/rev at Huntington | Unit is non-complying; 229.9(c) allows yard moves <=10 mph solely for repair; test-move fit unconfirmed | G3 could stall on authority, not hardware | Dragan / Daphna: CSX written confirmation
RSK-NEW-23 | MED | Ambient design window | Maxwell TMS: -10 to 45 C ambient | Sweep 0-50 C: condenser loop 69 C at 50 C (check valves 65 C); chiller capacity -20% | No agreed operating envelope (DR-52) | Bill: set envelope with CSX/Dragan
RSK-NEW-24 | MED | BMS cold thresholds | Jinko BMS: no charge or discharge below 3 C | Cell data (Micah thermal deck): discharge -30 to 60 C | Loco unusable after cold soak until preheated (F56) | Micah: set Voltify BMS thresholds
RSK-NEW-25 | MED | Heating capacity | Maxwell TMS study: 24 kW heating | POC Power Budget / architecture doc: 1 x Webasto HVH120, 12 kW (adopted as baseline 2026-10-08) | Cold-soak recovery 0->5 C ~4.0 h (vs ~1.9 h at 24 kW); preconditioning plan must allow for it | Bill + Micah: preconditioning procedure; decide whether 12 kW is enough for Jan-Feb
RSK-NEW-26 | MED | Heating setpoint | Jinko BMS: heat on 12 C, off 13.5 C | Model optimal band 15-35 C | Pack never reaches optimal band in cool weather (F57) | Micah: raise setpoints; re-run sweep
RSK-NEW-27 | MED | Thermal model placeholders | Model: battery-coolant UA 5 kW/K, linear MTM capacity map, D77 single-node thermal | No measured data yet | Verdicts at 40-50 C depend on them | VJ + Jack: obtain data; C-19 re-run
RSK-NEW-28 | MED | Aux load assumption | Phase 2 duty cycles: 30 kW base aux + 42 kW moving | Phase 3 load budget: ~0.6-5.2 kW by state + 44.7 kW blowers when moving | Range and standby energy estimates differ (F60) | Bill: measure in H-17/J-18; update load_budget.csv ¦ v1.4: CSX4091 yard day aux budget 209 + TMS 89 + converter 12 = 310 kWh (38% of battery energy); measurement in H-17/J-18 now has the biggest range leverage
RSK-NEW-29 | MED | PE fan health on hot days | Phase 3 fault run: PE fan loss at ~34 C ambient | No fan status signal to VMS in any interface doc found | Chopper/inverter overtemperature within minutes (F59) | VJ + Micah: add fan feedback and a derate rule
RSK-NEW-31 | MED | 45 C design point | Fault sweep baseline at 45 C: condenser loop 66.4 C (check valves 65 C) during heavy duty with charging | Maxwell design window up to 45 C | 45 C operation fails on check-valve rating alone (F55) | Jack + Maxwell: valve rating or relocation before setting DR-52
RSK-NEW-32 | MED | Axle cut-out tonnage | Fault sweep: LC-3 on 0.5% not held with 3 axles | No reduced-tonnage rule in the operating procedure | Stalls on grade after an axle cut-out (F62) | Dragan: 3-axle tonnage rule
RSK-NEW-33 | MED | Model starting resistance | Vehicle model: rolling resistance ~4 lb/ton, no breakaway term | Load Cases tab: starting resistance ~15 lb/ton; LC-3 start on 0.5% needs more than adhesion allows | Heavy-train starts are optimistic in the model | Bill: add breakaway resistance (C-22)
RSK-NEW-34 | MED | Traction blower rating | POC Power Budget / architecture doc: traction blowers 25 kW (12.75 kW nominal) | GP40-V spec: replace traction-motor blower with two 30 HP blowers (~44.7 kW) | Aux draw while moving differs by ~20-30 kW; motor cooling basis differs (F64) | Dragan + Micah: confirm blower hardware and rating
RSK-NEW-36 | MED | Battery cooling capacity | POC Power Budget open item: 4 MTMs x 12 kW = 48 kW | Margin at 45 C, and at 2.5-3 MW bounding charge cases (demo is 2.1 MW, DR-17) | Margin at 3 MW charge or 45 C (sweep: cells held at 28 C so far) | Jack + Maxwell: confirm module count/rating
RSK-NEW-40 | MED | Phase 3 model numerics at transitions | Phase 3 plant: solver min-step violations at every traction start/stop/brake (6-994 events per run; effective tolerance up to 2e4 x requested; global zero-crossing disabled) | Native plant in the same harness: no solver warnings; verdicts, temperatures and SOC agree (11/11) ¦ v1.2: CSX4091 25.5 h legacy-settings run: 32,471 solver warnings (min-step from t = 0.0015 s, throughout). Energy balance still closes within ~1% (SOC-derived 817 vs 812 kWh out on Rev C) | Phase 3 instantaneous currents near transitions are not reliable; summary metrics and verdicts are | Bill: review dclink/lcc switching laws and zero-crossing setting; use native plant for transient studies ¦ v1.2: Bill: model Rev D smooths brake/TE-sign/precharge discontinuities, tests zero-crossing on (C-26); use native plant (no warnings) as cross-check for transients
RSK-NEW-41 | MED | Main DC-link contactor close spike | Native model: ~2.3 kA for ~0.12 ms when the main contactor closes at 99% of bus voltage (~14 V across ~6 mOhm) | No main-contactor make rating or close criterion (% of bus vs absolute dV) documented; owner VMS VIO vs LCC open (RSK-NEW-01) | Contact wear or welding on every power-up (F02/F03) | Micah + Integral: confirm close criterion, contactor make rating and repeat-precharge cooldown
RSK-NEW-42 | MED | Charge taper and charge time | Model (Phase 3 and native): current tapers linearly in SOC from 93% to 95%; 92->93% in 79 s at 1884 A, 93->94.9% takes ~520 s | BMS likely tapers on cell voltage (CV phase); band and thresholds not documented | Charge-time budget for the showcase and daily duty (DR charge window) | Micah + Jinko: BMS taper basis and thresholds; update model
RSK-NEW-44 | MED | Polarity reverser removal | Architecture: reverser selects incoming pantograph polarity | AES-fed rigid overhead line has fixed, Voltify-controlled polarity | Removing the reverser (and part of VIO #4 scope) simplifies the HVR; only needed for third-party catenary | Daphna + Bill: roadmap decision on third-party catenary
RSK-NEW-45 | MED | ITV capacitor discharge into roof fault | ITV DC-link capacitance 13.8 mF at 1500 V (~15.5 kJ) | HSCB cannot interrupt capacitor discharge | Fault energy limited only by path impedance; busbar, cable and surge arrester ratings unverified | Micah: verify ratings and path inductance
RSK-NEW-46 | MED | MCS charge routing | Architecture doc: MCS path through HSCB stack and ITV | Oct 8 (Jonathan/Bill): MCS direct to TRB-BUS is the baseline | Changes HSCB scope and MCS protection design | Micah: update architecture doc
RSK-NEW-02 | LOW | String count / capacity | Architecture: 6 strings x 4 packs | Oct 6 decision (demo plan): 48 batteries, 6 strings at ~1,500 V; deck still implies 12 strings | Resolved; documents need updating | Micah: update deck text; retire 12-string references
RSK-NEW-11 | LOW | Battery capacity naming | Architecture: 5.016 MWh | HLR 4.2 MWh Phase 1 (retired by Oct 6 decision) | All energy math now uses 5.02 MWh | Micah: remove 4.2 MWh from deck and HLR
RSK-NEW-05 | LOW | Dynamic brake | GP40-V spec: new DB grids, regen on DB grids | HLR: not supporting dynamic/regen braking | No longer a transport issue; confirm for yard duty (F25) | Daphna: confirm with CSX
RSK-NEW-09 | LOW | Huntington charging entry | Packs may need shop charging | No defined entry point; MCS controller not developed | Only needed if SOC low (F36) | Mitchell: procedure if needed
RSK-NEW-12 | LOW | Load test | GP40-V spec: load testing and calibration before release, 2,000-3,000 HP | No DB grids / load box path in prototype | Release test undefined | Dragan: define prototype load test
RSK-NEW-37 | LOW | Converter labels and 24 V PS count | Architecture doc: converter table labels; 5 x 500 W 24 V PS | POC Power Budget: NetPower is 14 V 6 kW and DCC65M24 28.3 V 7.5 kW (labels swapped); 4 x RMD500 (2 kW) | Documentation error only | Micah: update architecture doc
RSK-NEW-47 | LOW | D77 flux/torque basis | Model to Rev B: Kphi = 9.0(1-exp(-I/600)), fitted to one FRA point | D77-D78 curve (Jonathan, 40 in / 62:15): Kphi 10-26% higher below 600 A; R ~0.030 Ohm from stall line | Torque per amp, current and loss at yard currents; top speed at the 750 V cap (~36 vs ~42 mph at 500 A) | Closed by model Rev C; Bill: confirm wheel diameter (42 in per Jonathan, 40 in GP40 standard)
RSK-NEW-48 | MED | D77 short-time ratings not enforced | D77 curve: 1,050 A continuous, 1,150 A 15 min, 1,500 A 5 min | Model and LCC proxy: 1,500 A limit with no time limit; no LCC derate rule documented | Notch 8 for 15 min runs ~1,060 A per motor; heavy LC-3 starts can exceed the 15-min rating (F49, F50) | Integral: LCC motor current/time derate; Bill: add I^2t check to model report
RSK-NEW-49 | MED | Traction power cap | Jonathan (2026-10-15): prototype uses 500 hp per motor (373 kW; 1.49 MW total) | Model and arch basis: 536 kW per motor (D77 FRA input rating; 2.144 MW); choppers 655 kW | Notch 8 balancing speed 14 vs 20 mph on LC-3; energy per pull; which cap the LCC enforces is undefined (MODEL_NOTES #6) | Jonathan + Integral: written LCC power limit; Bill: rerun J-17 load sizing at the chosen cap
RSK-NEW-50 | MED | Pack topology in the model | Oct 6 decision: 48 batteries, 6 strings at ~1,500 V | Phase 3 / Rev C model: 416S x 12 strings (~1,331 V nominal, 1,884 A) | Same energy, but bus voltage, current and I^2R losses differ by ~10-15%; BMS current limit basis | Bill: confirm string/series count with Micah; update proto_loco_params battery block (model Rev D)
RSK-NEW-51 | LOW | Regen opportunity (post-demo) | Prototype: no regen; all braking friction | CSX4091 Rev C decomposition (v1.4): 181.6 kWh/day into friction brakes (49% of wheel energy, ~55% of recorder rail energy) | ~150 kWh/day recoverable (~18% of battery output) if regen is added; brake wear; heat in yard | Daphna + Bill: post-demo roadmap item
RSK-NEW-52 | HIGH | Dynamic charging without the ITV | HLR fallback: pantographs to TRB-bus if the ITV is late | Jonathan 2026-10-12: no filtering; contact-wire transients reach the Zekalabs 750V-PS (1.7 kV SiC) on the same HVR port; little spike margin near 1.5 kV | Aux supply damage and loss of the 750 V bus during Showcase 2 (F69) | Decision proposed: no dynamic charging without the ITV; Micah: surge/filter review before any ITV-bypass static charging
RSK-NEW-53 | MED | Demo charge limit vs charge window | Showcase 2: up to 2 mi at 0.5 mph, segment A >= 10 min at the cap | Demo limit 2.1 MW at the wire / 1,666 A (ground ESS 0.5C); 20->95% SOC at 2.1 MW takes ~1.9 h (~1 mi) | Showcase script and SOC plan must fit the lower power; wire voltage below 1,260 V makes the 1,666 A limit bind first | Bill: update the Showcase 2 script; Matan/Oren: confirm wire voltage range and DPS100 settings (J-25)
RSK-NEW-54 | MED | Motor resistance / loss basis | Model: R_m 0.035 ohm per D77 (armature + field), copper loss only; no iron, brush or windage loss | No source document for R_m; D77-D78.pdf and Integral data not yet checked for hot resistance | Motor copper is the largest drivetrain loss: 110.5 kWh/day yard (13.6% of battery energy), motor 77% efficient while motoring; drives motor heating and range | Integral via Jonathan: D77 hot armature + series-field resistance and loss data; Bill: update P.ax.R_m and add core/brush loss if material (G-21)
RSK-NEW-55 | MED | Standstill power management | CSX4091 yard model: loco stationary 66% of the day; aux budget + TMS + converter = 310 kWh/day (38% of battery energy), 123 kWh while stopped | No requirement or state rule for shedding aux/TMS load at standstill (SLEEP/STANDBY entry, timers) | Hotel load is a bigger range lever than any drivetrain efficiency gain; also sets the charge-interval plan | Micah + Bill: define standstill load-shed rules in the state manager; measure in H-17/J-18; re-run decomposition
RSK-NEW-56 | LOW | Model vs recorder energy | Model Rev C wheel energy 1.09-1.11 x the CSX4091 recorder rail energy (yard 369.1 vs 331.1 kWh) | Rev B tonnage was energy-fit to the recorder; ratio should be ~1.0 | Range and charge-interval estimates ~10% conservative; friction share may be inflated by speed-loop hunting on 1 Hz recorder speed | Bill: check fit basis, Crr and speed tracking (G-22); Dragan: switch list / car counts (G-13)

## Thermal Sweep
MATLAB Phase 2 thermal sweep (proto_loco, 2026-10-08): 8 scenarios x 5 ambients x 2 start conditions — Phase 2 parameters (24 kW heater; pre-POC baseline)
OPTIMAL: cell 15-35 C, no derate, >=3 K margin on every PE/condenser limit. OK: inside BMS L1, no derate. DERATED: BMS derate or speed not held. FAIL: hard limit (BMS L2, charger 55 C, inverter 60 C, chopper 63 C, condenser 65 C, motor 180 C).
Placeholders drive the 40-50 C results (MODEL_NOTES Phase 2 table). Jinko as-shipped BMS thresholds. Python replica matches within ~0.2 K.
Preconditioned start (pack at 25 C)
Scenario | DVP | 0 C | 10 C | 20 C | 40 C | 50 C
S1_first_move | H-12/H-13 | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL
S2_showcase1 | J-02B | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL
S3_dyncharge_2p5MW | J-09 | OPTIMAL | OPTIMAL | OPTIMAL | OK | FAIL
S4_dyncharge_3p0MW | J-09 (3 MW) | OPTIMAL | OPTIMAL | OPTIMAL | OK | FAIL
S5_cont_pull_10mph | J-16/P-02 | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL | OK
S6_notch8_15min | J-17/P-01 | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL | FAIL
S7_switch_shift_8h | J-18 | OPTIMAL | OPTIMAL | OPTIMAL | OK | FAIL
S8_park_6h | G6 / J-21 | OPTIMAL | OPTIMAL | OPTIMAL | OPTIMAL | FAIL
Soaked start (pack at ambient)
Scenario | DVP | 0 C | 10 C | 20 C | 40 C | 50 C
S1_first_move | H-12/H-13 | FAIL | OK | OPTIMAL | OK | FAIL
S2_showcase1 | J-02B | FAIL | OK | OPTIMAL | OK | FAIL
S3_dyncharge_2p5MW | J-09 | FAIL | OK | OPTIMAL | OK | FAIL
S4_dyncharge_3p0MW | J-09 (3 MW) | FAIL | OK | OPTIMAL | OK | FAIL
S5_cont_pull_10mph | J-16/P-02 | FAIL | OK | OPTIMAL | OK | FAIL
S6_notch8_15min | J-17/P-01 | FAIL | OK | OPTIMAL | OK | FAIL
S7_switch_shift_8h | J-18 | FAIL | OK | OPTIMAL | OK | FAIL
S8_park_6h | G6 / J-21 | OK | OK | OPTIMAL | OK | FAIL
Findings
1. Preconditioned pack: cells stay 25-28 C in every case. The battery is not the thermal limiter.
2. PE loop limits first in heat: charger supply 57.6 C (2.5 MW) / 58.5 C (3 MW) at 50 C; 2.0 K margin at 40 C. Inverter fluid 60.4 C under Notch 8 at 50 C. Crossover ~46-50 C ambient (F54). ¦ v1.3: Demo charge limit is now 2.1 MW (DR-17); S3 (2.5 MW) and S4 (3 MW) are bounding cases above it
3. Condenser loop reaches 69.4 C at 50 C ambient (check valves 65 C): 50 C is outside the Maxwell design window (F55).
4. Soaked 0 C: every move/charge fails (Jinko BMS blocks below 3 C). Heaters take ~1.9 h to 5 C (F56).
5. Soaked 10 C: OK, not OPTIMAL. Heating stops at 13.5 C, below the 15-35 C band (F57).
6. Soaked 50 C: cell starts at BMS L2; ~1.2 h to 45 C, ~3.6 h to 35 C. Soaked starts cost 100-200 kWh TMS energy per hot day (F58).
7. TMS energy per 8 h shift (preconditioned): 18 kWh at 0-20 C, 65 kWh at 40 C, 90 kWh at 50 C.
Full results (MATLAB run_thermal_sweep output; last row truncated in the pasted table)
scenario | start | T_amb (C) | verdict | Tcell_min | Tcell_max | PE supply max | Charger supply max | Inverter out max | Condenser max | k_dis_min | k_chg_min | soc_end | E_tms (kWh) | limit
S1_first_move | soaked | 0 | FAIL | 0 | 0.15244 | 2.1628 |  | 4.2462 | 0 | 0 | 1 | 0.49808 | 2.8767 | cell <= BMS L2 cold
S1_first_move | soaked | 10 | OK | 10 | 10.152 | 12.304 |  | 14.42 | 10 | 1 | 1 | 0.49802 | 2.8767 | cell 10-10 C outside 15-35 C
S1_first_move | soaked | 20 | OPTIMAL | 20 | 20 | 21.828 |  | 23.432 | 20 | 1 | 1 | 0.49855 | 0.24337
S1_first_move | soaked | 40 | OK | 39.679 | 40 | 42.385 |  | 44.595 | 62.919 | 1 | 1 | 0.49793 | 3.3091 | cell 40-40 C outside 15-35 C
S1_first_move | soaked | 50 | FAIL | 49.735 | 50 | 52.408 |  | 54.63 | 69.39 | 0.00019569 | 1 | 0.49791 | 3.459 | cell >= BMS L2 hot; condenser loop > 65 C (check valve)
S2_showcase1 | soaked | 0 | FAIL | 0 | 0.95355 | 2.6872 |  | 4.8408 | 0 | 0 | 1 | 0.49204 | 10.882 | cell <= BMS L2 cold
S2_showcase1 | soaked | 10 | OK | 10 | 10.953 | 12.958 |  | 15.112 | 10 | 1 | 1 | 0.49112 | 10.882 | cell 10-11 C outside 15-35 C
S2_showcase1 | soaked | 20 | OPTIMAL | 20 | 20.002 | 22.403 |  | 24.03 | 20 | 1 | 1 | 0.49314 | 0.9156
S2_showcase1 | soaked | 40 | OK | 38.077 | 40 | 43.075 |  | 45.34 | 62.974 | 1 | 1 | 0.49073 | 12.846 | cell 38-40 C outside 15-35 C
S2_showcase1 | soaked | 50 | FAIL | 48.435 | 50 | 53.071 |  | 55.332 | 69.39 | 0.00017759 | 1 | 0.49075 | 12.96 | cell >= BMS L2 hot; condenser loop > 65 C (check valve)
S3_dyncharge_2p5MW | soaked | 0 | FAIL | 0 | 8.195 | 7.513 | 7.513 | 9.6665 | 0 | 0 | 0 | 0.49073 | 58.188 | cell <= BMS L2 cold
S3_dyncharge_2p5MW | soaked | 10 | OK | 10 | 16.923 | 17.513 | 17.513 | 19.666 | 10 | 1 | 1 | 0.94911 | 19.384 | cell 10-17 C outside 15-35 C
S3_dyncharge_2p5MW | soaked | 20 | OPTIMAL | 20 | 24.415 | 26.958 | 26.958 | 28.585 | 20 | 1 | 1 | 0.94911 | 4.8878
S3_dyncharge_2p5MW | soaked | 40 | OK | 31.676 | 40 | 47.648 | 47.648 | 49.93 | 62.974 | 1 | 1 | 0.94863 | 70.811 | cell 32-40 C outside 15-35 C
S3_dyncharge_2p5MW | soaked | 50 | FAIL | 42.949 | 50 | 57.626 | 57.626 | 59.887 | 69.39 | 0.00060109 | 0.0067515 | 0.88826 | 69.104 | cell >= BMS L2 hot; charger supply > 55 C; condenser loop > 65 C (check valve)
S4_dyncharge_3p0MW | soaked | 0 | FAIL | 0 | 9.4744 | 8.4354 | 8.4354 | 10.589 | 0 | 0 | 0 | 0.57109 | 58.188 | cell <= BMS L2 cold
S4_dyncharge_3p0MW | soaked | 10 | OK | 10 | 17.7 | 18.435 | 18.435 | 20.588 | 10 | 1 | 1 | 0.94921 | 16.584 | cell 10-18 C outside 15-35 C
S4_dyncharge_3p0MW | soaked | 20 | OPTIMAL | 20 | 25.29 | 27.88 | 27.88 | 29.507 | 20 | 1 | 1 | 0.94921 | 4.8878
S4_dyncharge_3p0MW | soaked | 40 | OK | 32.229 | 40 | 48.571 | 48.571 | 50.853 | 62.974 | 1 | 1 | 0.94878 | 70.64 | cell 32-40 C outside 15-35 C
S4_dyncharge_3p0MW | soaked | 50 | FAIL | 43.485 | 50 | 58.549 | 58.549 | 60.81 | 69.39 | 0.00061738 | 0.0067513 | 0.94866 | 69.104 | cell >= BMS L2 hot; charger supply > 55 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
S5_cont_pull_10mph | soaked | 0 | FAIL | 0 | 2.9732 | 2.6988 |  | 4.8523 | 0 | 0 | 1 | 0.87775 | 30.532 | cell <= BMS L2 cold
S5_cont_pull_10mph | soaked | 10 | OK | 10 | 13.796 | 18.231 |  | 20.384 | 10 | 1 | 1 | 0.61862 | 25.823 | cell 10-14 C outside 15-35 C
S5_cont_pull_10mph | soaked | 20 | OPTIMAL | 20 | 20.94 | 27.675 |  | 29.302 | 20 | 1 | 1 | 0.62374 | 2.5656
S5_cont_pull_10mph | soaked | 40 | OK | 34.731 | 40 | 48.366 |  | 50.648 | 62.974 | 1 | 1 | 0.61719 | 37.306 | cell 35-40 C outside 15-35 C
S5_cont_pull_10mph | soaked | 50 | FAIL | 45.557 | 50 | 58.529 |  | 60.79 | 69.39 | 0.00029842 | 1 | 0.68314 | 36.281 | cell >= BMS L2 hot; inverter fluid > 60 C; condenser loop > 65 C (check valve)
S6_notch8_15min | soaked | 0 | FAIL | 0 | 0.87763 | 2.6924 |  | 4.8459 | 0 | 0 | 1 | 0.89295 | 10.155 | cell <= BMS L2 cold
S6_notch8_15min | soaked | 10 | OK | 10 | 11.731 | 19.046 |  | 21.2 | 10 | 1 | 1 | 0.78326 | 10.155 | cell 10-12 C outside 15-35 C
S6_notch8_15min | soaked | 20 | OPTIMAL | 20 | 20.667 | 28.52 |  | 30.148 | 20 | 1 | 1 | 0.78545 | 0.85449
S6_notch8_15min | soaked | 40 | OK | 38.679 | 40 | 49.173 |  | 51.455 | 62.974 | 1 | 1 | 0.7835 | 12.381 | cell 39-40 C outside 15-35 C
S6_notch8_15min | soaked | 50 | FAIL | 48.576 | 50 | 58.479 |  | 60.74 | 69.39 | 0.00016979 | 1 | 0.87389 | 12.096 | cell >= BMS L2 hot; inverter fluid > 60 C; condenser loop > 65 C (check valve)
S7_switch_shift_8h | soaked | 0 | FAIL | 0 | 13.604 | 3.6973 |  | 5.8508 | 0 | 0 | 1 | 0.73183 | 147.41 | cell <= BMS L2 cold
S7_switch_shift_8h | soaked | 10 | OK | 10 | 13.659 | 13.697 |  | 15.85 | 10 | 1 | 1 | 0.74248 | 50.29 | cell 10-14 C outside 15-35 C
S7_switch_shift_8h | soaked | 20 | OPTIMAL | 20 | 20.069 | 23.142 |  | 24.769 | 20 | 1 | 1 | 0.74906 | 17.599
S7_switch_shift_8h | soaked | 40 | OK | 26.229 | 40 | 43.824 |  | 46.104 | 62.974 | 1 | 1 | 0.72692 | 128.13 | cell 26-40 C outside 15-35 C
S7_switch_shift_8h | soaked | 50 | FAIL | 26.34 | 50 | 53.81 |  | 56.071 | 69.39 | 0.096973 | 1 | 0.71229 | 201.11 | cell >= BMS L2 hot; condenser loop > 65 C (check valve)
S8_park_6h | soaked | 0 | OK | 0 | 13.605 | 1.2541 |  | 2.048 | 0 | 1 | 1 | 0.55893 | 143.74 | cell 0-14 C outside 15-35 C
S8_park_6h | soaked | 10 | OK | 10 | 13.66 | 11.254 |  | 12.048 | 10 | 1 | 1 | 0.57862 | 46.088 | cell 10-14 C outside 15-35 C
S8_park_6h | soaked | 20 | OPTIMAL | 20 | 20 | 20.699 |  | 20.966 | 20 | 1 | 1 | 0.58525 | 13.199
S8_park_6h | soaked | 40 | OK | 26.225 | 40 | 41.336 |  | 42.208 | 62.974 | 1 | 1 | 0.5683 | 97.314 | cell 26-40 C outside 15-35 C
S8_park_6h | soaked | 50 | FAIL | 26.338 | 50 | 51.367 |  | 52.269 | 69.39 | 1 | 1 | 0.55085 | 183.83 | cell >= BMS L2 hot; condenser loop > 65 C (check valve)
S1_first_move | precond | 0 | OPTIMAL | 24.903 | 25 | 1.8277 |  | 3.4319 | 0 | 1 | 1 | 0.49855 | 0.24337
S1_first_move | precond | 10 | OPTIMAL | 24.942 | 25 | 11.828 |  | 13.432 | 10 | 1 | 1 | 0.49855 | 0.24337
S1_first_move | precond | 20 | OPTIMAL | 24.981 | 25 | 21.828 |  | 23.432 | 20 | 1 | 1 | 0.49855 | 0.24337
S1_first_move | precond | 40 | OPTIMAL | 25 | 25.059 | 41.909 |  | 43.608 | 40 | 1 | 1 | 0.49847 | 0.68064
S1_first_move | precond | 50 | OPTIMAL | 25 | 25.098 | 51.953 |  | 53.692 | 50 | 1 | 1 | 0.49841 | 0.94031
S2_showcase1 | precond | 0 | OPTIMAL | 24.643 | 25 | 2.4029 |  | 4.0301 | 0 | 1 | 1 | 0.49314 | 0.9156
S2_showcase1 | precond | 10 | OPTIMAL | 24.786 | 25 | 12.403 |  | 14.03 | 10 | 1 | 1 | 0.49314 | 0.9156
S2_showcase1 | precond | 20 | OPTIMAL | 24.93 | 25 | 22.403 |  | 24.03 | 20 | 1 | 1 | 0.49314 | 0.9156
S2_showcase1 | precond | 40 | OPTIMAL | 25 | 25.217 | 42.518 |  | 44.256 | 40 | 1 | 1 | 0.49274 | 2.8722
S2_showcase1 | precond | 50 | OPTIMAL | 25 | 25.36 | 52.549 |  | 54.314 | 50 | 1 | 1 | 0.49261 | 3.5375
S3_dyncharge_2p5MW | precond | 0 | OPTIMAL | 24.967 | 27.657 | 6.9577 | 6.9577 | 8.5849 | 0 | 1 | 1 | 0.94911 | 4.8878
S3_dyncharge_2p5MW | precond | 10 | OPTIMAL | 24.981 | 28.02 | 17.356 | 17.307 | 19.441 | 36.303 | 1 | 1 | 0.94911 | 11.093
S3_dyncharge_2p5MW | precond | 20 | OPTIMAL | 24.994 | 28.029 | 27.485 | 27.484 | 29.612 | 46.978 | 1 | 1 | 0.94911 | 13.777
S3_dyncharge_2p5MW | precond | 40 | OK | 25 | 28.058 | 47.648 | 47.648 | 49.93 | 62.974 | 1 | 1 | 0.94903 | 34.053 | PE margin 2.0 K
S3_dyncharge_2p5MW | precond | 50 | FAIL | 25 | 28.099 | 57.626 | 57.626 | 59.887 | 69.39 | 1 | 1 | 0.949 | 40.826 | charger supply > 55 C; condenser loop > 65 C (check valve)
S4_dyncharge_3p0MW | precond | 0 | OPTIMAL | 24.968 | 28.042 | 8.3269 | 8.3257 | 10.38 | 25.776 | 1 | 1 | 0.94921 | 12.134
S4_dyncharge_3p0MW | precond | 10 | OPTIMAL | 24.981 | 28.055 | 18.364 | 18.364 | 20.449 | 36.303 | 1 | 1 | 0.94921 | 14.261
S4_dyncharge_3p0MW | precond | 20 | OPTIMAL | 24.994 | 28.07 | 28.408 | 28.408 | 30.535 | 46.978 | 1 | 1 | 0.94921 | 16.703
S4_dyncharge_3p0MW | precond | 40 | OK | 25 | 28.128 | 48.571 | 48.571 | 50.853 | 62.974 | 1 | 1 | 0.94914 | 36.949 | PE margin 2.0 K
S4_dyncharge_3p0MW | precond | 50 | FAIL | 25 | 28.238 | 58.549 | 58.549 | 60.81 | 69.39 | 1 | 1 | 0.94912 | 44.577 | charger supply > 55 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
S5_cont_pull_10mph | precond | 0 | OPTIMAL | 24.862 | 25 | 7.6752 |  | 9.3024 | 0 | 1 | 1 | 0.62389 | 2.5656
S5_cont_pull_10mph | precond | 10 | OPTIMAL | 24.981 | 25.286 | 17.675 |  | 19.302 | 10 | 1 | 1 | 0.6239 | 2.5656
S5_cont_pull_10mph | precond | 20 | OPTIMAL | 24.997 | 25.653 | 27.675 |  | 29.302 | 20 | 1 | 1 | 0.62391 | 2.5656
S5_cont_pull_10mph | precond | 40 | OPTIMAL | 25 | 26.433 | 47.821 |  | 49.586 | 40 | 1 | 1 | 0.62244 | 9.8453
S5_cont_pull_10mph | precond | 50 | OK | 25 | 26.824 | 57.821 |  | 59.586 | 50 | 1 | 1 | 0.62243 | 9.9125 | PE margin 0.4 K
S6_notch8_15min | precond | 0 | OPTIMAL | 24.962 | 25.333 | 8.5204 |  | 10.148 | 0 | 1 | 1 | 0.78556 | 0.85449
S6_notch8_15min | precond | 10 | OPTIMAL | 24.983 | 25.438 | 18.52 |  | 20.148 | 10 | 1 | 1 | 0.78557 | 0.85449
S6_notch8_15min | precond | 20 | OPTIMAL | 24.997 | 25.543 | 28.52 |  | 30.148 | 20 | 1 | 1 | 0.78557 | 0.85449
S6_notch8_15min | precond | 40 | OPTIMAL | 25 | 25.794 | 48.657 |  | 50.422 | 40 | 1 | 1 | 0.78509 | 3.2307
S6_notch8_15min | precond | 50 | FAIL | 25 | 25.927 | 58.659 |  | 60.424 | 50 | 1 | 1 | 0.78508 | 3.3014 | inverter fluid > 60 C
S7_switch_shift_8h | precond | 0 | OPTIMAL | 19.048 | 25 | 3.1419 |  | 4.7691 | 0 | 1 | 1 | 0.74906 | 17.599
S7_switch_shift_8h | precond | 10 | OPTIMAL | 21.454 | 25 | 13.142 |  | 14.769 | 10 | 1 | 1 | 0.74906 | 17.599
S7_switch_shift_8h | precond | 20 | OPTIMAL | 23.859 | 25 | 23.142 |  | 24.769 | 20 | 1 | 1 | 0.74907 | 17.599
S7_switch_shift_8h | precond | 40 | OK | 25 | 28.002 | 43.73 |  | 46.008 | 62.974 | 1 | 1 | 0.73961 | 64.838 | PE margin 2.0 K
S7_switch_shift_8h | precond | 50 | FAIL | 25 | 28.005 | 53.809 |  | 56.07 | 69.39 | 1 | 1 | 0.73456 | 90.032 | condenser loop > 65 C (check valve)
S8_park_6h | precond | 0 | OPTIMAL | 20.334 | 25 | 0.6988 |  | 0.96635 | 0 | 1 | 1 | 0.58525 | 13.199
S8_park_6h | precond | 10 | OPTIMAL | 22.201 | 25 | 10.699 |  | 10.966 | 10 | 1 | 1 | 0.58525 | 13.199
S8_park_6h | precond | 20 | OPTIMAL | 24.067 | 25 | 20.699 |  | 20.966 | 20 | 1 | 1 | 0.58525 | 13.199
S8_park_6h | precond | 40 | OPTIMAL | 25 | 27.8 | 40.78 |  | 41.124 | 40 | 1 | 1 | 0.58104 | 34.124
S8_park_6h | precond | 50 | FAIL | [10 empty] | condenser loop > 65 C (check valve)
Note on F9: PE margin 2.0 K
Note on G9: charger supply > 55 C; condenser loop > 65 C (check valve)
Note on F10: PE margin 2.0 K
Note on G10: charger supply > 55 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
Note on G11: PE margin 0.4 K
Note on G12: inverter fluid > 60 C
Note on F13: PE margin 2.0 K
Note on G13: condenser loop > 65 C (check valve)
Note on G14: condenser loop > 65 C (check valve)
Note on C19: cell <= BMS L2 cold
Note on D19: cell 10-10 C outside 15-35 C
Note on F19: cell 40-40 C outside 15-35 C
Note on G19: cell >= BMS L2 hot; condenser loop > 65 C (check valve)
Note on C20: cell <= BMS L2 cold
Note on D20: cell 10-11 C outside 15-35 C
Note on F20: cell 38-40 C outside 15-35 C
Note on G20: cell >= BMS L2 hot; condenser loop > 65 C (check valve)
Note on C21: cell <= BMS L2 cold
Note on D21: cell 10-17 C outside 15-35 C
Note on F21: cell 32-40 C outside 15-35 C
Note on G21: cell >= BMS L2 hot; charger supply > 55 C; condenser loop > 65 C (check valve)
Note on C22: cell <= BMS L2 cold
Note on D22: cell 10-18 C outside 15-35 C
Note on F22: cell 32-40 C outside 15-35 C
Note on G22: cell >= BMS L2 hot; charger supply > 55 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
Note on C23: cell <= BMS L2 cold
Note on D23: cell 10-14 C outside 15-35 C
Note on F23: cell 35-40 C outside 15-35 C
Note on G23: cell >= BMS L2 hot; inverter fluid > 60 C; condenser loop > 65 C (check valve)
Note on C24: cell <= BMS L2 cold
Note on D24: cell 10-12 C outside 15-35 C
Note on F24: cell 39-40 C outside 15-35 C
Note on G24: cell >= BMS L2 hot; inverter fluid > 60 C; condenser loop > 65 C (check valve)
Note on C25: cell <= BMS L2 cold
Note on D25: cell 10-14 C outside 15-35 C
Note on F25: cell 26-40 C outside 15-35 C
Note on G25: cell >= BMS L2 hot; condenser loop > 65 C (check valve)
Note on C26: cell 0-14 C outside 15-35 C
Note on D26: cell 10-14 C outside 15-35 C
Note on F26: cell 26-40 C outside 15-35 C
Note on G26: cell >= BMS L2 hot; condenser loop > 65 C (check valve)

## System Model
Phase 3 system model (loco_system/voltify_loco_system.slx, 2026-10-08)
Subsystem | Contents | Edit via
Scenario | Duty trace: speed, grade, ambient, trailing tons, wire power, state request | traces/*.csv
Fault Injection | 14 fault channels, piecewise constant in time | faults/*.csv
Controls | Stateflow State Manager (SLEEP/STANDBY/READY/TRACTION/CHARGING/FAULT/ESTOP); Command Arbiter; Power Budget | Chart; load_budget.csv
Plant | Simscape locosys.locomotive_sys: battery 12 strings, DC link, 4 axles (chopper + D77), train, aux chain, ITV, thermal network | +locosys/*.ssc; proto_loco_params.m
Dashboard | Scopes; logs Y, SYS, LOADS, BUSES; report: verdict, time in state, energy by load/bus | report_loco_run.m
Auxiliary load budget by operating state (kW at the load; TMS and traction excluded) — baseline: Micah POC Power Budget Rev B
load_id | micah_id | name | bus | SLEEP | STANDBY | READY | TRACTION | CHARGING | FAULT | ESTOP | moving_kW | peak_kW | source
L01 | C24-01..07 | HVC VMS and comms (Premio; HMI; UPS; Starlink; router; gateway; RFID) | 24V_Ctrl | 0.05 | 0.155 | 0.155 | 0.155 | 0.155 | 0.155 | 0 | 0 | 0.29 | POC Power Budget Rev B; SLEEP = UPS hold (arch doc)
L02 | C24-08..09 | VMS VIO logic + DC-link and deep-sleep contactor coils | 24V_Ctrl | 0 | 0.022 | 0.022 | 0.022 | 0.022 | 0.022 | 0 | 0 | 0.105 | POC Power Budget Rev B
L03 | C24-11..14 | TRB electronics (12 BCUs; 96 BMMs; 24 string contactor coils; 2 ETH switches) | 24V_Ctrl | 0 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0 | 0 | 0.359 | POC Power Budget Rev B (no ESMU on prototype)
L04 | C24-15/16/19/20 | HVR controllers (panto ctrl; 3 VIOs; reverser ctrl; RTV) | 24V_Ctrl | 0 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0 | 0 | 0.051 | POC Power Budget Rev B
L05 | C24-18 | HSCB A/B holding (retained, v1.1) | 24V_Ctrl | 0 | 0 | 0.06 | 0.06 | 0.06 | 0 | 0 | 0 | 0.1 | POC Power Budget Rev B; held only when closed
L06 | C24-17 | Charging main contactor coils (panto-CP x1; charger-CP x2) | 24V_Ctrl | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0.15 | POC Power Budget Rev B; held only while charging
L07 | C24-21..25 | Converter and inverter control supplies | 24V_Ctrl | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.124 | POC Power Budget Rev B
L08 | C24-26 | MCS controller logic x2 (MCS out of demo scope) | 24V_Ctrl | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0 | 0.01 | POC Power Budget Rev B
L09 | C24-29 | E-Stop translators and misc relays | 24V_Ctrl | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0 | 0 | 0.01 | POC Power Budget Rev B
L10 | V72-02 | Locomotive control (cab computer; MCO position) | 72V | 0 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0 | 0 | 0.08 | POC Power Budget Rev B
L11 | V72-03 | Cab lights and displays | 72V | 0 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0 | 0 | 0.2 | POC Power Budget Rev B
L12 | V72-04 | Cab HVAC (nominal = 50% cycling) | 72V | 0 | 0 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 1.5 | POC Power Budget Rev B; crew present in READY/TRACTION/CHARGING (state mapping = assumption)
L13 | V72-05 | Exterior lighting (headlights; ditch; class) | 72V | 0 | 0 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0.8 | POC Power Budget Rev B (assumption in source)
L14 | V72-06 | Wake circuit (always on) | 72V | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0 | 0.005 | POC Power Budget Rev B
L15 | V72-07 | E-Stop 72 V loop | 72V | 0 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0 | 0 | 0.002 | POC Power Budget Rev B
L16 | V72-08 | Polarity reverser coil (latching: 0 W held) | 72V | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | POC Power Budget Rev B
L17 | B24-03 | Pantograph 24 V kits x4 (folded sense; raised hold when charging) | 24V_BTMS | 0 | 0.015 | 0.015 | 0.015 | 0.1 | 0.015 | 0 | 0 | 1 | POC Power Budget Rev B (folded 15 W from arch doc)
L18 | B12-03/06/07 | MTM ECUs x4; Thermiantor3; heater LV logic | 12V_BTMS | 0 | 0.047 | 0.047 | 0.047 | 0.047 | 0.047 | 0 | 0 | 0.25 | POC Power Budget Rev B
L19 | H75-04 | Brake compressor via ACH inverter (nominal = 30% cycling) | 750V | 0 | 0 | 1.53 | 1.53 | 1.53 | 0 | 0 | 0 | 5.1 | POC Power Budget Rev B
L20 | H75-05 | Traction blowers via ACH inverter (nominal = 50%; on when moving) | 750V | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.75 | 25.5 | POC Power Budget Rev B (arch doc 25 kW; GP40-V spec says 2 x 30 HP: RSK-NEW-34)
L21 | B12-01/02 | SPAL 12 V radiator fans x6 (LV radiators; PE x3 + condenser x3; nominal 60% speed) | 12V_BTMS | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 2.52 | POC Power Budget Rev B; LV radiators not in the plant thermal model (RSK-NEW-35)
Total (at the load)
Blue cells mirror loco_system/load_budget.csv (edit the CSV for the model). At the 750 V bus (after converter efficiencies): ~0.8 kW STANDBY, ~3.6 kW READY/TRACTION, ~3.7 kW CHARGING, +12.75 kW blowers when moving. TMS (MTM compressors, HVH120 heater, SPAL pumps, fans) is computed in the plant thermal model. Phase 2 assumed 30 kW base + 42 kW moving.
Fault library (loco_system/faults/fault_library.csv)
fault_id | fmea | description | channel | active_value | plant effect
MTM_LOSS_1 | F55 | One Maxwell chiller module lost (3 of 4) | n_mtm | 3 | Chiller capacity x n/4
MTM_LOSS_2 | F55 | Two Maxwell chiller modules lost (2 of 4) | n_mtm | 2 | Chiller capacity x n/4
PE_FAN_FAIL | F54 | PE radiator fans failed (ram/natural air only) | fan_pe | 0 | PE radiator UA to 20%
COND_FAN_FAIL | F55 | Condenser radiator fans failed | fan_cd | 0 | Condenser radiator UA to 20%
PE_PUMP_FAIL | F54 | PE loop pumps failed (5% residual flow) | pump_pe | 0.05 | PE flow 5%: outlet temps rise; UA falls
PE_PUMP_1OF3 | F54 | One of three PE SPAL pumps failed; two at 4750 rpm keep 95.4% flow (KULI 2026-10-09 App B) | pump_pe | 0.954 | PE flow 95.4%: outlet temps +0.3-0.4 K
BAT_PUMP_FAIL | TBD | Battery coolant pump failed | pump_bat | 0 | Cell-coolant UA to 20%
AXLE4_CUTOUT | F50 | Axle 4 chopper/motor cut out (3 of 4 axles) | n_ax_on | 3 | Adhesion and traction power x 3/4
STRING_OPEN_1 | TBD | One battery string isolated (11 of 12) | n_str | 11 | Capacity, resistance, BMS limits scale with strings
RACK_OPEN | TBD | One rack isolated (10 of 12 strings) | n_str | 10 | Capacity, resistance, BMS limits scale with strings
TSENSE_HIGH_5K | F46 | BMS cell temperature reads 5 K high | dT_sense_K | 5 | BMS reads cell temperature offset
TSENSE_LOW_5K | F46 | BMS cell temperature reads 5 K low | dT_sense_K | -5 | BMS reads cell temperature offset
BLOWER_FAIL | F50 | Traction motor blowers failed | blower_ok | 0 | Motor cooling UA to 15%
LCC_VMS_COMMS | F46 | LCC-VMS comms loss (Class A: no traction) | comms_ok | 0 | FAULT state: no traction/charging
AUX_DCDC_TRIP | TBD | 1500-750 V aux converter trip (aux loads and TMS lost) | aux_ok | 0 | Aux loads and TMS lost
CHARGER_DERATE_50 | TBD | Onboard charger derated to 50% | chg_derate | 0.5 | Charge power x value
ESTOP | TBD | E-Stop pressed | estop | 1 | ESTOP: HV and TMS off
CLASS_A_GENERIC | F46 | Any other Class A fault (traction and charging blocked) | classA | 1 | FAULT state: no traction/charging
BTMS_24V_PS_TRIP | F61 | BTMS 24 V supply (DCC65M24) trip: all SPAL pumps stop (PE loop) | pump_pe | 0.05 | PE flow 5%: outlet temps rise; UA falls
BTMS_24V_PS_TRIP | F61 | BTMS 24 V supply (DCC65M24) trip: all SPAL pumps stop (battery loop) | pump_bat | 0 | Cell-coolant UA to 20%
BTMS_12V_PS_TRIP | F55 | BTMS 12 V supply (NetPower) trip: MTM ECUs and internal pumps off (chillers lost; LV fans not modeled) | n_mtm | 0 | Chiller capacity x n/4
Team demo (2026-10-08): example_yard_day_8h.csv (Jacksonville summer, 24-34 C, 0-3,640 t, 45 min charge)
Run | Verdict | Limit
Baseline (no faults) | Pass (confirmed) | —
Hot day + faults (MTM loss 3-8 h; PE fans off 4-5 h; axle 4 cut out 6-8 h) | FAIL | Chopper fluid > 63 C and inverter fluid > 60 C during the PE fan outage (F59)
Native Simscape plant (native/loco_native.slx, 2026-10-10)
Plant is a Variant Subsystem: PLANT_ID = 1 Phase 3 plant (locosys .ssc), PLANT_ID = 2 native plant (library native/lib/loco_native_lib.slx: TRB String x6, DC-Link, Axle x4 = Chopper + FW + D77 + gear + wheel, Vehicle, LCC, AUX, Charger + FW, Thermal Plant, TMS Controller).
Run: RUN = run_loco_native(trace, 'Plant', 'native' ¦ 'phase3', <run_loco_system options>); regression: run_regression_native. Native runs at 0.45-0.95x real time (fixed-step local solvers, 1 ms).
Regression vs Phase 3 (C-23): 11/11 pass across S1-S8 at 25/40 C; max differences Tcell 0.001 K, Tsup 0.0013 K, SOC 0.0001, speed rms 0.016 mph. Open items list: native/OPEN_ITEMS.md.
Model Rev C drivetrain update (2026-10-16; loco_system_params.m options, defaults on the poc baseline; phase2 frozen)
Item | Before (Rev B) | Rev C | Source | Option
Wheel diameter | 40 in | 42 in (to confirm) | Jonathan 2026-10-15 | wheel_in
D77 flux Kphi(I) | 9.0(1-exp(-I/600)); 10-26% low below 600 A | Table, Kphi = 9.488 I/(299+I); within 1% at 300-1100 A | reference/D77-D78.pdf (40 in, 62:15) | motor_flux = d77_chart ¦ legacy
D77 current ratings | I_max 1500 A only | 1050 A cont / 1150 A 15 min / 1500 A 5 min recorded (not enforced) | D77-D78.pdf | P.ax.I_cont, I_15min, I_5min
Chopper loss | 5.25 kW at 1050 A (deck) | 2.47 kW at 1170 A, 500 Hz (switching 1.58 + conduction 0.90 kW) | Integral sim, J. Jankowski 2026-10-15 | chop_loss = integral_sim ¦ deck; chop_loss_scale
Motor power cap | 536 kW/motor (2.144 MW) | 536 kW default; 373 kW (500 hp) option | FRA rating / Jonathan | motor_cap_kW
Control latency | - | ~22 ms worst case; not modeled (1 s control step) | Integral | P.sys.ctrl_latency_s
Charger (AUX-B002) | 99.34%, 3.6 kW/K | Unchanged; 55 C inlet limit confirmed; ~21 kW at 3 MW; ~14 kW at the 2.1 MW demo limit | Integral | P.sys.chg_inlet_max_C
Report verdict | Speed check forced on | Follows scenario definition (S6 off) | report_loco_run.m | -
Solver output | Every warning printed | One-line summary; text in RUN.sim_log | run_loco_system.m | ShowWarnings
CSX4091 yard trace (Aug 26-27, 25.5 h, 27 C, regen off, Rev B tonnage)
Metric | Legacy settings | Rev C | Change
Battery out (kWh) | 841 | 812 | -29 (-3.4%)
Drivetrain energy = out - TMS - aux (kWh) | 536 | 514 | -22 (-4.1%)
TMS energy (kWh) | 96 | 89 | -7
Aux budget (kWh) | 209 | 209 | 0
SOC end (start 90%) | 73.9% | 74.4% | +0.5 pt
Peak cell (C) | 28 | 27.2 | chiller-on threshold 28 C
Peak condenser (C) | 58.5 | 36.1 | chiller ran on legacy only
Peak motor (C) | 44.2 | 44.6 | ~same
Verdict | OPTIMAL | OPTIMAL | -
Diesel recorder rail energy (kWh) | 331 | 331 | Model wheel (motoring) 369.1 kWh = 1.11 x recorder; battery-to-wheel 45.4% day / 59.5% motoring (C-26, v1.4; was ~64%, which was drivetrain/battery out)
Friction brake energy (kWh) | - | 181.6 | no regen (RSK-NEW-51); 49% of wheel energy (v1.4 decomposition)
Solver warnings | 32,471 | not counted (pre-summary run) | RSK-NEW-40
Notch 8 balancing speed, LC-3 3,640 t on 0.5% (check_notch8_balance.m)
Traction cap | Total power (MW) | Balancing speed (mph) | Power for 30 mph (MW)
536 kW/motor (D77 FRA) | 2.144 | 20.4 | 3.17
373 kW/motor (500 hp) | 1.492 | 14.2 | 3.17
Phase 2 regression (2026-10-16): 73/80; all 7 misses are S6 verdict labels (speed check), physics deltas < 0.003 K and < 1e-5 SOC; report fixed.
v1.3: demo charge limit 2.1 MW / 1,666 A (DR-17) is in loco_system_params.m (P.sys.demo_chg_P_max_W, demo_chg_I_wire_max_A); traces/S9_dyncharge_2p1MW_demo.csv; report flags any charge request above it. S3/S4 kept as bounding cases.
CSX4091 energy decomposition (decompose_csx4091.m, results_csx4091_20261016_0823.mat, Rev C, regen off) — v1.4
Item | peak2h (2.0 h) | yard (25.5 h) | Note
Battery chemical out (kWh) | 159.4 | 813 | terminal + I2R; no charging in trace
Battery I2R (kWh) | 0.2 | 0.5
Aux loads, budget (kWh) | 23.1 | 209 | Micah POC Power Budget (load_budget.csv)
TMS (kWh) | 6.9 | 88.7
Aux converter loss (kWh) | 1.3 | 12.4 | eta 0.96
DC-link / precharge (kWh) | 0 | 0
Chopper loss (kWh) | 2.7 | 11.4 | Integral sim basis (confirmed from signals; deck basis would be 5.9 / 22.7)
Motor copper loss (kWh) | 36.8 | 110.5 | R_m 0.035 ohm, source unverified (RSK-NEW-54); no iron/brush loss
Gear loss (kWh) | 2.6 | 11.4 | eta_g 0.97
Closure residual (kWh) | 0 | 0 | L and C storage
Wheel energy (kWh) | 85.7 | 369.1 | all motoring; regen off
of which rolling (kWh) | 49.8 | 194.4 | Crr 0.002
of which friction brake (kWh) | 38.7 | 181.6 | RSK-NEW-51
of which grade (kWh) | -3.9 | -8
of which aero / kinetic (kWh) | 1.1 | 1.1
Recorder rail energy (kWh) | 78.4 | 331.1 | diesel SD event recorder
Model wheel / recorder rail | 1.09 | 1.11 | RSK-NEW-56
Battery kWh per recorder rail kWh | 2.03 | 2.46
Motoring time (h / %) | 0.65 / 32% | 5.42 / 21%
Standstill time (h / %) | 0.89 / 44% | 16.74 / 66% | RSK-NEW-55
Battery energy at standstill (kWh) | 7.5 | 122.8 | all aux bus
Efficiency while motoring: chopper / motor / gear | 97.9 / 70.5 / 97.0 % | 97.7 / 77.4 / 97.0 % | motor low at yard speeds: high current, low back-EMF
Battery-to-wheel: motoring / whole day | 60.3 / 53.8 % | 59.5 / 45.4 %

## Fault Sweep
Phase 3 fault sweep on the POC Power Budget baseline with the PE loop update (run_fault_sweep, 2026-10-10): 20 faults + baseline x 20/40/45 C, traces/fault_test_3h.csv, fault onset 0.5 h, pack preconditioned 25 C
Left: verdict. Right: effect relative to the no-fault baseline at the same ambient (WORSE = new limit, lower verdict or first limit >0.25 h earlier; WATCH = large rise without a limit; MASKED = passes only because cooling ran less; TRADE-OFF = passes at a functional cost; BY-DESIGN = designed stop).
Fault | FMEA | 20 C | 40 C | 45 C |  | 20 C vs base | 40 C vs base | 45 C vs base | First limit (hours after onset) | Key delta vs baseline
PE_PUMP_FAIL | F54 | FAIL | FAIL | FAIL |  | WORSE | WORSE | WORSE | 20 C: chopper fluid > limit @ 0.00 h; 40 C: chopper fluid > limit @ 0.00 h; 45 C: chopper fluid > limit @ 0.00 h | 40 C: chopper +97.5 K, inverter +3.1 K
BTMS_24V_PS_TRIP | F61 | FAIL | FAIL | FAIL |  | WORSE | WORSE | WORSE | 20 C: chopper fluid > limit @ 0.00 h; 40 C: chopper fluid > limit @ 0.00 h; 45 C: chopper fluid > limit @ 0.00 h | 40 C: chopper +97.6 K, inverter +3.1 K
PE_FAN_FAIL | F54 | OPTIMAL | FAIL | FAIL |  | WATCH | WORSE | WORSE | 40 C: chopper fluid > limit @ 0.23 h; 45 C: chopper fluid > limit @ 0.16 h | 40 C: chopper +24.7 K, inverter +24.6 K
TSENSE_HIGH_5K | F46 | OPTIMAL | OK | FAIL |  | SAME | WORSE | WORSE | 45 C: condenser loop > limit @ 0.06 h | 40 C: inverter +1.0 K, cell -2.5 K
AXLE4_CUTOUT | F50 | DERATED | DERATED | DERATED |  | WORSE | WORSE | WORSE | 20 C: speed deficit > 1 mph @ 0.13 h; 40 C: speed deficit > 1 mph @ 0.13 h; 45 C: speed deficit > 1 mph @ 0.13 h | 40 C: motor +19.8 K, SOC end +3 pts
BLOWER_FAIL | F50 | OPTIMAL | OPTIMAL | FAIL |  | WATCH | WATCH | WATCH | 45 C: condenser loop > limit @ 2.08 h | 40 C: motor +49.3 K
AUX_DCDC_TRIP | TBD | OPTIMAL | OPTIMAL | OPTIMAL |  | WATCH | WATCH | WATCH |  | 40 C: motor +49.3 K
COND_FAN_FAIL | F55 | OPTIMAL | OPTIMAL | FAIL |  | SAME | SAME | SAME | 45 C: condenser loop > limit @ 2.05 h | 40 C: no change
MTM_LOSS_1 | F55 | OPTIMAL | OPTIMAL | OPTIMAL |  | SAME | SAME | MASKED |  | 40 C: no change
MTM_LOSS_2 | F55 | OPTIMAL | OPTIMAL | OPTIMAL |  | SAME | SAME | MASKED |  | 40 C: no change
BTMS_12V_PS_TRIP | F55 | OPTIMAL | OPTIMAL | OPTIMAL |  | SAME | SAME | MASKED |  | 40 C: no change
TSENSE_LOW_5K | F46 | OPTIMAL | OPTIMAL | OPTIMAL |  | SAME | SAME | MASKED |  | 40 C: no change
BAT_PUMP_FAIL | TBD | OPTIMAL | OPTIMAL | FAIL |  | SAME | SAME | SAME | 45 C: condenser loop > limit @ 2.06 h | 40 C: no change
PE_PUMP_1OF3 | F54 | OPTIMAL | OPTIMAL | FAIL |  | SAME | SAME | SAME | 45 C: condenser loop > limit @ 2.08 h | 40 C: chopper +0.4 K, inverter +0.2 K
STRING_OPEN_1 | TBD | OPTIMAL | OPTIMAL | FAIL |  | SAME | SAME | SAME | 45 C: condenser loop > limit @ 2.05 h | 40 C: no change
RACK_OPEN | TBD | OPTIMAL | OPTIMAL | FAIL |  | SAME | SAME | SAME | 45 C: condenser loop > limit @ 2.09 h | 40 C: SOC end -2 pts
CHARGER_DERATE_50 | TBD | OPTIMAL | OPTIMAL | OPTIMAL |  | SAME | SAME | TRADE-OFF |  | 40 C: SOC end -8 pts
LCC_VMS_COMMS | F46 | DERATED | DERATED | DERATED |  | BY-DESIGN | BY-DESIGN | BY-DESIGN | 20 C: traction blocked (state) @ 0.00 h; 40 C: traction blocked (state) @ 0.00 h; 45 C: traction blocked (state) @ 0.00 h | 40 C: cell -1.3 K, motor -28.7 K, SOC end -3 pts
CLASS_A_GENERIC | F46 | DERATED | DERATED | DERATED |  | BY-DESIGN | BY-DESIGN | BY-DESIGN | 20 C: traction blocked (state) @ 0.00 h; 40 C: traction blocked (state) @ 0.00 h; 45 C: traction blocked (state) @ 0.00 h | 40 C: cell -1.3 K, motor -28.7 K, SOC end -3 pts
ESTOP | TBD | DERATED | DERATED | DERATED |  | BY-DESIGN | BY-DESIGN | BY-DESIGN | 20 C: traction blocked (state) @ 0.00 h; 40 C: traction blocked (state) @ 0.00 h; 45 C: traction blocked (state) @ 0.00 h | 40 C: cell -1.3 K, motor -28.7 K, SOC end -3 pts
BASELINE |  | OPTIMAL | OPTIMAL | FAIL |  | BASELINE | BASELINE | BASELINE | 45 C: condenser loop > limit @ 2.08 h | 40 C: no change
Findings
1. PE pump loss and a BTMS 24 V supply trip (DCC65M24 feeds all SPAL pumps) are equally severe: chopper fluid 127-153 C at onset under load at every ambient (F61, RSK-NEW-30). Confirms the DCC65M24 and pump spares and the need for a flow-loss trip.
2. PE fan loss fails at 40 C (chopper > 63 C after 14 min) and 45 C (after 10 min); at 20 C it passes with 8 K margin (4.7 K on the old baseline; lower aux heat now) (F59).
3. The no-fault baseline fails at 45 C on the condenser loop only (66.3 C vs 65 C check valves, ~2.1 h after onset, during charging). PE loop, cells and motors stay inside limits (F55, RSK-NEW-31).
4. Chiller loss (1, 2, or all 4 modules via a BTMS 12 V supply trip) has no effect on this 3 h duty up to 40 C: cells peak at ~28 C. At 45 C these faults look better than baseline only because the condenser runs cooler (MASKED).
5. Axle 4 cut-out cannot hold LC-3 on 0.5% at any ambient; remaining motors ~20 K hotter (F62).
6. Temperature sensor +5 K: TMS energy roughly doubles to triples (22 vs 10 kWh at 20 C; 59 vs 28 kWh at 40 C), condenser margin 2.7 K at 40 C, fails at 45 C within 4 min; -5 K: chiller never starts on this duty (F63).
7. Blower loss and aux converter trip: motors +49 K in 3 h without reaching the (placeholder) limit; aux trip also stops TMS and budget loads. WATCH for long duty (F64, C-22).
8. Battery pump loss, 1-2 open strings and charger derate: no thermal effect in 3 h; strings cost 1-2 SOC points, a 50% charger derate costs ~9 SOC points per charge window.
9. Comms loss, Class A and E-Stop stop the loco as designed. TMS energy for the 3 h duty (baseline): 10 / 28 / 40 kWh at 20 / 40 / 45 C.
10. v1.0 PE loop update (KULI 2026-10-09): no verdict or relative-to-baseline changes; chopper peaks +0.7-0.9 K (less flow per chopper), inverter peaks -0.1 K (more flow). One PE pump out of three (PE_PUMP_1OF3): SAME at all ambients, chopper +0.3-0.4 K.
11. Chopper heat is the open sensitivity: the +0.85 K shift implies a ~4.9 K chopper coolant rise at peak duty. At the KULI loss basis (2.7x the model) the 45 C baseline chopper peak would be ~64 C vs the 63 C limit (40 C: ~59 C). Pending Integral loss data (C-24, F65, RSK-NEW-38).
Limits: 3 h duty; lumped thermal; motor model and chiller map are placeholders; LV (SPAL) radiators not modeled (RSK-NEW-35); no breakaway resistance (RSK-NEW-33). C-22 repeats on 8 h duty.
Full results (results/fault_sweep_20261010_1013.csv, POC baseline + PE update; Tchop/Tinv from compare_fault_sweeps vs 20261007_1600, PE_PUMP_1OF3 rows at 0.1 K)
fault | fmea | T_amb | verdict | first_limit | t_first_limit_h | Tcell_max | Tsup_max | Tchop_max | Tinv_max | Tcond_max | Tmotor_max | soc_end | E_tms_kWh | dSOC_end | dTchop_max | dTinv_max | dTcell_max | dTmotor_max | by_design_stop | limit
AUX_DCDC_TRIP | TBD | 20 | OPTIMAL | none |  | 25.9499 | 26.3935 | 30.6217 | 26.7896 | 20 | 123.4543 | 0.87933 | 3.4852 | 0.0032669 | -0.1419 | -0.011899 | -0.022585 | 49.2926 | 0
AUX_DCDC_TRIP | TBD | 40 | OPTIMAL | none |  | 27.7974 | 46.5376 | 50.7658 | 47.0519 | 40 | 143.4533 | 0.87808 | 20.5728 | 0.0033301 | -0.12302 | -0.013012 | -0.029407 | 49.29 | 0
AUX_DCDC_TRIP | TBD | 45 | OPTIMAL | none |  | 28.2816 | 51.5384 | 55.7665 | 52.0526 | 45 | 148.454 | 0.87788 | 22.3817 | 0.0054368 | -0.13806 | -0.49182 | 0.2761 | 49.2919 | 0
AXLE4_CUTOUT | F50 | 20 | DERATED | speed deficit > 1 mph | 0.12694 | 25.5842 | 26.3935 | 31.5198 | 26.7896 | 20 | 93.9841 | 0.90345 | 10.4207 | 0.027393 | 0.75623 | -0.011899 | -0.38835 | 19.8224 | 0 | speed not held
AXLE4_CUTOUT | F50 | 40 | DERATED | speed deficit > 1 mph | 0.12694 | 27.3826 | 46.5376 | 51.6652 | 47.0519 | 40 | 113.983 | 0.90233 | 27.4748 | 0.027586 | 0.77644 | -0.013012 | -0.44416 | 19.8197 | 0 | speed not held
AXLE4_CUTOUT | F50 | 45 | DERATED | speed deficit > 1 mph | 0.12694 | 27.8693 | 51.5384 | 56.6656 | 52.0526 | 45 | 118.984 | 0.90215 | 29.3172 | 0.029705 | 0.76098 | -0.49182 | -0.13626 | 19.8219 | 0 | speed not held
BASELINE |  | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1617 | 0.87606 | 10.4207 | 0 | 0 | 0 | 0 | 0 | 0
BASELINE |  | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1633 | 0.87475 | 27.7692 | 0 | 0 | 0 | 0 | 0 | 0
BASELINE |  | 45 | FAIL | condenser loop > limit | 2.0769 | 28.0055 | 51.6076 | 55.9046 | 52.5445 | 66.2718 | 99.1621 | 0.87244 | 40.0357 | 0 | 0 | 0 | 0 | 0 | 0 | condenser loop > 65 C (check valve)
BAT_PUMP_FAIL | TBD | 20 | OPTIMAL | none |  | 25.9901 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1616 | 0.87606 | 10.4207 | -2.4142e-07 | 2.7944e-08 | 2.7912e-08 | 0.01755 | -9.9911e-05 | 0
BAT_PUMP_FAIL | TBD | 40 | OPTIMAL | none |  | 27.8328 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1618 | 0.87475 | 27.7692 | 1.9128e-07 | -7.8503e-07 | -7.8478e-07 | 0.005989 | -0.0015068 | 0
BAT_PUMP_FAIL | TBD | 45 | FAIL | condenser loop > limit | 2.0635 | 28.0202 | 51.721 | 55.9484 | 52.6796 | 66.2718 | 99.162 | 0.87218 | 41.3566 | -0.00026239 | 0.043797 | 0.13511 | 0.014644 | -7.2839e-05 | 0 | condenser loop > 65 C (check valve)
BLOWER_FAIL | F50 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 123.4498 | 0.87606 | 10.4207 | 6.3992e-08 | 7.8941e-07 | 7.8913e-07 | -1.2282e-06 | 49.2881 | 0
BLOWER_FAIL | F50 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 143.453 | 0.87475 | 27.7692 | -1.8203e-07 | -7.2308e-07 | -7.2284e-07 | -6.8136e-06 | 49.2897 | 0
BLOWER_FAIL | F50 | 45 | FAIL | condenser loop > limit | 2.0769 | 28.0055 | 51.6076 | 55.9046 | 52.5445 | 66.2718 | 148.4559 | 0.87244 | 40.0357 | -1.4485e-08 | -7.8328e-07 | -7.7785e-07 | 8.4919e-06 | 49.2938 | 0 | condenser loop > 65 C (check valve)
BTMS_12V_PS_TRIP | F55 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1618 | 0.87606 | 10.4207 | 8.3742e-08 | -2.9394e-07 | -2.9413e-07 | 4.5316e-07 | 7.2755e-05 | 0
BTMS_12V_PS_TRIP | F55 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1618 | 0.87475 | 27.7691 | -8.7019e-08 | 3.1248e-07 | 3.1238e-07 | -8.5379e-06 | -0.0015043 | 0
BTMS_12V_PS_TRIP | F55 | 45 | OPTIMAL | none |  | 28.3115 | 51.5686 | 55.9066 | 52.2154 | 45 | 99.1624 | 0.87391 | 32.6616 | 0.0014697 | 0.0020389 | -0.32904 | 0.30595 | 0.0002956 | 0
BTMS_24V_PS_TRIP | F61 | 20 | FAIL | chopper fluid > limit | 0 | 25.9929 | 26.3935 | 127.3828 | 29.6956 | 20 | 74.1614 | 0.87522 | 20.2963 | -0.00084481 | 96.6192 | 2.8941 | 0.020424 | -0.00028448 | 0 | chopper fluid > 63 C
BTMS_24V_PS_TRIP | F61 | 40 | FAIL | chopper fluid > limit | 0 | 27.8333 | 46.5376 | 148.4569 | 50.1232 | 40 | 94.164 | 0.87458 | 29.0695 | -0.00016704 | 97.5681 | 3.0583 | 0.0064913 | 0.00065279 | 0 | chopper fluid > 63 C
BTMS_24V_PS_TRIP | F61 | 45 | FAIL | chopper fluid > limit | 0 | 28.0202 | 51.5384 | 153.3021 | 64.0939 | 66.2718 | 99.1618 | 0.87218 | 41.3566 | -0.0002625 | 97.3975 | 11.5494 | 0.01465 | -0.00030133 | 0 | chopper fluid > 63 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
CHARGER_DERATE_50 | TBD | 20 | OPTIMAL | none |  | 25.2388 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1617 | 0.79658 | 10.4207 | -0.079476 | 0 | 0 | -0.7337 | 0 | 0
CHARGER_DERATE_50 | TBD | 40 | OPTIMAL | none |  | 27.1389 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1633 | 0.7932 | 27.4365 | -0.081542 | 0 | 0 | -0.68791 | 0 | 0
CHARGER_DERATE_50 | TBD | 45 | OPTIMAL | none |  | 27.6258 | 51.5512 | 55.9093 | 52.0654 | 45 | 99.1621 | 0.79284 | 29.3172 | -0.079607 | 0.0047443 | -0.47903 | -0.37974 | 0 | 0
CLASS_A_GENERIC | F46 | 20 | DERATED | traction blocked (state) | 0 | 25.0201 | 26.3935 | 30.6217 | 26.7896 | 20 | 45.4782 | 0.84484 | 10.4207 | -0.031225 | -0.1419 | -0.011899 | -0.9524 | -28.6835 | 1 | speed not held
CLASS_A_GENERIC | F46 | 40 | DERATED | traction blocked (state) | 0 | 26.5607 | 46.5376 | 50.7658 | 47.0519 | 40 | 65.4785 | 0.84255 | 21.8838 | -0.032195 | -0.12302 | -0.013012 | -1.2661 | -28.6848 | 1 | speed not held
CLASS_A_GENERIC | F46 | 45 | DERATED | traction blocked (state) | 0 | 27.0516 | 51.5384 | 55.7665 | 52.0526 | 45 | 70.479 | 0.84107 | 29.3172 | -0.031372 | -0.13806 | -0.49182 | -0.95392 | -28.6831 | 1 | speed not held
COND_FAN_FAIL | F55 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1618 | 0.87606 | 10.4207 | 8.3742e-08 | -2.9394e-07 | -2.9413e-07 | 4.5316e-07 | 7.2755e-05 | 0
COND_FAN_FAIL | F55 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1618 | 0.87475 | 27.769 | 2.141e-07 | -1.0972e-06 | -1.0968e-06 | -1.1788e-05 | -0.0015421 | 0
COND_FAN_FAIL | F55 | 45 | FAIL | condenser loop > limit | 2.0486 | 28.0056 | 51.5903 | 55.9078 | 52.4058 | 65.9545 | 99.1643 | 0.87409 | 31.7834 | 0.0016443 | 0.0032468 | -0.13863 | 6.3871e-05 | 0.0022342 | 0 | condenser loop > 65 C (check valve)
ESTOP | TBD | 20 | DERATED | traction blocked (state) | 0 | 25.0201 | 26.3935 | 30.6217 | 26.7896 | 20 | 45.4782 | 0.84743 | 1.7352 | -0.028635 | -0.1419 | -0.011899 | -0.9524 | -28.6835 | 1 | speed not held
ESTOP | TBD | 40 | DERATED | traction blocked (state) | 0 | 26.5606 | 46.5376 | 50.7658 | 47.0519 | 40 | 65.4785 | 0.84685 | 4.6341 | -0.0279 | -0.12302 | -0.013012 | -1.2662 | -28.6848 | 1 | speed not held
ESTOP | TBD | 45 | DERATED | traction blocked (state) | 0 | 27.0514 | 51.5384 | 55.7665 | 52.0526 | 45 | 70.479 | 0.8468 | 4.8817 | -0.025646 | -0.13806 | -0.49182 | -0.95409 | -28.6831 | 1 | speed not held
LCC_VMS_COMMS | F46 | 20 | DERATED | traction blocked (state) | 0 | 25.0201 | 26.3935 | 30.6217 | 26.7896 | 20 | 45.4782 | 0.84484 | 10.4207 | -0.031225 | -0.1419 | -0.011899 | -0.9524 | -28.6835 | 1 | speed not held
LCC_VMS_COMMS | F46 | 40 | DERATED | traction blocked (state) | 0 | 26.5607 | 46.5376 | 50.7658 | 47.0519 | 40 | 65.4785 | 0.84255 | 21.8838 | -0.032195 | -0.12302 | -0.013012 | -1.2661 | -28.6848 | 1 | speed not held
LCC_VMS_COMMS | F46 | 45 | DERATED | traction blocked (state) | 0 | 27.0516 | 51.5384 | 55.7665 | 52.0526 | 45 | 70.479 | 0.84107 | 29.3172 | -0.031372 | -0.13806 | -0.49182 | -0.95392 | -28.6831 | 1 | speed not held
MTM_LOSS_1 | F55 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1618 | 0.87606 | 10.4207 | -4.2017e-07 | 6.1709e-07 | 6.1686e-07 | 2.0269e-07 | 0.00014945 | 0
MTM_LOSS_1 | F55 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1618 | 0.87475 | 27.7691 | 8.1458e-07 | -6.7978e-07 | -6.7956e-07 | -6.9865e-06 | -0.001526 | 0
MTM_LOSS_1 | F55 | 45 | OPTIMAL | none |  | 28.0066 | 51.5977 | 55.905 | 52.4572 | 61.3993 | 99.1644 | 0.87272 | 38.6737 | 0.00027236 | 0.00039165 | -0.08724 | 0.0010886 | 0.0023353 | 0
MTM_LOSS_2 | F55 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1618 | 0.87606 | 10.4207 | 8.3742e-08 | -2.9394e-07 | -2.9413e-07 | 4.5316e-07 | 7.2755e-05 | 0
MTM_LOSS_2 | F55 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1631 | 0.87475 | 27.7692 | -6.4036e-09 | -1.1292e-06 | -1.1289e-06 | -5.3411e-07 | -0.00021856 | 0
MTM_LOSS_2 | F55 | 45 | OPTIMAL | none |  | 28.0087 | 51.5878 | 55.9055 | 52.3817 | 56.2714 | 99.1644 | 0.87314 | 36.5179 | 0.00070054 | 0.00086433 | -0.16274 | 0.0031618 | 0.0023226 | 0
PE_FAN_FAIL | F54 | 20 | OPTIMAL | none |  | 25.9718 | 51.3281 | 55.5453 | 51.7088 | 20 | 74.1615 | 0.87622 | 8.6707 | 0.0001588 | 24.7818 | 24.9073 | -0.00074214 | -0.00018859 | 0
PE_FAN_FAIL | F54 | 40 | FAIL | chopper fluid > limit | 0.2275 | 27.8173 | 71.3322 | 75.5494 | 71.7129 | 40 | 94.1616 | 0.87618 | 11.5695 | 0.0014367 | 24.6607 | 24.648 | -0.0095172 | -0.0017149 | 0 | charger supply > 55 C; chopper fluid > 63 C; inverter fluid > 60 C
PE_FAN_FAIL | F54 | 45 | FAIL | chopper fluid > limit | 0.16389 | 28.0037 | 76.3322 | 80.5495 | 76.9877 | 66.2718 | 99.1618 | 0.87405 | 22.5107 | 0.0016095 | 24.6449 | 24.4433 | -0.0018005 | -0.00026052 | 0 | charger supply > 55 C; chopper fluid > 63 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
PE_PUMP_1OF3 | F54 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 31.1 | 27 | 20 | 74.1617 | 0.87606 | 10.4207 | 0 | 0.33643 | 0.19851 | 0 | 0 | 0
PE_PUMP_1OF3 | F54 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 51.3 | 47.3 | 40 | 94.1633 | 0.87475 | 27.7692 | 0 | 0.41121 | 0.23513 | 0 | 0 | 0
PE_PUMP_1OF3 | F54 | 45 | FAIL | condenser loop > limit | 2.0769 | 28.0055 | 51.6076 | 56.3 | 52.8 | 66.2718 | 99.1621 | 0.87244 | 40.0357 | 0 | 0.3954 | 0.25555 | 0 | 0 | 0 | condenser loop > 65 C (check valve)
PE_PUMP_FAIL | F54 | 20 | FAIL | chopper fluid > limit | 0 | 25.9754 | 26.3935 | 128.4473 | 29.6957 | 20 | 74.1613 | 0.87522 | 20.2964 | -0.00084494 | 97.6837 | 2.8942 | 0.0028867 | -0.00040758 | 0 | chopper fluid > 63 C
PE_PUMP_FAIL | F54 | 40 | FAIL | chopper fluid > limit | 0 | 27.8273 | 46.5376 | 148.3882 | 50.1232 | 40 | 94.1619 | 0.87458 | 29.0695 | -0.00016697 | 97.4994 | 3.0583 | 0.00048801 | -0.0014848 | 0 | chopper fluid > 63 C
PE_PUMP_FAIL | F54 | 45 | FAIL | chopper fluid > limit | 0 | 28.0055 | 51.5384 | 152.7818 | 64.0949 | 66.2718 | 99.1641 | 0.87244 | 40.0357 | 6.2267e-08 | 96.8772 | 11.5505 | 8.5486e-06 | 0.0020449 | 0 | chopper fluid > 63 C; inverter fluid > 60 C; condenser loop > 65 C (check valve)
RACK_OPEN | TBD | 20 | OPTIMAL | none |  | 25.9432 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1619 | 0.86105 | 10.4207 | -0.015006 | 1.7784e-07 | 1.4805e-07 | -0.029268 | 0.00016832 | 0
RACK_OPEN | TBD | 40 | OPTIMAL | none |  | 27.8214 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1637 | 0.85942 | 27.7727 | -0.015323 | -1.2367e-06 | -1.2394e-06 | -0.0053457 | 0.00036814 | 0
RACK_OPEN | TBD | 45 | FAIL | condenser loop > limit | 2.0906 | 28.0039 | 51.5512 | 55.9093 | 52.1333 | 66.2718 | 99.1625 | 0.85665 | 40.0494 | -0.015792 | 0.0047446 | -0.41119 | -0.0016533 | 0.00037249 | 0 | condenser loop > 65 C (check valve)
STRING_OPEN_1 | TBD | 20 | OPTIMAL | none |  | 25.9889 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1614 | 0.86979 | 10.4207 | -0.0062667 | 3.2745e-07 | 2.6288e-07 | 0.016405 | -0.00030851 | 0
STRING_OPEN_1 | TBD | 40 | OPTIMAL | none |  | 27.85 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1638 | 0.86841 | 27.7487 | -0.0063365 | -3.7699e-07 | -3.8641e-07 | 0.023188 | 0.00047697 | 0
STRING_OPEN_1 | TBD | 45 | FAIL | condenser loop > limit | 2.0544 | 28.0067 | 51.7854 | 56.013 | 52.7527 | 66.2718 | 99.1621 | 0.86588 | 40.0973 | -0.0065633 | 0.10835 | 0.20828 | 0.0012091 | 5.6046e-05 | 0 | condenser loop > 65 C (check valve)
TSENSE_HIGH_5K | F46 | 20 | OPTIMAL | none |  | 25.0201 | 26.8502 | 31.1884 | 27.6085 | 44.8575 | 74.1632 | 0.87583 | 22.02 | -0.00023026 | 0.42484 | 0.80698 | -0.9524 | 0.0015108 | 0
TSENSE_HIGH_5K | F46 | 40 | OK | none |  | 25.356 | 47.0917 | 51.4399 | 48.0486 | 62.341 | 94.1628 | 0.87237 | 58.9448 | -0.0023783 | 0.55108 | 0.98371 | -2.4708 | -0.00056793 | 0 | PE margin 2.7 K
TSENSE_HIGH_5K | F46 | 45 | FAIL | condenser loop > limit | 0.056111 | 25.4434 | 52.1212 | 56.4794 | 53.1057 | 66.2718 | 99.1642 | 0.87391 | 59.1009 | 0.0014634 | 0.57479 | 0.56127 | -2.5621 | 0.002078 | 0 | condenser loop > 65 C (check valve)
TSENSE_LOW_5K | F46 | 20 | OPTIMAL | none |  | 25.9725 | 26.4054 | 30.7636 | 26.8015 | 20 | 74.1618 | 0.87606 | 10.4207 | 8.3742e-08 | -2.9394e-07 | -2.9413e-07 | 4.5316e-07 | 7.2755e-05 | 0
TSENSE_LOW_5K | F46 | 40 | OPTIMAL | none |  | 27.8268 | 46.5506 | 50.8888 | 47.0649 | 40 | 94.1618 | 0.87475 | 27.7691 | -8.7019e-08 | 3.1248e-07 | 3.1238e-07 | -8.5379e-06 | -0.0015043 | 0
TSENSE_LOW_5K | F46 | 45 | OPTIMAL | none |  | 28.3107 | 51.5512 | 55.9093 | 52.0654 | 45 | 99.1624 | 0.87458 | 29.3172 | 0.0021357 | 0.004744 | -0.47903 | 0.3052 | 0.0002956 | 0
Note on A88: Tchop/Tinv from the 2026-10-10 sweep summary (0.1 K); other columns copied from the baseline at the same ambient. Full precision: results/fault_sweep_20261010_1013.csv

## Spares
Spares plan — initial risk-based pass (2026-10-08). Source: Voltify Proto Switcher (GP Based) - Locomotive Kit FULL BOM (Jonathan), FMEA, RSK register, fault sweep.
Go-kit = spares staged at Huntington for build and first power; they travel with the loco to Jacksonville (dead-in-tow). JAX depot = shipped directly to Jacksonville for the 30-day run and the CSX 90-day evaluation. Totals are what to hold, not what to buy (subtract stock on hand).
Sizing rule: stop-the-loco single point or fast thermal failure = 1+ on site; long-lead / single-source = 1 total; wear and consumables = 10-20% of installed (min 1-2); not needed for the demo = 0. Lead times are assumptions. Quantities come down as the "Reduce when" triggers close.
BOM # | Item | Mfr / P/N | Installed (demo) | BOM spare target (Jonathan) | Stock (BOM) | Risk category | FMEA / RSK / fault-sweep link | Lead time (assumed) | Go-kit (HHR, travels) | JAX depot | Total recommended | Delta vs BOM target | Rationale | Reduce when | Owner | Status
4.1.2 | Chopper (Traction Converter, ITC) | Integral ITC-0001 | 4 | 1 | — | SPOF-degrade + long lead | F22, F49, F62; RSK-NEW-32 | Long | 1 | 0 |  |  | Axle loss = ~25% tonnage cut (fault sweep); Integral long lead. One unit travels with the loco as the swap spare. | Integral confirms 2-week swap/repair support at JAX | Jonathan + Integral | Open
3.8.1.1 | LCC CPU PCB | Integral (LCC-K008) | 1 | 1 | C:1 | SPOF-stop | F46, F51 | Long | 1 | 0 |  |  | LCC loss = no traction (Class A). Pre-load SW per H-30 manifest. | Integral on-site support contract in place | Jonathan + Integral | Open
3.8.1.2 | LCC IO PCB | Integral (LCC-K008) | 1 | 1 | C:1 | SPOF-stop | F46 | Long | 1 | 0 |  |  | As LCC CPU. | As above | Jonathan + Integral | Open
3.8.2 | Cab Display Kit | Integral LDU-K001 | 1 |  | — | SPOF-stop | F46 | Long | 0 | 1 |  |  | Operator interface for traction; Integral item. | Integral confirms loaner/turnaround | Jonathan + Integral | Open
3.1.1 | Reverser Motor Module | DLL Type 711 | 1 |  | — | SPOF-stop | H-13 (fwd/rev) | Med | 1 | 0 |  |  | Single reverser drive; no direction change without it. | Reverser cycles cleanly through H-13 and J-02B | Bryan | Open
3.1.2 | Reverser Switch Module | DLL Type 712 | 4 |  | — | SPOF-stop | H-13 | Med | 1 | 0 |  |  | Per-motor switch; one failure blocks an axle or direction. | As above | Bryan | Open
4.1.4.1 / 6.1.5.1 / 6.1.8.1 / 6.5.1 | 2000 A fuse (DC-link, charger, filter) | HIITIO | 4 | 5 | — | Bring-up + SPOF-stop | F37 (precharge), H-05..H-09 | Med | 2 | 3 |  |  | Common P/N in 4 places; first-energization faults and inrush events blow fuses. Aligned to BOM target (5). | Precharge/inrush verified at full voltage (H-07) and 30 days without a fuse event | Bryan | Open
4.1.5 | DC-link / chopper fuse | TBD (not defined) | 4 |  | — | Bring-up + SPOF-degrade | F22 | Med | 2 | 1 |  |  | One per chopper; blown fuse = axle out. | P/N defined and no fuse event through J-11 | Jack | Open
4.1.6 | Power contactor (traction) | HHR item | 10 |  | — | Wear | F53 | Med | 1 | 1 |  |  | Switcher stop/go cycling (F53). | Cycle count from J-18 well inside rating | Dragan | Open
4.1.8.4 | HV precharge resistor | TBD | 2 |  | — | Bring-up | F37 | Short | 1 | 0 |  |  | Most likely part to fail at first precharge. | H-07 passes at full voltage | Jack | Open
4.1.8.2 / 5.3.4 / 6.1.4.4 / 6.1.9.4 | Contactor REC47B1JA (string + precharge) | Rincon REC47B1JA | 27 |  | — | Wear + SPOF-degrade | F37, F53 | Med | 2 | 2 |  |  | 27 installed; a welded/failed string contactor removes a string (fault sweep: small effect) but a precharge contactor stops HV. | 30 days of cycles with no feedback fault | Bryan | Open
6.1.4.5 / 6.1.9.5 | Contactor RXR1KB1QC (panto + charger mains) | Rincon RXR1KB1QC | 6 |  | — | SPOF-stop (charging) | F12, F37 | Med | 1 | 1 |  |  | Charging path; MCS units (8) deferred, not counted. | Static + dynamic charging pass (J-08/J-09) | Bryan | Open
4.1.8.3 / 6.1.4.6 / 6.1.9.6 | Contactor RECNC46B1QA (discharge) | Rincon RECNC46B1QA | 3 |  | — | Safety | F15 | Med | 1 | 0 |  |  | Discharge path is part of HV-safe state. | H-11 discharge verified | Bryan | Open
3.7.2 / 9.6.2 | E-Stop contact block (1NO+1NC) | Schneider 9001KA1 | 2 |  | — | Safety | E-Stop tests | Short | 2 | 0 |  |  | Cheap; E-Stop chain must be intact to run. | — | Bryan | Open
3.7.1 | E-Stop mushroom body | Schneider 9001SKR9R | 1 |  | — | Safety | E-Stop tests | Short | 1 | 0 |  |  | As above. | — | Bryan | Open
4.1.9 / 6.1.6.2 | E-Stop hardware timer (Voltify) | Voltify | 2 |  | — | Safety + SPOF-stop | E-Stop tests | Med | 1 | 0 |  |  | Custom board; no off-the-shelf replacement. | Board passes H-09/H-10 and 30 days | Micah | Open
6.3 | 750V-PS (1500 to 750 V DC/DC) | Zekalabs LB-1186-01-01 | 1 |  | — | SPOF-stop + single source | AUX_DCDC_TRIP (fault sweep), F59, F64; RSK-108 | Long | 1 | 0 |  |  | Loss = all aux, TMS, blowers and compressor lost. Single source; thermal-derate troubleshooting ongoing. | Vendor derate issue closed and 30 days clean | Bryan | Open
4.2 | 72V-PS (750 to 72 V DC/DC) | Zekalabs LB-1113-41 | 1 |  | — | SPOF-stop + single source | 72 V bus, F40 | Long | 1 | 0 |  |  | Loss = 72 V on starter battery only (hours). Ties to open Zekalabs PO quantity question (1 vs 3). | As above | Bryan | Open
4.3 / 7.5 | AC inverter (blower + compressor) | Inmotion ACH65M30-WEHT | 2 |  | — | SPOF-stop (compressor) / degrade (blowers) | F64 | Long | 0 | 1 |  |  | Common P/N; compressor loss = no air = no movement. One spare covers both. | 30 days with no inverter fault | Bryan | Open
3.3.2 | 24 V PS 500 W | RECOM RMD500-110-24SEW | 4 | 4 | — | Degrade | 24V_Ctrl peak 72% load (POC budget) | Short | 2 | 2 |  |  | Loss of 1 of 4 leaves ~1.5 kW vs 1.45 kW peak: no margin. Aligned to BOM target (shown as "4?" in the BOM). | Peak 24 V load measured < 1.2 kW | Bryan | Open
7.1.2 | BTMS 24 V PS (pumps) | Inmotion DCC65M24 | 1 | 1 | — | SPOF-stop (fast) | F61, PE_PUMP_FAIL (fault sweep); RSK-NEW-30 | Long | 1 | 0 |  |  | Feeds all 6 SPAL pumps: loss = PE pump failure = choppers > 63 C at once. Keep BOM target. | Flow-loss trip implemented (H-34) and 30 days clean | Bryan | Open
7.1.3 | BTMS 12 V PS (MTM LV, SPAL fans) | NetPower DG16K0-14BL | 1 | 1 | — | SPOF-degrade | F59, F55 | Med | 1 | 0 |  |  | Feeds MTM ECUs and 12 V fans. Keep BOM target. | As above | Bryan | Open
7.1.1.2 | 750 V fuse, BTMS module | Eaton EVK22-60-T | 4 | 5 | — | Bring-up | F55 | Short | 2 | 3 |  |  | Aligned to BOM target (5). | No fuse event through J-11 | Bryan | Open
7.1.1.3 | 750 V fuse, PTC heater | Eaton EKM10-30-AT | 1 | 5 | — | Bring-up | F56 | Short | 2 | 3 |  |  | Aligned to BOM target (5). | As above | Bryan | Open
7.1.1.4 | 750 V fuse, BTMS 24 V PS | TBD | 1 | 5 | — | Bring-up | F61 | Short | 2 | 3 |  |  | Blown fuse = all pumps lost (fast failure). Aligned to BOM target (5). | No fuse event through J-11 | Bryan | Open
7.1.1.5 | 750 V fuse, BTMS 12 V PS | TBD | 1 | 5 | — | Bring-up | F59 | Short | 2 | 3 |  |  | Blown fuse = MTM ECUs and 12 V fans lost. Aligned to BOM target (5). | No fuse event through J-11 | Bryan | Open
6.6.2..6.6.5 | 750 V fuse, VHR panel (72V-PS, inverters, BTMS box) | TBD | 4 |  | — | Bring-up | AUX_DCDC_TRIP | Short | 2 | 2 |  |  | One spare per rating; P/Ns not yet defined. | P/Ns defined; no fuse event through J-11 | Jack | Open
7.6.1.1 | AC 3-phase contactor (compressor box) | HHR item | 2 |  | — | SPOF-stop | Air system | Short | 1 | 0 |  |  | Compressor start; no air = no movement. | — | Dragan | Open
3.2.2 | VMS computer | Premio ACO-6000-CML-1 | 1 | 1 | C:2 | SPOF-stop | F46, F51 | Med | 1 | 0 |  |  | VMS loss = no HV state machine. Keep a pre-imaged unit (H-30 manifest). | — | Jared | Open
3.2.4 | ETH to 4x CAN gateway | Kvaser | 1 | 1 | — | SPOF-stop | F46, F21 | Short | 1 | 0 |  |  | All 4 CAN buses to VMS pass through it. | — | Jared | Open
3.2.7 / 6.1.1.1 / 6.1.4.2 / 6.1.9.2 | VIO controller PCB (pre-flashed) | Voltify | 4 |  | — | SPOF-stop | F37, F51 | Med | 1 | 1 |  |  | 4 instances (VMS, panto panel, charger panel, HSCB+REV); custom board. | All 4 instances pass 30 days; spare boards from build lot | Micah | Open
3.2.1 | UPS | Bicker UPS-IP-3 | 1 |  | — | Degrade | F48 (logging), graceful shutdown | Med | 0 | 1 |  |  | Loss risks uncontrolled VMS shutdown and data loss. | — | Jared | Open
3.2.3 | Touchscreen HMI | beetronics 12TS7M | 1 | 1 | — | Degrade (Class B) | Fault Classes | Short | 0 | 1 |  |  | Keep BOM target. | — | Jared | Open
3.2.6 | Ethernet router (LTE/WiFi) | Teltonika ATRM50 | 1 | 1 | — | Degrade | F48, RSK-NEW-19 (data logging) | Short | 0 | 1 |  |  | Data path and LTE fallback for Starlink. | Starlink + LTE both proven at JAX | Matan | Open
3.2.6.1 | Cellular roof antenna | TBD | 1 | 1 | — | Degrade | F48 | Short | 0 | 1 |  |  | Keep BOM target. | As above | Matan | Open
3.2.6.2 | WiFi roof antenna | TBD | 1 | 1 | — | Low | — | Short | 0 | 1 |  |  | Not needed for operation; aligned to BOM target (1). | — | Matan | Open
3.2.2.2 | VMS power push button | TBD | 1 | 3 | — | Low | — | Short | 1 | 2 |  |  | Aligned to BOM target (3). | — | Jared | Open
3.2.9 | Audio speaker | TBD | 1 | 1 | — | Low | — | Short | 0 | 1 |  |  | Not needed for operation; aligned to BOM target (1). | — | Jared | Open
3.2.8 / 4.5 / 6.7 | Maintenance key + yellow door-lock key | Secheron | 1 |  | — | Safety (LOTO) | Grounding switch / LOTO | Med | 1 | 0 |  |  | A lost key blocks maintenance access. | — | Dragan | Open
6.4.3 | RVT (residual voltage tester) PCB | Voltify | 1 |  | — | Safety | F16 | Med | 1 | 0 |  |  | Grounding-switch interlock depends on it. | RVT interlock verified (H-22) | Micah | Open
5.3.2 | BCU (2nd-level BMS) | Jinko/BMS | 12 |  | — | SPOF-degrade | F46 (BMS comm loss = Class A) | Long | 1 | 1 |  |  | BCU loss isolates its string; swap restores capacity. | Strings stable 30 days | Micah | Open
5.3.3 | Combiner fuse | TBD | 12 |  | — | Bring-up | F04 | Med | 2 | 0 |  |  | String combining at first energization. | All strings online (H-05) | Bryan | Open
5.3.6 | Combiner current sensor | TBD | 12 |  | — | Degrade | F04 | Med | 1 | 0 |  |  | Bad reading can trip a string. | — | Micah | Open
5.3.7 | Combiner power distro PCB | Voltify | 6 |  | — | SPOF-degrade | F04 | Med | 1 | 0 |  |  | Custom board. | — | Micah | Open
5.5 | TRB Ethernet switch | TBD | 2 |  | — | SPOF-degrade | F46 | Short | 1 | 0 |  |  | Loss = BCU comms on that side. | — | Jared | Open
5.2 | Battery pack module | Jinko | 48 |  | — | Degrade (string isolation) | Fault sweep STRING_OPEN/RACK_OPEN | Long | 0 | 0 |  |  | 10-11 strings still run the demo (fault sweep). Revisit for CSX 90-day. | — | Micah | Open
6.1.6.1 | ITI-AUX controller (onboard charger) | Integral | 1 | 1 | — | SPOF-stop (charging) | F12; critical path | Long | 0 | 1 |  |  | Keep BOM target. Full ITV spare not recommended (cost); Integral support instead. | Charging passes J-09 and 30 days | Jonathan + Integral | Open
8.6.2 | Pantograph controller PCB (pre-flashed) | Voltify | 1 |  | — | SPOF-stop (charging) | F09, F12 | Med | 0 | 1 |  |  | Dynamic charging is a showcase function; custom board. | Dynamic charging 30 days clean | Micah | Open
8.2.2 | Pantograph current collector (carbon strip) | Morgan MY258A4 | 8 | 16 | — | Wear | Pantograph contact (80-100 N) | Med | 0 | 16 |  |  | Two full sets; wear rate on the rigid OCS is unknown. Aligned to BOM target (16). | Measured wear rate shows > 3 months life | Jonathan | Open
8.3 | Surge arrester (pantograph) | Secheron | 4 |  | — | Degrade | — | Med | 0 | 1 |  |  | Lightning/switching surge on roof. | — | Jonathan | Open
8.4 | Pantograph current sensor | LEM HAX 1000-S | 4 |  | — | Degrade | — | Med | 0 | 1 |  |  | Per-head current measurement. | — | Micah | Open
8.2.1 | Pantograph body | Secheron SPL26 | 4 |  | — | Degrade (redundant) | — | Long | 0 | 0 |  |  | Only 2 heads needed per leg; 4 fitted gives redundancy. | — | Jonathan | Open
7.2.11 / 7.3.6 | SPAL high-capacity coolant pump | SPAL 30207006A | 6 |  | — | SPOF-stop (fast) | F61, PE_PUMP_FAIL; RSK-NEW-30 | Med | 1 | 2 |  |  | PE pump loss is the most severe fault (choppers > 63 C at once); common P/N with battery pumps. | Flow-loss trip in place (H-34) and pumps run 30 days | VJ | Open
7.2.2.3 / 7.3.2.3 | SPAL 12 V radiator fan | SPAL VA117-ABL506P | 6 |  | — | SPOF-degrade (fast on hot days) | F59; RSK-NEW-29 | Short | 1 | 1 |  |  | PE fan loss fails at 40 C in 9-12 min (fault sweep). | Fan status feedback + derate implemented | VJ | Open
7.2.3 / 7.3.3 | EMP HV radiator + fan assembly (750 V) | EMP 2029352000 | 2 |  | — | SPOF-degrade (fast on hot days) | F54, F59; RSK-NEW-35 | Long | 0 | 1 |  |  | Matches Jonathan's plan (one JAX LRU, one Cerritos bench spare not counted here). | 30 days at JAX with no fan fault | VJ | Open
7.2.5 / 7.3.5 / 7.2.4 / 7.3.4 | Coolant / ambient temperature sensor | TBD | 6 |  | — | Degrade | F63 (sensor bias) | Short | 1 | 1 |  |  | Sensor bias drives wrong cooling decisions (fault sweep). | — | VJ | Open
4.4.1 / 7.3.7.1 | Flow regulator | TBD | 11 |  | — | Degrade | F54 | Short | 1 | 1 |  |  | Mis-set or failed regulator starves a device. | KULI flow split verified on loco | VJ | Open
4.4.2 / 7.2.10.1 / 7.3.7.2 | Coolant hose set (repair kit) | TBD | 3 |  | — | SPOF-stop (leak) | F54, F61 | Short | 1 | 1 |  |  | Leak = pump loss equivalent. | No leaks through 30 days | VJ | Open
— | Coolant top-up (Zerex G-48 or approved) | Valvoline Zerex G-48 |  |  | — | Consumable | F54 check-valve/coolant compatibility | Short | 40 L | 40 L |  |  | Fill and leak top-up for 3 loops. | — | VJ | Open
7.2.8 | BTMS thermal module (MTM) | Maxwell | 4 |  | — | Degrade (not needed for demo duty) | F55; RSK-NEW-36 | Long | 0 | 0 |  |  | Fault sweep: 1-2 module loss has no effect on 3 h duty up to 45 C. Revisit for 8 h duty (C-22) and CSX summer. | — | Jack | Open
7.2.9 | PTC heater | Webasto HVH120 | 1 |  | — | Degrade (cold soak only) | F56, F58; RSK-NEW-25 | Med | 0 | 0 |  |  | Jan-Feb Jacksonville mild; preconditioning plan covers it. Revisit after J-21. | — | Jack | Open
7.3.1 | PE cooling controller | Voltify/Integral | 1 |  | — | SPOF-stop (fast) | F59, F61 | Med | 1 | 0 |  |  | Controls PE pumps and fans; if built as a custom board, keep a pre-flashed spare. | — | Micah | Open
10.0.2.3 | Traction blower filter | HHR item | 2 |  | — | Consumable | F64 | Short | 0 | 2 |  |  | Clogged filter = blower loss equivalent. | — | Dragan | Open
10.0.2.1 | Traction blower | HHR item | 2 |  | — | Degrade (WATCH) | F64; RSK-NEW-34 | Long | 0 | 0 |  |  | Fault sweep: +49 K motor rise in 3 h, no limit. Decide after C-22 (8 h). | — | Dragan | Open
3.2.5 | Starlink modem | Starlink | 1 |  | — | Degrade | F48, RSK-NEW-19 | Short | 0 | 1 |  |  | Primary telemetry path; LTE router is the fallback, but data logging from first power is a requirement (DR-50). | Starlink + LTE both proven at JAX | Matan | Open
3.2.5.1 | Starlink roof antenna | Starlink | 1 |  | — | Degrade | F48 | Short | 0 | 0 |  |  | Roof unit rarely fails; modem spare covers the likely failure. | — | Matan | Open
10.0.1 | RFID reader (operator authentication) | FEIG LRU500i-PoE-UHF | 1 |  | — | SPOF-stop (if VMS requires RFID to enable) | VMS state machine | Med | 0 | 1 |  |  | If authentication gates traction, a dead reader stops the loco; confirm whether a bypass exists. | VMS bypass for RFID confirmed | Jared | Open
6.3.1 | E-Stop voltage level translator | Voltify | 1 |  | — | Safety + SPOF-stop | E-Stop tests | Med | 1 | 0 |  |  | Custom board in the E-Stop chain. | Board passes H-09/H-10 and 30 days | Micah | Open
5.8 | Gas and fire sensor | TBD |  |  | — | Safety | Fire/gas detection (TBD) | Med | 0 | 1 |  |  | Safety detection must be functional to operate; quantity and P/N TBD. | P/N and count defined | Jared | Open
1.1 | 72 V lead-acid starter battery (32 V blocks) | Donor (HHR) | 2 |  | HHR:2 | Degrade | 72 V bus, dead-in-tow 72 V endurance | Med | 0 | 0 |  |  | Two blocks already in HHR stock beyond the installed set; no extra spare. | — | Dragan | Open
7.2.13 | Inline coolant flow meter | OMICON F-4600 | 1 |  | — | Low | F61 (flow monitoring) | Short | 0 | 0 |  |  | Instrumentation only; does not stop the loco. | — | VJ | Open
2.1 | Air brake system | NYAB CCBIIe | 1 | 0 | — | SPOF-stop | Brakes (FRA 229/232) | Long | 0 | 0 |  |  | BOM target 0; covered by NYAB service and the HHR air-brake supplier. | — | Dragan | Open
6.1.7 | Integral LC filter | Integral LCF-0001 | 1 |  | — | SPOF-stop (charging) | F12 | Long | 0 | 0 |  |  | Passive filter, low failure rate; Integral support instead of a spare. | — | Jonathan + Integral | Open
9.x | MCS box (inlets, controllers, contactors, HMI) | Various |  |  | — | Not needed for demo | DR-05 | — | 0 | 0 |  |  | MCS deferred to post-demo. | — | — | Open
6.1.2 | HSCB | Secheron | 2 |  | — | SPOF-stop | DR-42; RSK-NEW-16; F67 | TBD (Secheron) | 0 | 0 |  |  | Retained for demo in v1.1; no charging without it. Spare quantity TBD against Secheron lead time | — | Bryan | Open
Summary
Lines with a recommended spare
Go-kit units (Huntington, travels with loco)
JAX depot units
Total units recommended (excl. coolant)
Lines below Jonathan target (delta < 0)
Lines above Jonathan target (delta > 0)
Stop-the-loco / safety lines
Long-lead lines with a spare
Notes
1. Biggest additions where the BOM had no target: one spare chopper and LCC boards with the loco (axle loss cuts tonnage ~25%; LCC loss stops the loco), a 750V-PS and 72V-PS (single-source, all aux lost), pumps and fans (fastest failures in the fault sweep), and the common 2000 A fuse and Rincon contactors for first energization.
2. Items held at 0 on purpose: Maxwell modules, PTC heater, battery modules, pantograph bodies, traction blowers and MCS. (v1.1: HSCB removed from this list; retained for demo, spare quantity TBD.) The fault sweep and demo scope show they do not stop the demo; revisit after C-22 (8 h duty) and before CSX summer service.
3. Aligned to Jonathan's BOM targets wherever they are higher (2000 A fuse 5, 750 V BTMS fuses 5 each, RECOM 24 V PS 4, VMS push button 3, WiFi antenna 1, speaker 1, pantograph carbon strips 16). No line is below his target. Lines without a BOM target carry a suggestion based on function and failure risk.
4. BOM shows BOTH an EMP HV radiator + fan assembly and an LV radiator with 3 SPAL fans per loop. The POC Power Budget lists only the SPAL fans; the model and KULI only the EMP set (RSK-NEW-35).
5. Several BOM P/Ns are TBD or marked "??" (fuses, sensors, flow regulators, UPS, display). Spare quantities hold, but cannot be ordered until P/Ns are fixed.
6. Integral items (chopper, LCC boards, LDU, ITI-AUX): confirm with Integral whether they hold field spares and their turnaround, which may replace Voltify-held spares.

## Energy
Dynamic charging window
Pack energy (MWh) — 48 batteries, 6 strings | 5.016 | Dynamic charging demo plan, Oct 6 (confirmed); 4.2 MWh retired
Usable SOC window (fraction) | 80% | Assumption: 10-90%
Charge power at wire (MW) | 2.1 | Demo limit (DR-17): 0.5C x 4.2 MWh Jacksonville ground ESS; wire current <= 1,666 A
Wire-to-battery efficiency | 97% | Assumption; to be measured (J-06)
Speed (mph) | 0.5 | Showcase
Target distance (mi) | 2 | Showcase
Usable energy (MWh)
Time to fill at charge power (h)
Distance covered while filling (mi)
Time to cover target distance (h)
Power to spread usable energy over target distance (MW)
Charge C-rate |  | Cell rating 0.5C
Power at 0.5C (MW)
Wire current at the charge power with a 1,500 V wire (A); limit 1,666 A |  | Below 1,260 V wire voltage the 1,666 A limit binds before 2.1 MW
Dead-in-tow standby (72 V battery)
72 V battery capacity (Ah) | 650 | GP40-V spec battery (Deka East Penn 650 Ah)
Nominal voltage (V) | 72
Allowed depth of discharge | 50% | Assumption for lead-acid
Usable 72 V energy (kWh)
Lean monitoring load (W) | 60 | Assumption: BCUs 36 W + ETH switch + cellular modem
Full monitoring load (W) | 260 | Assumption: + VMS ~50 W, Starlink ~50 W, gateway, VIO, UPS
Tow duration (h) | 252 | 1.5 weeks worst case (10/6 stand-up)
Lean mode energy over tow (kWh)
Full mode energy over tow (kWh)
Lean mode endurance (days)
Full mode endurance (days)
Tow SOC window (traction pack)
Energy needed at JAX before charging infra (MWh) | 0.3 | Assumption: recommission + 20-min run + yard moves
Reserve floor (fraction) | 15% | Assumption
Minimum tow SOC
Proposed maximum tow SOC | 50% | Proposal; confirm with CSX hazmat
Yard duty (CSX4091 model, v1.4)
Battery energy per yard day (kWh) | 813 | decompose_csx4091, 25.5 h Jacksonville yard trace, Rev C, regen off
Days per charge in usable window |  | Usable window from B3
Aux + TMS share of daily energy | 0.38 | RSK-NEW-55